Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-011-2018 | Application approval for Substituted Service for Richard Francis Calcutta - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>,<em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice andProcedure is hereby varied to permit service upon Richard Francis Calcutta of anysection 104 application in respect of the Property to be effected in the manner specifiedin paragraph 1(a), above, provided that the measures specified in paragraph 1(a) arecarried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-011-2018 | Application approval for Substituted Service for Richard Francis Calcutta - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and anysection 104(1) application made pursuant to this Order, should clearly indicate &quot;RichardFrancis Calcutta&quot; as a registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-011-2018 | Application approval for Substituted Service for Richard Francis Calcutta - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon Richard Francis Calcuttapursuant to this Order, and any section 104(1) application made pursuant to this Order,will be deemed to have been served 10 business days following the day on which all themethods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-011-2018 | Application approval for Substituted Service for Richard Francis Calcutta - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service ofsection 34(1)(a) notices upon Richard Francis Calcutta in respect of the Property, as wellas the date of expiration of the 30 day period within which owners may file writtenstatements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-011-2018 | Application approval for Substituted Service for Richard Francis Calcutta - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of Richard Francis Calcutta, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-011-2018 | Application approval for Substituted Service for Richard Francis Calcutta - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Richard Francis Calcutta shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon DarleneSharon Grandbois of the notices required to be served pursuant to sections 34(1)(a) and104(2) of the NEB Act, may be effected in respect of the Property by:<br />a.Leaving copies of the notice and a true copy of this Order with Darlene SharonGrandbois and Richard Francis Calcutta; or, in the alternative, by mailing thenotices and a true copy of this Order by registered mail to Darlene SharonGrandbois at both her last known address and the address on the Land TitleCertificate; and to Richard Francis Calcutta at both his last known address andthe address on the Land Title Certificate; and<br />b.Publication of a copy of the notices in a single copy of the North ThompsonTimes and the Surrey Now-Leader, in both official languages.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon DarleneSharon Grandbois of notices required to be served on the owners of lands pursuant tosection 87(1) of the NEB Act may be effected in respect of the Property in the mannerspecified in paragraph 1(a), above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>,<em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice andProcedure is hereby varied to permit service upon Darlene Sharon Grandbois of anysection 104 application in respect of the Property to be effected in the manner specifiedin paragraph 1(a), above, provided that the measures specified in paragraph 1(a) arecarried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and anysection 104(1) application made pursuant to this Order, should clearly indicate &quot;DarleneSharon Grandbois&quot; as a registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices upon Darlene Sharon Grandbois pursuantto this Order, and any section 104(1) application made pursuant to this Order, will bedeemed to have been served 10 business days following the day on which all themethods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service ofsection 34(1)(a) notices upon Darlene Sharon Grandbois in respect of the Property, aswell as the date of expiration of the 30 day period within which owners may file writtenstatements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of Darlene Sharon Grandbois, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-010-2018 | Application approval for Substituted Service for Darlene Sharon Grandbois - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | Revoked |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Darlene Sharon Grandbois shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon James C. Kavanagh of the notices required to be served pursuant to paragraph 34(1)(a) and 104(2) of the NEB Act may be effected in respect of the Property by:<br />a. Leaving copies of the notice and a true copy of this Order with Kay Fabbri-Benham and M. Doreen Appleby or, in the alternative, by mailing the notices and a true copy of this Order by registered mail to both Kay Fabbri-Benham and M. Doreen Appleby at the last known address of each; and<br />b. Publication of a copy of the notice in a single copy of the Vancouver Sun, the Langley Times, and the Langley Advance, in both official languages; and<br />c. Publication of a copy of the notice in a single copy of the Norwalk Hour and the La Jolla Light.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon James C. Kavanagh of notices required to be served on the owners of lands pursuant to section 87(1) of the NEB Act may be effected in respect of the Property in the manner specified in paragraph 1(a) above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>, <em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice and Procedure is hereby varied to permit service upon James C. Kavanagh of any section 104 application in respect of the Property to be effected in the manner specified in paragraph 1(a), above, provided that the measures specified in paragraph 1(a) are carried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and any section 104(1) application made pursuant to this Order, should clearly indicate &quot;James C. Kavanagh&quot; as the registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon James C. Kavanagh pursuant to this Order, and any section 104(1) application made pursuant to this Order, will be deemed to have been served 10 business days following the day on which all the methods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of section 34(1)(a) notices upon James C. Kavanagh in respect of the Property, as well as the date of expiration of the 30 day period within which owners may file written statements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of James C. Kavanagh, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any 34(1)(a), 87(1), and 104(2) notices by way of substituted service to James C. Kavanagh shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-015-2018 | approved application for Substituted Service for James C. Kavanagh - Trans Mountain Expansion Project. | 2018-02-06 | 2018-02-06 |  | In Progress |  | 9 | <br />Trans Mountain shall publish a notice for the Property in support of the application which will set out both Parcel Identifier Numbers for the Property in the Vancouver Sun, the Langley Times, and the Langley Advance, in both official languages.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Theresa McMahon of the notices required to be served pursuant to paragraphs 34(1)(a) and 104(2) of the NEB Act, may be effected in respect of the Property by:<br />a. Mailing the notices and a true copy of this Order by registered mail to Theresa McMahon, at both her last known address and the address on the Land Titles Certificate; and<br />b. Publication of a copy of the notices in a single copy of the North Thompson Times, in both official languages; and<br />c. Publication of a copy of the notices in a single copy of the Sierra Sun.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Theresa McMahon of notices required to be served on the owners of lands pursuant to section 87(1) of the NEB Act may be effected in respect of the Property in the manner specified in paragraph 1(a), above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>, <em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice and Procedure is hereby varied to permit service upon Theresa McMahon of any section 104 application in respect of the Property to be effected in the manner specified in paragraph 1(a), above, provided that the measures specified in paragraph 1(a) are carried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and any section 104(1) application made pursuant to this Order, should clearly indicate &quot;Theresa McMahon&quot; as a registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon Theresa McMahon pursuant to this Order, and any section 104(1) application made pursuant to this Order, will be deemed to have been served 10 business days following the day on which all the methods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 6 | <br /><br />Trans Mountain shall advise the Board in writing of the effective date of service of section 34(1)(a) notices upon Theresa McMahon in respect of the Property, as well as the date of expiration of the 30 day period within which owners may file written statements of objection to the proposed detailed pipeline route.<br /><br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of Theresa McMahon, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-018-2018 | An order authorizing substituted service of notices required under sections 34(1)(a), 87(1), and 104(2) of the National Energy Board Act, and for service of section 104(1) applications made pursuant to the National Energy Board Act. We believe that for this application, Trans Mountain’s attempts to effect personal service have been reasonable. With this order, Trans Mountain would not have to reapply for substituted service for the individuals named. | 2018-02-09 | 2018-02-09 |  | In Progress |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Theresa McMahon shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Joyce Eleanor Van Veelen of the notices required to be served pursuant to sections 34(1)(a) and 104(2) of the NEB Act may be effected in respect of the Property by:<br />a. Leaving copies of the notices and a true copy of this Order with both Brian Van Veelen and William Van Veelen or, in the alternative, by mailing the notices and a true copy of this Order by registered mail to Brian Van Veelen and William Van Veelen at the last known address of each; and<br />b. Publication of a copy of the notices in a single copy of the Wabamun Community Voice and the Red Deer Advocate (a local newspaper circulated in the area in which the owner of the Property last resided), in both official languages.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Joyce Eleanor Van Veelen of notices required to be served on the owners of lands pursuant to section 87(1) of the NEB Act may be effected in respect of the Property in the manner specified in paragraph 1(a) above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>, <em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice and Procedure is hereby varied to permit service upon Joyce Eleanor Van Veelen of any section 104 application in respect of the Property to be effected in the manner specified in paragraph 1(a), above, provided that the measures specified in paragraph 1(a) are carried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and any section 104(1) application made pursuant to this Order, should clearly indicate &quot;Joyce Eleanor Van Veelen&quot; as the registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon Joyce Eleanor Van Veelen pursuant to this Order, and any section 104(1) application made pursuant to this Order, will be deemed to have been served 10 business days following the day on which all the methods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of section 34(1)(a) notices upon Joyce Eleanor Van Veelen in respect of the Property, as well as the date of expiration of the 30 day period within which owners may file written statements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of upon Joyce Eleanor Van Veelen, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-009-2018 | Application approval for Substituted Service for Joyce Eleanor Van Veelen - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Joyce Eleanor Van Veelen shall be accompanied by a true copy of this Order (and its accompanying correspondence)<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Julia Ewashko of the notices required to be served pursuant to sections 34(1)(a) and 104(2) of the NEB Act may be effected in respect of the Property by:<br />a. Leaving copies of the notices and a true copy of this Order with John Edward Ewashko or, in the alternative, by mailing the notices and a true copy of this Order by registered mail to John Edward Ewashko at his last known address; and<br />b. Publication of a copy of the notice in a single copy of the Wabamun Community Voice and the Spruce Grove Examiner (a local newspaper circulated in the area in which the owner of the Property last resided) in both official languages.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Julia Ewashko of notices required to be served on the owners of lands pursuant to section 87(1) of the NEB Act may be effected in respect of the Property in the manner specified in paragraph 1(a) above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>, <em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice and Procedure is hereby varied to permit service upon Julia Ewashko of any section 104 application in respect of the Property to be effected in the manner specified in paragraph 1(a), above, provided that the measures specified in paragraph 1(a) are carried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and any section 104(1) application made pursuant to this Order, should clearly indicate &quot;Julia Ewashko&quot; as a registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon Julia Ewashko pursuant to this Order, and any section 104(1) application made pursuant to this Order, will be deemed to have been served 10 business days following the day on which all the methods of substituted service ordered by the Board have been carried out<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of section 34(1)(a) notices upon Julia Ewashko in respect of the Property, as well as the date of expiration of the 30 day period within which owners may file written statements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of Julia Ewashko, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-008-2018 | Application approval for Substituted Service for Julia Ewashko.- Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Julia Ewashko shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Alice Kalinowski of the notices required to be served pursuant to sections 34(1)(a) and 104(2) of the NEB Act, may be effected in respect of the Property by:<br />a. Leaving copies of the requisite notice and a true copy of this Order with Alice Kalinowski, Katherine Shuttle, and Victor Kalinowski; or, in the alternative, by mailing the notices and a true copy of this Order by registered mail to Alice Kalinowski to the addresses listed on title for Alice Kalinowski, as well as her last known address; and to Katherine Shuttle and Victor Kalinowski, at their the last known addresses; and<br />b. Publication of a copy of the notice in a single copy of the Edson Leader and the Wabamun Community Voice, in both official languages.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Alice Kalinowski of notices required to be served on the owners of lands pursuant to section 87(1) of the NEB Act may be effected in respect of the Property in the manner specified in paragraph 1(a) above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>, <em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice and Procedure is hereby varied to permit service upon Alice Kalinowski of any section 104 applications in respect of the Property to be effected in the manner specified in paragraph 1(a), above, provided that the measures specified in paragraph 1(a) are carried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and any section 104(1) application made pursuant to this Order, should clearly indicate &quot;Alice Kalinowski&quot; as a registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon Alice Kalinowski pursuant to this Order, and any section 104(1) application made pursuant to this Order, will be deemed to have been served 10 business days following the day on which all the methods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of section 34(1)(a) notices upon Alice Kalinowski in respect of the Property, as well as the date of expiration of the 30 day period within which owners may file written statements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of Alice Kalinowski, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-012-2018 | Application approval for Substituted Service for Alice/Alexandra Kalinowksi - Trans Mountain Expansion Project | 2018-02-05 | 2018-02-05 |  | In Progress |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Alice Kalinowski shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 1 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Balwinder Kaur Ghag of the notices required to be served pursuant to sections 34(1)(a) and 104(2) of the NEB Act may be effected in respect of the Property by:<br />a. Leaving copies of the notices and a true copy of this Order with Balwinder Kaur Ghag or, in the alternative, by mailing the notices and a true copy of this Order by registered mail to Balwinder Kaur Ghag at 44843 South Sumas Road, Chilliwack BC V2R 2Y2 which is the address of residence or place of business of Balwinder Kaur Ghag and at 44495 Watson Road, Chilliwack, BC V2R 2Y2 which is the address of any other place thought to be frequented by Balwinder Kaur Ghag; by mailing the notices and a true copy of this Order by registered mail to Swarn Singh Ghag and Gurmit Kaur Ghag, who are located at 44843 South Sumas Road, Chilliwack, BC V2R 2Y2; by mailing the notices and a true copy of this Order by registered mail to the mother of Balwinder Kaur Ghag, who is located at 44594 Watson Road, Chilliwack, BC V2R 2Y2; and by serving the notice on an adult resident of the Property at issue in person or by registered mail; and<br />b. Publication of a copy of the notice in a single copy of the Chilliwack Progress, in both official languages;<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 2 | <br />Pursuant to section 3 of the Substituted Service Regulations, service upon Balwinder Kaur Ghag of notices required to be served on the owners of lands pursuant to section 87(1) of the NEB Act may be effected in respect of the Property in the manner specified in paragraph 1(a) above.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 3 | <br />Pursuant to section 4(1) of the <em>National Energy Board Rules of Practice and Procedure</em>, <em>1995 </em>(Rules of Practice and Procedure), section 55(2) of the Rules of Practice and Procedure is hereby varied to permit service upon Balwinder Kaur Ghag of any section 104 application in respect of the Property to be effected in the manner specified in paragraph 1(a), above, provided that the measures specified in paragraph 1(a) are carried out on the same day on which the application is filed with the Board.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 4 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served pursuant to this Order, and any section 104(1) application made pursuant to this Order, should clearly indicate &quot;Balwinder Kaur Ghag&quot; as a registered owner of the Property.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 5 | <br />Any section 34(1)(a), 87(1) and 104(2) notices served upon Balwinder Kaur Ghag pursuant to this Order, and any section 104(1) application made pursuant to this Order, will be deemed to have been served 10 business days following the day on which all the methods of substituted service ordered by the Board have been carried out.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 6 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of section 34(1)(a) notices upon Balwinder Kaur Ghag in respect of the Property, as well as the date of expiration of the 30 day period within which owners may file written statements of objection to the proposed detailed pipeline route.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 7 | <br />Trans Mountain shall advise the Board in writing of the effective date of service of any section 104(1) application made in respect of Balwinder Kaur Ghag, as well as the date of expiration of the 10 day period within which owners may file written statements of objection to the section 104(1) application.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | MO-065-2018 | Right of Entry TMEP - Balwinder Kaul Ghag | 2018-07-12 | 2018-07-12 |  | Revoked |  | 8 | <br />Pursuant to section 6 of the Substituted Service Regulations, service of any section 34(1)(a), 87(1), and 104(2) notices by way of substituted service to Balwinder Kaur Ghag shall be accompanied by a true copy of this Order (and its accompanying correspondence).<br />&nbsp; | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-017-2018 | Order to approve PPBoRs for Richardson Segment 4 | 2018-08-02 | 2018-08-03 |  | Revoked | Cariboo/British Columbia | 1 | <p>Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-017-2018 | Order to approve PPBoRs for Richardson Segment 4 | 2018-08-02 | 2018-08-03 |  | Revoked | Cariboo/British Columbia | 2 | <p>Trans Mountain shall file with the Board, and provide to Mr. John Richardson and Mr. Robert McMahon, within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:</p>i. the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii. the estimated timelines associated with the fulfillment of each commitment; | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-017-2018 | Order to approve PPBoRs for Richardson Segment 4 | 2018-08-02 | 2018-08-03 |  | Revoked | Cariboo/British Columbia | 3 | <p>Trans Mountain shall file with the Board, within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or Board Decision for MH-078-2017; and</p> | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-017-2018 | Order to approve PPBoRs for Richardson Segment 4 | 2018-08-02 | 2018-08-03 |  | Revoked | Cariboo/British Columbia | 4 | <p>Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Board under this Order.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-014-2018 | Approval of PPBoR - Fraser Heights and Min Guo | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 1 | <p>Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-014-2018 | Approval of PPBoR - Fraser Heights and Min Guo | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 2 | <p>Trans Mountain shall file with the Board, and provide to the Fraser Heights Community Association and Ms. Min Guo, within 30 days of the issuance of this Order, a Commitments Table listing all commitments made by Trans Mountain in its detailedroute application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />&nbsp;&nbsp;&nbsp; i.the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />&nbsp;&nbsp;&nbsp; ii.the estimated timelines associated with the fulfillment of each commitment;</p> | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-014-2018 | Approval of PPBoR - Fraser Heights and Min Guo | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 3 | <p>Trans Mountain shall file with the Board within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or Board Decision for MH-036-2017 and MH-053-2017; and</p> | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-014-2018 | Approval of PPBoR - Fraser Heights and Min Guo | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 4 | <p>Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Board under this Order.</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-013-2018 | Approval of PPBoR - City of Coquitlam | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 1 | <p>Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-013-2018 | Approval of PPBoR - City of Coquitlam | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 2 | <p>Trans Mountain shall file with the Board, and provide to the City of Coquitlam, within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />&nbsp;&nbsp;&nbsp; i.the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />&nbsp;&nbsp;&nbsp; ii.the estimated timelines associated with the fulfillment of each commitment;</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-013-2018 | Approval of PPBoR - City of Coquitlam | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 3 | <p>Trans Mountain shall file with the Board within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or Board Decision for MH-034-2017; and</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-013-2018 | Approval of PPBoR - City of Coquitlam | 2018-08-27 | 2018-08-29 |  | Revoked | Lower Mainland--Southwest /British Columbia | 4 | <p>Trans Mountain shall maintain, at its construction office(s), a copy of this Order and any filings made to the Board under this Order.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-018-2018 | Order to approve certain portions of Segment 2 PPBoRs Petterson/Maitland/Sarango/Murray. | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 1 | <p>Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Board otherwise directs.</p> | In Progress | Post Construction Phase | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-018-2018 | Order to approve certain portions of Segment 2 PPBoRs Petterson/Maitland/Sarango/Murray. | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 2 | <p>Trans Mountain shall file with the Board, and provide to Ms. Victoria Maitland and Mr. John Gordon McKay, Ms. Dianne Murray, Mr. Keelan Petterson, and Mr. Javier and Mrs. Annemarie Sarango, within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />&nbsp;&nbsp;&nbsp; i. the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />&nbsp;&nbsp;&nbsp; ii. the estimated timelines associated with the fulfillment of each commitment;</p> | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-018-2018 | Order to approve certain portions of Segment 2 PPBoRs Petterson/Maitland/Sarango/Murray. | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 3 | <p>Trans Mountain shall file with the Board, within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearings or Board Decisions for MH-017-2017 (Ms. Dianne Murray), MH-026-2017 (Mr. Javier and Mrs. Annemarie Sarango), and MH-060-2017 (Ms. Victoria Maitland and Mr. John Gordon McKay).</p> | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-018-2018 | Order to approve certain portions of Segment 2 PPBoRs Petterson/Maitland/Sarango/Murray. | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 4 | <p>Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Board under this Order.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-018-2018 | Order to approve certain portions of Segment 2 PPBoRs Petterson/Maitland/Sarango/Murray. | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Residence and its Foundation(a) Prior to Construction) <p>The Board directs Trans Mountain, <strong>prior to construction on or adjacent to the landowner lands</strong>, to:<br />&nbsp;&nbsp;&nbsp; a.1) conduct a pre-construction inspection of the landowner residence and its foundation;<br />&nbsp;&nbsp;&nbsp; a.2) prepare a <strong>pre-construction inspection report </strong>which will include, at a minimum, documentation including photographs of the pre-construction condition of the residence and foundation;<br />&nbsp;&nbsp;&nbsp; a.3) provide the landowner with a copy of the pre-construction inspection report; and<br />&nbsp;&nbsp;&nbsp; a.4) file with the Board, <strong>at least 15 days prior to the commencement of construction on or adjacent to the landowner lands</strong>, confirmation that it has fulfilled this requirement.</p>(b) After Construction and Final Clean-up) <p>The Board directs Trans Mountain, <strong>12 months after completing final clean-up on or adjacent to the landowner lands</strong>, to:<br />&nbsp;&nbsp;&nbsp; b.1) conduct a post-construction inspection of the items documented in the pre-construction inspection report;<br />&nbsp;&nbsp;&nbsp; b.2) provide a copy of the post-construction inspection report to the landowner; <strong>and</strong><br />&nbsp;&nbsp;&nbsp; b.3) file with the Board a confirmation that it has fulfilled this requirement.</p>(c) After Construction and Final Clean-up) <p>Trans Mountain must file with the Board, <strong>6 months following the completion of the post-construction inspection report</strong>:<br />&nbsp;&nbsp;&nbsp; c.1) confirmation that no new damage, other than that noted in the pre-construction report, was identified in the post-construction inspection report; <strong>or</strong><br />&nbsp;&nbsp;&nbsp; c.2) should any new damage be noted in the post-construction inspection report that was not present in the pre-construction report Trans Mountain is required to:<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; 1. confirm that work to repair any new damage has been completed by qualified professionals and has restored the landowner&rsquo;s residence and/or foundation to its pre-construction condition; <strong>or</strong><br /><strong>&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong>2. provide a timeline for when the repairs are planned to be completed; <strong>or</strong><br /><strong>&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong>3. provide justification that Trans Mountain determined the damage was not caused by construction.</p> | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-018-2018 | Order to approve certain portions of Segment 2 PPBoRs Petterson/Maitland/Sarango/Murray. | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 6 | Septic System(a)) <p>The Board directs Trans Mountain, <strong>prior to construction on or adjacent to the landowner lands</strong>, to:<br />&nbsp;&nbsp;&nbsp; a.1) have a professional installer conduct an inspection of the landowner&rsquo;s septic system to complete a pre-construction functional analysis and prepare a pre-construction septic system inspection report (<strong>pre-construction septic report</strong>) for the current system;<br />&nbsp;&nbsp;&nbsp; a.2) provide a copy of the pre-construction septic report to the landowner;&nbsp;<br />&nbsp;&nbsp;&nbsp; a.3) locate and mark the septic system including the tank and tile field; <strong>and&nbsp;<br />&nbsp;&nbsp;&nbsp;</strong> a.4) file with the Board, <strong>at least 15 days prior to the commencement of construction on or adjacent to the landowner lands</strong>, confirmation that it has fulfilled these requirements<strong>.</strong></p>(b)) <p>The Board directs Trans Mountain, <strong>within 60 days after completing final clean-up on or adjacent to the landowner lands</strong>, to:<br />&nbsp;&nbsp;&nbsp; b.1) re-inspect the septic system to complete a post-construction functional analysis and prepare a post-construction septic system inspection report (<strong>post-construction septic report</strong>);<br />&nbsp;&nbsp;&nbsp; b.2) provide a copy of post-construction septic report to the landowner; <strong>and </strong><br />&nbsp;&nbsp;&nbsp; b.3) file confirmation with the Board that:<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; 1. no new damage was identified in the post-construction septic report; <strong>or </strong><br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; 2. should any new damage be noted in the post-construction septic report that was not present in the pre-construction septic report, Trans Mountain is required to:<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; a. confirm that work to repair any new damage has been completed by qualified professionals and has restored the landowner&rsquo;s septic system to, at a minimum, its pre-construction condition; or<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; b. provide a timeline for when the repairs are planned to be completed; <strong>or</strong><br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; c. provide justification that Trans Mountain determined the damage was not caused by construction.</p>(c)) <p>The Board further directs Trans Mountain <strong>18 months after completing final clean-up </strong>to:<br />&nbsp;&nbsp;&nbsp; c.1) re-inspect the septic system to complete a post-construction functional analysis and prepare a final septic system inspection report (<strong>final septic report</strong>);<br />&nbsp;&nbsp;&nbsp; c.2) provide a copy of the final septic report to the landowner; <strong>and </strong><br />&nbsp;&nbsp;&nbsp; c.3) file confirmation with the Board that:<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; 1. no new damage was identified in the final septic report; <strong>or&nbsp; </strong><br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; 2. should any new damage be noted in the final septic report that was not present in the pre-construction or post-construction septic reports, Trans Mountain is required to:&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; a. confirm that work to repair any new damage has been completed by qualified professionals and has restored the landowner&rsquo;s septic system to, at a minimum, its pre-construction condition; or<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; b. provide a timeline for when the repairs are planned to be completed; <strong>or </strong><br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; c. provide justification that Trans Mountain determined the damage was not caused by construction.</p> | In Progress | Includes all Phases of Constr. | Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-019-2018 | Approval of Cribb Construction PPBoR order | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 1 | <p>Trans Mountain shall comply with all of the conditions contained in this Order and all commitments made during the detailed route hearing, unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-019-2018 | Approval of Cribb Construction PPBoR order | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 2 | <p>Trans Mountain shall file with the Board, and provide to Cribb Construction Ltd., within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />&nbsp;&nbsp;&nbsp; i. the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />&nbsp;&nbsp;&nbsp; ii. the estimated timelines associated with the fulfillment of each commitment;</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-019-2018 | Approval of Cribb Construction PPBoR order | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 3 | <p>Trans Mountain shall file with the Board within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or Board decision for MH-010-2017; and</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-019-2018 | Approval of Cribb Construction PPBoR order | 2018-08-02 | 2018-08-03 |  | Revoked | Banff--Jasper--Rocky Mountain House/Alberta | 4 | <p>Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Board under this Order.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-012-2018 | Approval of PPBoR - City of Burnaby and Underhill | 2018-07-09 | 2018-07-09 |  | Revoked | Lower Mainland--Southwest /British Columbia | 1 | <p>Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Board otherwise directs;</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-012-2018 | Approval of PPBoR - City of Burnaby and Underhill | 2018-07-09 | 2018-07-09 |  | Revoked | Lower Mainland--Southwest /British Columbia | 2 | <p>Trans Mountain shall file with the Board, and provide to the City of Burnaby, the Burnaby Residents, and Underhill Lands Ltd., within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />&nbsp;&nbsp;&nbsp; i. the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />&nbsp;&nbsp;&nbsp; ii. the estimated timelines associated with the fulfillment of each commitment;</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-012-2018 | Approval of PPBoR - City of Burnaby and Underhill | 2018-07-09 | 2018-07-09 |  | Revoked | Lower Mainland--Southwest /British Columbia | 3 | <p>Trans Mountain shall file with the Board, within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or Board Decisions for MH-046-2017 (Underhill Lands Ltd.); MH-049-2017, MH-050-2017, MH-051-2017, MH-052-2017, MH-057-2017 and MH-058-2017 (Burnaby Residents); and MH-033-2017 (City of Burnaby); and</p> | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required
Trans Mountain Pipeline ULC | Trans Mountain Pipeline Expansion Project | Construct Trans Mountain Pipeline Expansion | In Progress | OPL-T260-012-2018 | Approval of PPBoR - City of Burnaby and Underhill | 2018-07-09 | 2018-07-09 |  | Revoked | Lower Mainland--Southwest /British Columbia | 4 | <p>Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Board under this Order.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required
Trans Mountain Pipeline ULC | Trans Mountain s. 45 application to decommission facilities at Edson Pump Station | Decommission Facilities Edson Pump Station | Completed | MO-019-2014 |  | 2014-05-12 | 2014-05-12 |  | All Conditions Met | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45 application to decommission facilities at Edson Pump Station | Decommission Facilities Edson Pump Station | Completed | MO-019-2014 |  | 2014-05-12 | 2014-05-12 |  | All Conditions Met | Edmonton/Alberta | 2 | Trans Mountain shall decommission/deactivate and maintain the Edmonton Terminal Facilities in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45 application to decommission facilities at Edson Pump Station | Decommission Facilities Edson Pump Station | Completed | MO-019-2014 |  | 2014-05-12 | 2014-05-12 |  | All Conditions Met | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 45 application to decommission facilities at Edson Pump Station | Decommission Facilities Edson Pump Station | Completed | MO-019-2014 |  | 2014-05-12 | 2014-05-12 |  | All Conditions Met | Edmonton/Alberta | 4 | Within 30 days this order, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Standard | Filing Not Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain s. 45 & 44 application to decommission facilities and deactivate facilities at Edmonton Terminal | Decommission & Deactivate Facilities at Edmonton Terminal | Completed | MO-020-2014 |  | 2014-05-13 | 2014-05-13 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | Tans Mountain shall comply with all of the conditions contained in this Order unless theBoard otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45 & 44 application to decommission facilities and deactivate facilities at Edmonton Terminal | Decommission & Deactivate Facilities at Edmonton Terminal | Completed | MO-020-2014 |  | 2014-05-13 | 2014-05-13 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain shall decommission and maintain the Edson Pump Station in accordance ith the specifications, standards, commitments made and other information referred to n its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45 & 44 application to decommission facilities and deactivate facilities at Edmonton Terminal | Decommission & Deactivate Facilities at Edmonton Terminal | Completed | MO-020-2014 |  | 2014-05-13 | 2014-05-13 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 45 & 44 application to decommission facilities and deactivate facilities at Edmonton Terminal | Decommission & Deactivate Facilities at Edmonton Terminal | Completed | MO-020-2014 |  | 2014-05-13 | 2014-05-13 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of this Order, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountatin ULC - s. 58 application - Edmonton Terminal - Additional pumps, piping and facilities | Upgrade pumps, piping and facilities at Edmonton Terminal | Completed | XO-T260-011-2014 | IT IS ORDERED that, pursuant to sections 20 and 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is approved and exempt from the provisions of paragraph 30 (1)(a) and section 31of the NEB Act, subject to the following conditions:... | 2014-07-10 | 2014-07-10 | 2015-07-10 | All Conditions Met | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Unspecified | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountatin ULC - s. 58 application - Edmonton Terminal - Additional pumps, piping and facilities | Upgrade pumps, piping and facilities at Edmonton Terminal | Completed | XO-T260-011-2014 | IT IS ORDERED that, pursuant to sections 20 and 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is approved and exempt from the provisions of paragraph 30 (1)(a) and section 31of the NEB Act, subject to the following conditions:... | 2014-07-10 | 2014-07-10 | 2015-07-10 | All Conditions Met | Edmonton/Alberta | 2 | Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application and in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountatin ULC - s. 58 application - Edmonton Terminal - Additional pumps, piping and facilities | Upgrade pumps, piping and facilities at Edmonton Terminal | Completed | XO-T260-011-2014 | IT IS ORDERED that, pursuant to sections 20 and 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is approved and exempt from the provisions of paragraph 30 (1)(a) and section 31of the NEB Act, subject to the following conditions:... | 2014-07-10 | 2014-07-10 | 2015-07-10 | All Conditions Met | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application and in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountatin ULC - s. 58 application - Edmonton Terminal - Additional pumps, piping and facilities | Upgrade pumps, piping and facilities at Edmonton Terminal | Completed | XO-T260-011-2014 | IT IS ORDERED that, pursuant to sections 20 and 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is approved and exempt from the provisions of paragraph 30 (1)(a) and section 31of the NEB Act, subject to the following conditions:... | 2014-07-10 | 2014-07-10 | 2015-07-10 | All Conditions Met | Edmonton/Alberta | 4 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountatin ULC - s. 58 application - Edmonton Terminal - Additional pumps, piping and facilities | Upgrade pumps, piping and facilities at Edmonton Terminal | Completed | XO-T260-011-2014 | IT IS ORDERED that, pursuant to sections 20 and 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is approved and exempt from the provisions of paragraph 30 (1)(a) and section 31of the NEB Act, subject to the following conditions:... | 2014-07-10 | 2014-07-10 | 2015-07-10 | All Conditions Met | Edmonton/Alberta | 5 | Unless the Board otherwise directs prior to 10 July 2015, this Order shall expire on 10 July 2015 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 2 | Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 4 | Trans Mountain shall construct the crossing of the McLeod River using the horizontal directional drill method or, if this is not feasible, shall apply to the Board for approval of an alternative crossing technique and include an environmental assessment of the proposed alternative with its application. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 5 | Trans Mountain shall file with the Board, at least 15 days prior to the commencement of construction activities:a. a copy of the letter of clearance received under the Alberta Historical Resources Act confirming that Trans Mountain has obtained all of the required palaeontological, archeological, and heritage resource permits and clearances; and;b. a statement on how Trans Mountain intends to implement any comments or recommendations contained in the permits and clearances referred to in (a). | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 6 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - McLeod River HDD Pipe Replacement Project | Replace McLeod River HDD Pipe | Completed | XO-T260-017-2014 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the applied-for Project, as specified in Schedule A, is exempt from the provisions of paragraph 30(1)(a), and section 31 of the NEB Act subject to the following conditions:... | 2014-09-03 | 2014-09-03 | 2015-09-03 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta, Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia | 7 | Unless the Board otherwise directs prior to 3 September 2015, this Order shall expire on 3 September 2015 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Section 44 Application by Trans Mountain to deactivate Niton Station | Deactivate Niton Station Section | Completed | MO-119-2014 | IT IS ORDERED that, pursuant to section 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-10-01 | 2014-09-26 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Section 44 Application by Trans Mountain to deactivate Niton Station | Deactivate Niton Station Section | Completed | MO-119-2014 | IT IS ORDERED that, pursuant to section 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-10-01 | 2014-09-26 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain shall deactivate and maintain the Niton Station in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Section 44 Application by Trans Mountain to deactivate Niton Station | Deactivate Niton Station Section | Completed | MO-119-2014 | IT IS ORDERED that, pursuant to section 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-10-01 | 2014-09-26 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Section 44 Application by Trans Mountain to deactivate Niton Station | Deactivate Niton Station Section | Completed | MO-119-2014 | IT IS ORDERED that, pursuant to section 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-10-01 | 2014-09-26 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of this Order, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Includes all Phases of Constr. | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC - Request for Relief from Conditions 2, 4 of Order MO-019-2014 - Decommission and Deactivate Facilities at Edmonton Terminal | Deactivate Facilities at Edmonton Terminal | Completed | AO-001-MO-019-2014 | IT IS ORDERED that, pursuant to subsection 21(1) of the NEB Act, Condition 4 of the Order is amended as follows:... | 2014-09-02 | 2014-09-02 |  | All Conditions Met | Edmonton/Alberta | 4 | Within 30 days following completion of the Project, TransMountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 application - decommissioning of McLeod River Crossing. | Decommission McLeod River Crossing | Completed | MO-129-2014 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-12-09 | 2014-12-09 | 2015-12-09 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | TMPL shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 application - decommissioning of McLeod River Crossing. | Decommission McLeod River Crossing | Completed | MO-129-2014 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-12-09 | 2014-12-09 | 2015-12-09 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | TMPL shall decommission and maintain the McLeod River Crossing in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 application - decommissioning of McLeod River Crossing. | Decommission McLeod River Crossing | Completed | MO-129-2014 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-12-09 | 2014-12-09 | 2015-12-09 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | TMPL shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 application - decommissioning of McLeod River Crossing. | Decommission McLeod River Crossing | Completed | MO-129-2014 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-12-09 | 2014-12-09 | 2015-12-09 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of the date that the decommissioning is completed, TMPL shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, TMPL shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of TMPL. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 application - decommissioning of McLeod River Crossing. | Decommission McLeod River Crossing | Completed | MO-129-2014 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2014-12-09 | 2014-12-09 | 2015-12-09 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 9 December 2015, this Order shall expire on 9 December 2015 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 application to Decommission Piping and Facilities at Edmonton Terminal | Decommission Piping and Facilities at Edmonton Terminal | Completed | MO-002-2015 |  | 2015-02-10 | 2015-02-10 |  | All Conditions Met | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 application to Decommission Piping and Facilities at Edmonton Terminal | Decommission Piping and Facilities at Edmonton Terminal | Completed | MO-002-2015 |  | 2015-02-10 | 2015-02-10 |  | All Conditions Met | Edmonton/Alberta | 2 | Trans Mountain shall decommission and maintain the Edmonton Terminal Facilities in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 application to Decommission Piping and Facilities at Edmonton Terminal | Decommission Piping and Facilities at Edmonton Terminal | Completed | MO-002-2015 |  | 2015-02-10 | 2015-02-10 |  | All Conditions Met | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 application to Decommission Piping and Facilities at Edmonton Terminal | Decommission Piping and Facilities at Edmonton Terminal | Completed | MO-002-2015 |  | 2015-02-10 | 2015-02-10 |  | All Conditions Met | Edmonton/Alberta | 4 | Within 30 days of the issuance of this Order, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC– Edmonton Terminal Expansion Project – Request for extension to comply with Condition 5 of Order XO-T246-04-2008 | Construct Edmonton Terminal Expansion | Completed | AO-007-XO-T246-04-2008 | IT IS ORDERED that, pursuant to subsection 21(1) and section 20 of the NEB Act, Condition 5 of the Order is amended as follows:... | 2015-01-26 | 2015-01-26 |  | All Conditions Met | Edmonton/Alberta | 1 | Within 30 days following completion of the Project, TMI shall file with the Board a confirmation, by an officer of the company, that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC – Edmonton Terminal Additional Pumps, Piping and Facilities Project – Request for extension to comply with Condition 4 of Order XO-T260-011-2014. | Variance XO-T260-011-2014 Condition 4 Extend deadline | Completed | AO-001-XO-T260-011-2014 | IT IS ORDERED that, pursuant to subsection 21(1) and section 20 of the NEB Act, Condition 4 of the Order is amended as follows:... | 2015-01-26 | 2015-01-26 |  | All Conditions Met | Edmonton/Alberta | 1 | Within 30 days following completion of the Project, Trans Mountain shall file with the Board a confirmation, by an officer of the company, that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the company | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | XO-T260-002-2015 |  | 2015-04-24 | 2015-04-24 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | XO-T260-002-2015 |  | 2015-04-24 | 2015-04-24 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | XO-T260-002-2015 |  | 2015-04-24 | 2015-04-24 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | XO-T260-002-2015 |  | 2015-04-24 | 2015-04-24 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | XO-T260-002-2015 |  | 2015-04-24 | 2015-04-24 |  | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 24 April 2016, this Order shall expire on 24 April 2016 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | MO-042-2015 | IT IS ORDERED that, pursuant to ection 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-04-24 | 2015-04-24 | 2016-04-24 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless theBoard otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | MO-042-2015 | IT IS ORDERED that, pursuant to ection 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-04-24 | 2015-04-24 | 2016-04-24 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain shall deactivate and maintain Tank 41 in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | MO-042-2015 | IT IS ORDERED that, pursuant to ection 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-04-24 | 2015-04-24 | 2016-04-24 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | MO-042-2015 | IT IS ORDERED that, pursuant to ection 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-04-24 | 2015-04-24 | 2016-04-24 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of the date that the deactivation is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 58 application - Edson Tank 49 Construction and Tank 41 Deactivation Project | Construct Edson Tank 49 & Deactivate Tank 41 | Completed | MO-042-2015 | IT IS ORDERED that, pursuant to ection 44 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-04-24 | 2015-04-24 | 2016-04-24 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 24 April 2016, this Order shall expire on 24 April 2016 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 OPR application decommission certain facilities and piping at Edson Station. | Decommission Facilities and Piping at Edson Station | Completed | MO-043-2015 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-05-04 | 2015-05-04 | 2016-05-04 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 OPR application decommission certain facilities and piping at Edson Station. | Decommission Facilities and Piping at Edson Station | Completed | MO-043-2015 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-05-04 | 2015-05-04 | 2016-05-04 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain shall decommission and maintain the Project in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 OPR application decommission certain facilities and piping at Edson Station. | Decommission Facilities and Piping at Edson Station | Completed | MO-043-2015 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-05-04 | 2015-05-04 | 2016-05-04 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 OPR application decommission certain facilities and piping at Edson Station. | Decommission Facilities and Piping at Edson Station | Completed | MO-043-2015 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-05-04 | 2015-05-04 | 2016-05-04 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Trans Mountain. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45.1 OPR application decommission certain facilities and piping at Edson Station. | Decommission Facilities and Piping at Edson Station | Completed | MO-043-2015 | IT IS ORDERED that, pursuant to section 45.1 of the OPR, the applied-for Project, as specified in Schedule A, is approved subject to the following conditions:... | 2015-05-04 | 2015-05-04 | 2016-05-04 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 4 May 2016, this Order shall expire on 4 May 2016 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Terasen PIpelines 2004, s 44 application for deactivation of the 43 km, 609.6 mm OD (NPS 24) Darfield to Kamloops pipeline section | Deactivate Darfield to Kamloops pipeline section | Completed | AO-002-XO-T099-005-2004 |  | 2015-05-27 | 2015-05-27 |  | All Conditions Met | Thompson--Okanagan/British Columbia | 1 | Trans Mountain Pipeline ULC shall comply with all of the conditions contained in this Order unless the Board otherwise directs | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Terasen PIpelines 2004, s 44 application for deactivation of the 43 km, 609.6 mm OD (NPS 24) Darfield to Kamloops pipeline section | Deactivate Darfield to Kamloops pipeline section | Completed | AO-002-XO-T099-005-2004 |  | 2015-05-27 | 2015-05-27 |  | All Conditions Met | Thompson--Okanagan/British Columbia | 2 | Trans Mountain Pipeline ULC shall deactivate and maintain the Darfield to Kamloops pipeline in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-042-2015 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 22 April 2017, this Order shall expire on 22 April 2017, unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-043-2015 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 22 April 2017, this Order shall expire on 22 April 2017, unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-020-2014 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain shall comply with all the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-020-2014 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain shall decommission and maintain the Edson Pump Station in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-020-2014 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-020-2014 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 4 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to section 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 21 Variance Applications for MO-020-2014, MO-042-2015 & MO-043-2015 | Variance MO-020-2014, MO-042-2015 and MO-043-2015 | Completed | AO-001-MO-020-2014 | Trans Mountain Pipeline ULC (Trans Mountain) Application to Vary Orders MO-020-2014, MO-042-2015 and MO-043-2015 Pursuant to Section 21 of the National Energy Board Act (NEB Act) | 2016-04-22 | 2016-04-22 | 2017-04-22 | All Conditions Met | Banff--Jasper--Rocky Mountain House/Alberta | 5 | Unless the Board otherwise directs prior to 22 April 2017, this Order shall expire on 22 April 2017, unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-010-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-010-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 2 | Trans Mountain shall deactivate and maintain the approximate 625 meter segment of pipeline in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-010-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-010-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 4 | Within 30 days of the date that the deactivation is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-010-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 5 | Unless the Board otherwise directs prior to 21 February 2018, this Order shall expire on 21 February 2018 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-011-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-011-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 2 | Trans Mountain shall decommission the approximate 45 m segment of pipeline in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-011-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-011-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 4 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannotbe confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 44 Application to deactivate a segment and s. 45.1 Application to decommission a segment of pipeline at Edmonton Terminal | Deactivate & Decommission segment of pipeline at Edmonton Terminal | Completed | MO-011-2017 | Trans Mountain Pipeline ULC (Trans Mountain) – Application to deactivate an approximate 625 m segment of pipeline and to decommission an approximate 45 m segment of pipeline at Edmonton Terminal (the Project) under sections 44 and 45.1 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2017-02-21 | 2017-02-21 | 2018-02-21 | All Conditions Met | Edmonton/Alberta | 5 | Unless the Board otherwise directs prior to 21 February 2018, this Order shall expire on 21 February 2018 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 2 | Subject to condition 5, Trans Mountain shall decommission and maintain the piping at Trans Mountain&rsquo;s Burnaby Terminal in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing decommissioning activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing decommissioning activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 5 | Within 10 business days prior to completing decommissioning activities, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, and/or removal of other inactive infrastructure discovered during excavation activities that do not impact any other information provided in the Application. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 6 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-021-2017 | Application to Decommission Facility Piping at Burnaby Terminal (Project) under section 45.1 | 2017-04-20 | 2017-04-20 |  | Expired | Lower Mainland--Southwest /British Columbia | 7 | Unless the Board otherwise directs prior to 20 April 2018, this Order shall expire on 20 April 2018 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 2 | Subject to condition 5, Trans Mountain shall decommission and maintain the piping at Trans Mountain&rsquo;s Burnaby Terminal in its&nbsp;decommissioned state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing decommissioning activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing decommissioning activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 5 | Within 10 business days prior to completing decommissioning activities, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, and/or removal of other inactive infrastructure discovered during excavation activities that do not impact any other information provided in the Application. | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 6 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain s. 45 OPR application to decommission the facility at Burnaby Terminal | Decommission Facility Piping at Burnaby Terminal | In Progress | MO-066-2018 | Pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Project. Condition 7, the sunset clause, provides a date of 31 December 2018 by which the Project must commence. TMPU Burnaby Terminal | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Lower Mainland--Southwest /British Columbia | 7 | Unless the Board otherwise directs prior to 31 December&nbsp;2018, this Order shall expire on 31 December&nbsp;2018 unless the Project has commenced by that date. | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 2 | Subject to condition 5, Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing construction activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing construction activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 5 | Within 10 business days prior to placing the Project in service, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, diameter, wall thickness, and/or pipe grade that do not impact any other information provided in the Application. | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 6 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the National Energy Board Onshore Pipeline Regulations. | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountains s. 58 to construct relocated facility piping and related infrastructure at Burnaby Terminal. | Relocate Facility Piping and Related Infrastructure at Burnaby Terminal | In Progress | XO-T260-003-2017 | Application for the Burnaby Terminal Facility Piping Relocations (Project) under section 58 approval | 2017-04-20 | 2017-04-20 |  | In Progress |  | 7 | Unless the Board otherwise directs prior to 20 April 2018, this Order shall expire on 20 April 2018 unless construction of the Project has commenced by that date. | In Progress | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 2 | Subject to condition 5, Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing construction activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing construction activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 5 | Within 10 business days prior to placing the Project in service, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, diameter, wall thickness, and/or pipe grade that do not impact any other information provided in the Application. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 6 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the National Energy Board Onshore Pipeline Regulations. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-004-2017 | Application for the Edmonton Terminal Facility Piping Relocations | 2017-04-20 | 2017-04-20 | 2018-04-20 | Expired | Edmonton/Alberta | 7 | Unless the Board otherwise directs prior to 20 April 2018, this Order shall expire on 20 April 2018 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 2 | Subject to condition 5, Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing construction activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing construction activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 5 | Within 10 business days prior to placing the Project in service, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, diameter, wall thickness, and/or pipe grade that do not impact any other information provided in the Application. | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 6 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the National Energy Board Onshore Pipeline Regulations. | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 application - Edmonton Terminal Facility Piping Relocations | Relocate Facility Piping at Edmonton Terminal | In Progress | XO-T260-009-2018 | pursuant to section 58 of the NEB Act, approving the application to relocate, construct and operate piping at Trans Mountain’s Edmonton Terminal | 2018-07-23 | 2018-07-23 |  | In Progress | Edmonton/Alberta | 7 | Unless the Board otherwise directs prior to 31 December 2018, this Order shall expire on&nbsp;31 December&nbsp;2018 unless construction of the Project has commenced by that date. | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 2 | Subject to condition 5, Trans Mountain shall decommission and maintain the piping at Trans Mountain&rsquo;s Burnaby Terminal in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing decommissioning activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing decommissioning activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 5 | Within 10 business days prior to completing decommissioning activities, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, and/or removal of other inactive infrastructure discovered during excavation activities that do not impact any other information provided in the Application. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 6 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-022-2017 | Application to Decommission Facility Piping at Edmonton Terminal | 2017-04-20 | 2017-04-20 |  | Expired | Edmonton/Alberta | 7 | Unless the Board otherwise directs prior to 20 April 2018, this Order shall expire on 20 April 2018 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 2 | Subject to condition 5, Trans Mountain shall decommission and maintain the piping at Trans Mountain&rsquo;s Burnaby Terminal in its decommissioned state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 4 | Trans Mountain shall file with the Board, at least 15 days prior to commencing decommissioning activities, written confirmation that it has notified all potentially affected third parties of the Project at least 20 days prior to commencing decommissioning activities. | Closed | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 5 | Within 10 business days prior to completing decommissioning activities, Trans Mountain shall file with the Board all technical specification updates for the Project. Technical specification updates are limited to difference in pipe length, and/or removal of other inactive infrastructure discovered during excavation activities that do not impact any other information provided in the Application. | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 6 | Within 30 days of the date that the decommissioning is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45.1 OPR Application to Decommission Facility Piping at Edmonton Terminal | Decommission Facility Piping at Edmonton Terminal | In Progress | MO-067-2018 | pursuant to section 45.1 of the National Energy Board Onshore Pipeline Regulations approving the Projects. Condition 7, the sunset clause, in each Order, provides a date of 31 December 2018 by which the Projects must commence. | 2018-07-23 | 2018-07-23 | 2018-12-31 | In Progress | Edmonton/Alberta | 7 | Unless the Board otherwise directs prior to 31 December 2018, this Order shall expire on 31 December 2018 unless the Project has commenced by that date. | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC. s. 58 application - Meter Bank 2 Edmonton Terminal Expansion Project | Construct Meter Bank 2 at Edmonton Terminal | Completed | XO-T260-002-2017 | Trans Mountain Pipeline ULC (Trans Mountain) - Application for the Meter Bank 2 Edmonton Terminal Expansion Project (Project) under section 58 of the National Energy Board Act (NEB Act) | 2017-04-13 | 2017-04-13 | 2018-04-13 | All Conditions Met |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC. s. 58 application - Meter Bank 2 Edmonton Terminal Expansion Project | Construct Meter Bank 2 at Edmonton Terminal | Completed | XO-T260-002-2017 | Trans Mountain Pipeline ULC (Trans Mountain) - Application for the Meter Bank 2 Edmonton Terminal Expansion Project (Project) under section 58 of the National Energy Board Act (NEB Act) | 2017-04-13 | 2017-04-13 | 2018-04-13 | All Conditions Met |  | 2 | Trans Mountain shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC. s. 58 application - Meter Bank 2 Edmonton Terminal Expansion Project | Construct Meter Bank 2 at Edmonton Terminal | Completed | XO-T260-002-2017 | Trans Mountain Pipeline ULC (Trans Mountain) - Application for the Meter Bank 2 Edmonton Terminal Expansion Project (Project) under section 58 of the National Energy Board Act (NEB Act) | 2017-04-13 | 2017-04-13 | 2018-04-13 | All Conditions Met |  | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC. s. 58 application - Meter Bank 2 Edmonton Terminal Expansion Project | Construct Meter Bank 2 at Edmonton Terminal | Completed | XO-T260-002-2017 | Trans Mountain Pipeline ULC (Trans Mountain) - Application for the Meter Bank 2 Edmonton Terminal Expansion Project (Project) under section 58 of the National Energy Board Act (NEB Act) | 2017-04-13 | 2017-04-13 | 2018-04-13 | All Conditions Met |  | 4 | Within 30 days of the date that the approved Project is placed in service, Trans Mountain shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the National Energy Board Onshore Pipeline Regulations. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC. s. 58 application - Meter Bank 2 Edmonton Terminal Expansion Project | Construct Meter Bank 2 at Edmonton Terminal | Completed | XO-T260-002-2017 | Trans Mountain Pipeline ULC (Trans Mountain) - Application for the Meter Bank 2 Edmonton Terminal Expansion Project (Project) under section 58 of the National Energy Board Act (NEB Act) | 2017-04-13 | 2017-04-13 | 2018-04-13 | All Conditions Met |  | 5 | Unless the Board otherwise directs prior to 14 April 2018, this Order shall expire on 14 April 2018 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 Application to Reactivate the Trans Mountain Refined Products Direct Injection Transfer Line. | Reactivate Refined Products Direct Injection Transfer Line | In Progress | MO-004-2018 |  | 2018-01-29 | 2018-01-30 | 2021-01-29 | In Progress | Edmonton/Alberta | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 Application to Reactivate the Trans Mountain Refined Products Direct Injection Transfer Line. | Reactivate Refined Products Direct Injection Transfer Line | In Progress | MO-004-2018 |  | 2018-01-29 | 2018-01-30 | 2021-01-29 | In Progress | Edmonton/Alberta | 2 | Trans Mountain shall reactivate and operate the Direct Injection Transfer Line in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 Application to Reactivate the Trans Mountain Refined Products Direct Injection Transfer Line. | Reactivate Refined Products Direct Injection Transfer Line | In Progress | MO-004-2018 |  | 2018-01-29 | 2018-01-30 | 2021-01-29 | In Progress | Edmonton/Alberta | 3 | Trans Mountain shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 Application to Reactivate the Trans Mountain Refined Products Direct Injection Transfer Line. | Reactivate Refined Products Direct Injection Transfer Line | In Progress | MO-004-2018 |  | 2018-01-29 | 2018-01-30 | 2021-01-29 | In Progress | Edmonton/Alberta | 4 | Trans Mountain shall file with the Board, within 30 days of the date that the reactivation is completed, an Engineering report. The report shall include but not be limited to:<br />a) The results of the coating assessment for underground pipelines;<br />b) The results of the non-destructive examination and details about any repairs performed; and<br />c) A discussion on the above, and on any potential impact on the pipeline sections that have been reactivated. | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 Application to Reactivate the Trans Mountain Refined Products Direct Injection Transfer Line. | Reactivate Refined Products Direct Injection Transfer Line | In Progress | MO-004-2018 |  | 2018-01-29 | 2018-01-30 | 2021-01-29 | In Progress | Edmonton/Alberta | 5 | Within 30 days of the date that the reactivation is completed, Trans Mountain shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Trans Mountain shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Trans Mountain, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 Application to Reactivate the Trans Mountain Refined Products Direct Injection Transfer Line. | Reactivate Refined Products Direct Injection Transfer Line | In Progress | MO-004-2018 |  | 2018-01-29 | 2018-01-30 | 2021-01-29 | In Progress | Edmonton/Alberta | 6 | This Order shall expire on 29 January 2021 unless construction of the Project has commenced by that date.<br />&nbsp; | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 Application for Kamloops Terminal Facility Piping Relocations | Relocate Facility Piping at Kamloops Terminal | In Progress | XO-T260-001-2018 | Application for the Kamloops Terminal Facility Piping Relocations under section 58 of the NEB Act. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 1 | <p>TMPU shall comply with all of the conditions contained in this Order unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 Application for Kamloops Terminal Facility Piping Relocations | Relocate Facility Piping at Kamloops Terminal | In Progress | XO-T260-001-2018 | Application for the Kamloops Terminal Facility Piping Relocations under section 58 of the NEB Act. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 2 | <p>Subject to condition 4, TMPU shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 Application for Kamloops Terminal Facility Piping Relocations | Relocate Facility Piping at Kamloops Terminal | In Progress | XO-T260-001-2018 | Application for the Kamloops Terminal Facility Piping Relocations under section 58 of the NEB Act. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 3 | <p>TMPU shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 Application for Kamloops Terminal Facility Piping Relocations | Relocate Facility Piping at Kamloops Terminal | In Progress | XO-T260-001-2018 | Application for the Kamloops Terminal Facility Piping Relocations under section 58 of the NEB Act. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 4 | <p>At least 10 days prior to placing the facilities in service, TMPU shall file with the Board all technical specification updates for the terminal listed in the Application. Technical specification updates are limited to difference in pipe length, diameter, and/or pipe grade material that do not impact any other information provided in the Application.</p> | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 Application for Kamloops Terminal Facility Piping Relocations | Relocate Facility Piping at Kamloops Terminal | In Progress | XO-T260-001-2018 | Application for the Kamloops Terminal Facility Piping Relocations under section 58 of the NEB Act. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 5 | <p>Within 30 days of the date that the approved Project is placed in service, TMPU shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, TMPU shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of TMPU, appointed as Accountable Officer pursuant to s. 6.2 of the <em>National Energy Board Onshore Pipeline Regulations</em>.</p> | In Progress | Post Construction Phase | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 58 Application for Kamloops Terminal Facility Piping Relocations | Relocate Facility Piping at Kamloops Terminal | In Progress | XO-T260-001-2018 | Application for the Kamloops Terminal Facility Piping Relocations under section 58 of the NEB Act. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 6 | <p>Unless the Board otherwise directs prior to 17 January 2019, this Order shall expire on 17 January 2019 unless construction of the Project has commenced by that date.</p> | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | MO-001-2018 | Application to Decommission Facility Piping at Kamloops Terminal under section 45.1 of the OPR. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 1 | <p>TMPU shall comply with all of the conditions contained in this Order unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | MO-001-2018 | Application to Decommission Facility Piping at Kamloops Terminal under section 45.1 of the OPR. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 2 | <p>TMPU shall decommission the Kamloops Facility Piping in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | MO-001-2018 | Application to Decommission Facility Piping at Kamloops Terminal under section 45.1 of the OPR. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 3 | <p>TMPU shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | MO-001-2018 | Application to Decommission Facility Piping at Kamloops Terminal under section 45.1 of the OPR. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 4 | <p>Within 30 days of the date that the decommissioning is completed, TMPU shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, TMPU shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of TMPU, appointed as Accountable Officer pursuant to s. 6.2 of the OPR.</p> | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | MO-001-2018 | Application to Decommission Facility Piping at Kamloops Terminal under section 45.1 of the OPR. | 2018-01-17 | 2018-01-17 |  | In Progress | Thompson--Okanagan/British Columbia | 5 | <p>Unless the Board otherwise directs prior to 17 January 2019, this Order shall expire on 17 January 2019 unless the Project has commenced by that date.</p> | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | AO-001-MO-001-2018 | Pursuant to subsection 21(1) of the NEB Act, the Order is varied to grant relief requested regarding the expiration date, and to correct the sequential numbering of conditions, by replacing the conditions contained in the Order. | 2018-12-11 | 2018-12-11 |  | In Progress |  | 1 | <p>TMPU shall comply with all of the conditions contained in this Order unless the Board otherwise directs.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | AO-001-MO-001-2018 | Pursuant to subsection 21(1) of the NEB Act, the Order is varied to grant relief requested regarding the expiration date, and to correct the sequential numbering of conditions, by replacing the conditions contained in the Order. | 2018-12-11 | 2018-12-11 |  | In Progress |  | 2 | <p>TMPU shall decommission the Kamloops Facility Piping in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | AO-001-MO-001-2018 | Pursuant to subsection 21(1) of the NEB Act, the Order is varied to grant relief requested regarding the expiration date, and to correct the sequential numbering of conditions, by replacing the conditions contained in the Order. | 2018-12-11 | 2018-12-11 |  | In Progress |  | 3 | <p>TMPU shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions.</p> | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | AO-001-MO-001-2018 | Pursuant to subsection 21(1) of the NEB Act, the Order is varied to grant relief requested regarding the expiration date, and to correct the sequential numbering of conditions, by replacing the conditions contained in the Order. | 2018-12-11 | 2018-12-11 |  | In Progress |  | 4 | <p>Within 30 days of the date that the decommissioning is completed, TMPU shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, TMPU shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of TMPU, appointed as Accountable Officer pursuant to section 6.2 of the OPR.</p> | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | AO-001-MO-001-2018 | Pursuant to subsection 21(1) of the NEB Act, the Order is varied to grant relief requested regarding the expiration date, and to correct the sequential numbering of conditions, by replacing the conditions contained in the Order. | 2018-12-11 | 2018-12-11 |  | In Progress |  | 5 | <p>Unless the Board otherwise directs prior to 31 December 2019, this Order shall expire on 31 December 2019 unless the Project has commenced by that date.</p> | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Pipeline ULC s. 45 OPR Application to Decommission Facility Piping at Kamloops Terminal | Decommission Facility Piping at Kamloops Terminal | In Progress | AO-002-MO-001-2018 | Kamloops Decommissioning Sunset Clause Extension | 2019-12-05 | 2019-12-05 |  | In Progress |  | 5 | Unless the Commission otherwise directs prior to 31 December 2020, this Order shall expire on 31 December 2020 unless the Project has commenced by that date. | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-001-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide TransCanada Keystone Pipeline GP Ltd. (Keystone) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Keystone is required to obtain a $500 million line of credit from its affiliate company, TransCanada PipeLines Limited (TCPL). Subject to this order, Keystone will meet the $1 billion financial resources requirement in accordance with subsecti | 2017-01-05 | 2017-01-05 |  | In Progress |  | 1 | Keystone shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-001-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide TransCanada Keystone Pipeline GP Ltd. (Keystone) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Keystone is required to obtain a $500 million line of credit from its affiliate company, TransCanada PipeLines Limited (TCPL). Subject to this order, Keystone will meet the $1 billion financial resources requirement in accordance with subsecti | 2017-01-05 | 2017-01-05 |  | In Progress |  | 2 | Keystone shall obtain and maintain a line of credit from TCPL, in the amount of at least $500 million CAD. Keystone shall file with the Board for approval, by 28 February 2017, a copy of this line of credit along with a summary of the terms by which Keystone can utilize the line of credit to access funds. At a minimum, this line of credit must: a. provide Keystone with funds on demand and at its sole discretion; b. be irrevocable; c. be non-transferrable and non-assignable; and d. automatically renew and remain in force unless the Board has granted approval of alternative types of financial resources for Keystone.&nbsp;&nbsp; | In Progress | Unspecified | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-001-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide TransCanada Keystone Pipeline GP Ltd. (Keystone) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Keystone is required to obtain a $500 million line of credit from its affiliate company, TransCanada PipeLines Limited (TCPL). Subject to this order, Keystone will meet the $1 billion financial resources requirement in accordance with subsecti | 2017-01-05 | 2017-01-05 |  | In Progress |  | 3 | Keystone shall continue to maintain insurance policies in the amount of at least $500 million (when converted to CAD). Keystone shall file with the Board, by 28 February 2017, a certificate of insurance detailing its insured coverage types and amounts.&nbsp; | In Progress | Unspecified | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-001-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide TransCanada Keystone Pipeline GP Ltd. (Keystone) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Keystone is required to obtain a $500 million line of credit from its affiliate company, TransCanada PipeLines Limited (TCPL). Subject to this order, Keystone will meet the $1 billion financial resources requirement in accordance with subsecti | 2017-01-05 | 2017-01-05 |  | In Progress |  | 4 | Keystone shall notify the Board in writing if there are, or if Keystone has reason to believe that there will be, any material revisions to its financial resources plan. This includes changes to TCPL&rsquo;s financial condition or TCPL&rsquo;s corporate structure such that its ability to provide $500 million in funds via the line of credit to Keystone may be impaired.&nbsp;&nbsp; | In Progress | Unspecified | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-001-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide TransCanada Keystone Pipeline GP Ltd. (Keystone) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Keystone is required to obtain a $500 million line of credit from its affiliate company, TransCanada PipeLines Limited (TCPL). Subject to this order, Keystone will meet the $1 billion financial resources requirement in accordance with subsecti | 2017-01-05 | 2017-01-05 |  | In Progress |  | 5 | Keystone shall provide an update to its plan and file an updated table with the Board consistent with the format requested in NEB IR No. 1.1i) on 10 August 2016, on an annual basis within 30 days of the release of TransCanada Corporation&rsquo;s consolidated annual financial statements. | In Progress | Not Construction Related | Non Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-002-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Trans Mountain Pipeline ULC (Trans Mountain) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Trans Mountain is required to obtain a $500 million line of credit from its affiliate company, Kinder Morgan Inc. Subject to this order, Trans Mountain will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) | 2017-01-05 | 2017-01-05 |  | In Progress |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order unless the Board otherwise directs | In Progress | Not Construction Related | Non Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-002-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Trans Mountain Pipeline ULC (Trans Mountain) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Trans Mountain is required to obtain a $500 million line of credit from its affiliate company, Kinder Morgan Inc. Subject to this order, Trans Mountain will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) | 2017-01-05 | 2017-01-05 |  | In Progress |  | 2 | Trans Mountain shall obtain and maintain a line of credit from Kinder Morgan Inc., in the amount of at least $500 million CAD by 28 February 2017. Trans Mountain shall file with the Board for approval, by 28 February 2017, a copy of this line of credit along with a summary of the terms by which Trans Mountain can utilize the line of credit to access funds. At a minimum, this line of credit must: a. provide Trans Mountain with funds on demand and at its sole discretion; b. be irrevocable; c. be non-transferrable and non-assignable; and d. automatically renew and remain in force unless the Board has granted approval of alternative types of financial resources for Trans Mountain.&nbsp; | In Progress | Not Construction Related | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-002-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Trans Mountain Pipeline ULC (Trans Mountain) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Trans Mountain is required to obtain a $500 million line of credit from its affiliate company, Kinder Morgan Inc. Subject to this order, Trans Mountain will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) | 2017-01-05 | 2017-01-05 |  | In Progress |  | 3 | Trans Mountain shall continue to maintain insurance policies in the amount of at least $500 million (when converted to CAD). Trans Mountain shall file with the Board, by 28 February 2017, a certificate of insurance detailing its insured coverage types and amounts.&nbsp; | In Progress | Not Construction Related | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-002-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Trans Mountain Pipeline ULC (Trans Mountain) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Trans Mountain is required to obtain a $500 million line of credit from its affiliate company, Kinder Morgan Inc. Subject to this order, Trans Mountain will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) | 2017-01-05 | 2017-01-05 |  | In Progress |  | 4 | Trans Mountain shall notify the Board in writing if there are, or if Trans Mountain has reason to believe that there will be, any material revisions to its financial resources. This includes changes to Kinder Morgan Inc.&rsquo;s financial condition or corporate structure such that its ability to provide $500 million in funds via the line of credit to Trans Mountain may be impaired. | In Progress | Not Construction Related | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-002-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Trans Mountain Pipeline ULC (Trans Mountain) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Trans Mountain is required to obtain a $500 million line of credit from its affiliate company, Kinder Morgan Inc. Subject to this order, Trans Mountain will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) | 2017-01-05 | 2017-01-05 |  | In Progress |  | 5 | Trans Mountain shall provide an update to its financial resource requirement plan and file an updated table with the Board consistent with the format requested in NEB IR No. 1.1g) on 10 August 2016, on an annual basis within 30 days of the release of Kinder Morgan Inc.&rsquo;s consolidated annual financial statements.&nbsp; | In Progress | Not Construction Related | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-003-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Express Pipeline Ltd. (Express) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Express is required to obtain a $500 million line of credit from its affiliate company, Spectra Energy Partners, LP (SEP). Subject to this order, Express will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) of the NEB | 2017-01-05 | 2017-01-05 |  | In Progress |  | 1 | Express shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | In Progress | Not Construction Related | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-003-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Express Pipeline Ltd. (Express) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Express is required to obtain a $500 million line of credit from its affiliate company, Spectra Energy Partners, LP (SEP). Subject to this order, Express will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) of the NEB | 2017-01-05 | 2017-01-05 |  | In Progress |  | 2 | Express shall obtain and maintain a line of credit from Spectra Energy Partners, LP, in the amount of at least $500 million CAD by 28 February 2017. Express shall file with the Board for approval, by 28 February 2017, a copy of this line of credit along with a summary of the terms by which Express can utilize the line of credit to access funds. At a minimum, this line of credit must: a. provide Express with funds on demand and at its sole discretion; b. be irrevocable; c. be non-transferrable and non-assignable; and d. automatically renew and remain in force unless the Board has granted approval of alternative types of financial resources for Express. | In Progress | Not Construction Related | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-003-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Express Pipeline Ltd. (Express) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Express is required to obtain a $500 million line of credit from its affiliate company, Spectra Energy Partners, LP (SEP). Subject to this order, Express will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) of the NEB | 2017-01-05 | 2017-01-05 |  | In Progress |  | 3 | Express shall continue to maintain insurance policies in the amount of at least $500 million (when converted to CAD). Express shall file with the Board, by 28 February 2017, a certificate of insurance detailing its insured coverage types and amounts.&nbsp; | In Progress | Not Construction Related | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-003-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Express Pipeline Ltd. (Express) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Express is required to obtain a $500 million line of credit from its affiliate company, Spectra Energy Partners, LP (SEP). Subject to this order, Express will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) of the NEB | 2017-01-05 | 2017-01-05 |  | In Progress |  | 4 | Express shall notify the Board in writing if there are, or if Express has reason to believe that there will be, any material revisions to its financial resources. This includes changes to Spectra Energy Partners, LP&rsquo;s financial condition or corporate structure such that its ability to provide $500 million in funds via the line of credit to Express may be impaired.&nbsp; | In Progress | Not Construction Related | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Implementation of Financial Resource Requirements | Implementation of Financial Resource Requirements | In Progress | FRO-003-2017 | Issuance of an order, under subsection 48.13(2) of the NEB Act to provide Express Pipeline Ltd. (Express) with more direct access to financial resources, including readily accessible types. In addition to its existing insurance coverage, Express is required to obtain a $500 million line of credit from its affiliate company, Spectra Energy Partners, LP (SEP). Subject to this order, Express will meet the $1 billion financial resources requirement in accordance with subsection 48.13(1) of the NEB | 2017-01-05 | 2017-01-05 |  | In Progress |  | 5 | Express shall provide an update to its financial resource requirement plan and file an updated table with the Board consistent with the format requested in NEB IR No. 1.1i) on 10 August 2016, on an annual basis within 30 days of the release of Spectra Energy Partners, LP&rsquo;s consolidated annual financial statements. | In Progress | Not Construction Related | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.(Phase 01 (Westridge Marine Terminal) ) For filings associated with<strong>&nbsp;</strong>Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with<strong>&nbsp;</strong>Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with<strong>&nbsp;</strong>Phase 27 (Spread 2)<br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 28 (Spread 3)) For filings associated with<strong>&nbsp;</strong>Phase 28 (Spread 3)<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with<strong>&nbsp;</strong>Phase 29 (Spread 4)<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5A) ) For filings associated with<strong>&nbsp;</strong>Phase 30 (Spread 5A)&nbsp;<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5B) ) For filings associated with<strong>&nbsp;</strong>Phase 30 (Spread 5B)&nbsp;<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with<strong>&nbsp;</strong>Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)&nbsp;<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with<strong>&nbsp;</strong>Phase 32 (c.7 Omahil &ndash; Spread 5B)&nbsp;<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with<strong>&nbsp;</strong>Phase 33 (Spread 6)<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with<strong>&nbsp;</strong>Phase 34 (c.7 Tzeachten &ndash; Spread 6)<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with<strong>&nbsp;</strong>Phase 35 (c.77 Lightning Rock &ndash; Spread 6)<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 36 (Spread 7)) For filings associated with<strong>&nbsp;</strong>Phase 36 (Spread 7)<br /><br />&nbsp;&nbsp;&nbsp;&nbsp;(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with<strong>&nbsp;</strong>Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with<strong>&nbsp;</strong>Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with<strong>&nbsp;</strong>Phase 39 (Burnaby Tunnel) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)<br />&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)<br />&nbsp;(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)<br />&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)<br />&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB <strong>at least thirty days prior to commencing construction</strong> of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with&nbsp;Phase 38 (Westridge Delivery Lines) &nbsp; &nbsp; &nbsp;&nbsp;(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 101 | <strong>Uninterruptible Power Supply (UPS) and battery systems</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction at each terminal and pump station</strong>, confirmation that the UPS system design and planned operation related to that facility, is in compliance with the requirements of CSA 22.1 &ndash; 15 or other applicable standard(s) that exceeds the requirements of CSA 22.1 &ndash; 15. If another standard is used, this filing must include the name of the standard and an explanation of why the standard was used and how it meets or exceeds the requirements of CSA 22.1 1 &ndash; 15.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 102 | <strong>Landowner and tenant complaint process/system</strong><br />Trans Mountain must file with the Board, <strong>at least 30 days prior to commencing construction</strong>, confirmation that it has created and will maintain, up until the Project is abandoned or decommissioned pursuant to the NEB Act, a process/system that chronologically tracks landowner and tenant complaints related to the Project.<br />The filing must contain confirmation that the process/system will track:<br />a) a description of each complaint;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) how each complaint was received (e.g., telephone, letter, email);<br />c) the date each complaint was received;<br />d) subsequent dates of all contact or correspondence with each complainant;<br />e) records of any site visits, monitoring, or inspections;<br />f) contact information for all parties involved in each complaint;<br />g) the date of each complaint&rsquo;s resolution; and<br />h) if a complaint remains unresolved, a description of any further actions to be taken or an explanation for why no further action is required.<br />Trans Mountain must make available to a landowner or tenant, upon request, the records related to the complaint(s) that the landowner or tenant made to Trans Mountain, including any investigations, reports or surveys conducted in relation to the complaint.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 103 | <strong>Utility crossings </strong><br />Trans Mountain must file with the Board, <strong>at least 30 days prior to commencing construction</strong>, a list of all underground utilities to be crossed by the Project. The list must include the location and owners of the utilities to be crossed, as well as confirmation that all the agreements or crossing permits for those utilities to be crossed have been acquired or will be acquired prior to construction.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with&nbsp;Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with&nbsp;Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with&nbsp;Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with&nbsp;Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with&nbsp;Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with&nbsp;Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with&nbsp;Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with&nbsp;Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with&nbsp;Phase 39 (Burnaby Tunnel)&nbsp; &nbsp; &nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 104 | <strong>Updated engineering alignment sheets and drawings</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pipe installation</strong>, updated engineering alignment sheets and drawings and, <strong>as they become available and prior to their implementation</strong>, any modifications to those sheets and drawings.(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 105 | <strong>Quality assurance verification</strong><br />Trans Mountain must file <strong>monthly summary reports, </strong><strong>from commencing </strong><strong>construction until after commencing operations, </strong>outlining non-conformances with its design, materials, and construction specifications and the disposition of these non-conformances.(Phase 26 (Spread 1)) <p>For filings associated with Phase 26 (Spread 1)<br />&nbsp;</p>(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)<br />&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase&nbsp;30 (Spread 5A)<br />&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)<br />&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)<br />&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase&nbsp;30 (Spread 5A)<br />&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)<br />&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 107 | <strong>Indigenous, local, and regional employment and business opportunity monitoring reports</strong><br />a) Trans Mountain must file with the NEB, <strong>within 3 months after commencing construction</strong>, <strong>and every 6&nbsp;months thereafter until after commencing operations</strong>, monitoring reports for Indigenous, local, and regional employment and business opportunities for the Project. The reports must include:<br />i) a summary of the elements or indicators monitored;<br />ii) a summary and analysis of Indigenous, local, and regional employment and business opportunities during the reporting period; and<br />iii) a summary of Trans Mountain&rsquo;s consultation, undertaken during the reporting period, with relevant Indigenous groups and local, regional, community and industry groups or representatives, regarding employment and business opportunities. This summary must include any issues or concerns raised regarding employment and business opportunities and how Trans Mountain has addressed or responded to them.<br />b) Trans Mountain must file with the NEB, <strong>within 6 months after commencing operations</strong>, a final report on employment during the construction phase.(a)) Trans Mountain must file with the NEB, <strong>within 3 months after commencing construction</strong>, <strong>and every 6&nbsp;months thereafter until after commencing operations</strong>, monitoring reports for Indigenous, local, and regional employment and business opportunities for the Project. The reports must include:<br />i) a summary of the elements or indicators monitored;<br />ii) a summary and analysis of Indigenous, local, and regional employment and business opportunities during the reporting period; and<br />iii) a summary of Trans Mountain&rsquo;s consultation, undertaken during the reporting period, with relevant Indigenous groups and local, regional, community and industry groups or representatives, regarding employment and business opportunities. This summary must include any issues or concerns raised regarding employment and business opportunities and how Trans Mountain has addressed or responded to them.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(b)) Trans Mountain must file with the NEB, <strong>within 6 months after commencing operations</strong>, a final report on employment during the construction phase.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | In Progress | During Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 108 | <strong>Contingency watercourse crossings</strong><br />a) For any watercourse crossing where Trans Mountain will employ a contingency crossing method instead of its proposed primary method, and where <strong>any</strong> of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; cannot be implemented, Trans Mountain must file with the NEB <strong>at least 30 days prior to commencing construction of the contingency watercourse crossing:</strong><br />i) confirmation of the contingency watercourse crossing method that will be employed, the rationale for employing that method, and a summary of the differences between the primary and contingency watercourse crossing methods; and<br />ii) the following site-specific information:<ol><li>detailed crossing-specific design drawings;</li><li>photographs up-stream, down-stream, and at the crossing location;</li><li>a description of the fish species and habitat that is present at the crossing location, and if fish spawning is likely to occur within the immediate area;</li><li>a description of the composition of the riparian habitat at the crossing location and an indication if the riparian habitat has a limiting effect on the productive capacity of the watercourse, and if its removal or disturbance represents a potential influence on fish communities;</li><li>the site-specific mitigation and habitat enhancement measures to be used to minimize impacts;</li><li>any potential residual effects;</li><li>proposed reclamation measures; and</li><li>a discussion of the potential impacts to local fisheries resources within the immediate area as a result of the crossing&rsquo;s construction; and</li></ol>b) For all other instances where a contingency crossing method will be employed and all of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; will be implemented, Trans Mountain must file with the NEB a notification, at least 15 days prior to commencing the contingency crossing, that the contingency method will be employed. With this notification, Trans Mountain must explain why the contingency method is being employed and provide a summary of the differences between the primary and contingency watercourse crossing methods.<br />c) Trans Mountain must confirm, within 30 days after commencing operations, that any contingency watercourse crossing(s) identified to the NEB pursuant to a) and b) were the only contingency watercourse crossing(s) implemented for the construction of the pipeline.<ol></ol>(a)) a) For any watercourse crossing where Trans Mountain will employ a contingency crossing method instead of its proposed primary method, and where&nbsp;<strong>any</strong>&nbsp;of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; cannot be implemented, Trans Mountain must file with the NEB&nbsp;<strong>at least 30 days prior to commencing construction of the contingency watercourse crossing:</strong><br />i) confirmation of the contingency watercourse crossing method that will be employed, the rationale for employing that method, and a summary of the differences between the primary and contingency watercourse crossing methods; and<br />ii) the following site-specific information:<ol><li>detailed crossing-specific design drawings;</li><li>photographs up-stream, down-stream, and at the crossing location;</li><li>a description of the fish species and habitat that is present at the crossing location, and if fish spawning is likely to occur within the immediate area;</li><li>a description of the composition of the riparian habitat at the crossing location and an indication if the riparian habitat has a limiting effect on the productive capacity of the watercourse, and if its removal or disturbance represents a potential influence on fish communities;</li><li>the site-specific mitigation and habitat enhancement measures to be used to minimize impacts;</li><li>any potential residual effects;</li><li>proposed reclamation measures; and</li><li>a discussion of the potential impacts to local fisheries resources within the immediate area as a result of the crossing&rsquo;s construction; and</li></ol>(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(b)) b) For all other instances where a contingency crossing method will be employed and all of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; will be implemented, Trans Mountain must file with the NEB a notification, at least 15 days prior to commencing the contingency crossing, that the contingency method will be employed. With this notification, Trans Mountain must explain why the contingency method is being employed and provide a summary of the differences between the primary and contingency watercourse crossing methods.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(c)) c) Trans Mountain must confirm, within 30 days after commencing operations, that any contingency watercourse crossing(s) identified to the NEB pursuant to a) and b) were the only contingency watercourse crossing(s) implemented for the construction of the pipeline.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 109 | <strong>Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act</em> &ndash; Westridge Marine Terminal</strong><br />a) In the event that Fisheries and Oceans Canada determines that the Westridge Marine Terminal expansion requires Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act</em>, Trans Mountain must file with the NEB, <strong>at least 10 days prior to commencing works specified in the respective Authorization(s), </strong>a copy of the Authorization(s); and<br />b) Trans Mountain must confirm, <strong>within 30 days after commencing operations, </strong>that any <em>Fisheries Act</em> Authorization(s) required for the Westridge Marine Terminal expansion were obtained from Fisheries and Oceans Canada and filed with the NEB pursuant to a), or notify the Board if no Authorization(s) was required.(a)) In the event that Fisheries and Oceans Canada determines that the Westridge Marine Terminal expansion requires Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act</em>, Trans Mountain must file with the NEB, <strong>at least 10 days prior to commencing works specified in the respective Authorization(s), </strong>a copy of the Authorization(s); and(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(b)) Trans Mountain must confirm, <strong>within 30 days after commencing operations, </strong>that any <em>Fisheries Act</em> Authorization(s) required for the Westridge Marine Terminal expansion were obtained from Fisheries and Oceans Canada and filed with the NEB pursuant to a), or notify the Board if no Authorization(s) was required.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 11 | <strong>Indigenous, local, and regional skills and business capacity inventory</strong><br />&nbsp;(?b) ) Trans Mountain must file with the NEB,&nbsp;<strong>at least 3 months prior to commencing construction</strong>, any updates to the elements of the inventory described in a)i) through vi).(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(a)) Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing construction</strong>, an Indigenous, local, and regional skills and business capacity inventory for the Project. The skills and capacity inventory must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a description of the information and data sources;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a summary of Indigenous, local, and regional skills and business capacity;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the Indigenous, local and regional capacity for employment and business opportunities for the Project;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) plans for communicating employment and business opportunities to Indigenous, local, and regional communities;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a description of identified or potential skills and business capacity gaps, and any proposed measures to address them or to support or increase skills or capacity; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) plans for communicating identified gaps regarding skills and business capacity with Indigenous, local, and regional communities and businesses, and any proposed measures to support or increase skills or capacity.<br />&nbsp;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 110 | <strong>Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act</em> and <em>Species at Risk Act</em> permit(s) &ndash; pipeline</strong><br />For instream activities, except for those related to the Westridge Marine Terminal:<br />a) for any instream activities that will require Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act,</em> Trans Mountain must file with the NEB,<strong> at least 10 days prior to commencing the respective instream activities, </strong>a copy of the Authorization under paragraph 35(2)(b) of the<em> Fisheries Act</em>.<br />b) for any instream activities that will require a permit(s) under the<em> Species at Risk Act</em>, Trans Mountain must file with the NEB, <strong>at least 10 days prior to commencing the respective instream activities, </strong>a copy of the permit(s) issued under the<em> Species at Risk Act</em>.<br />c) Trans Mountain must confirm, <strong>within 30 days after commencing operations, </strong>that:<br />i) any required <em>Fisheries Act</em> Authorization(s) were obtained from Fisheries and Oceans Canada and filed with the NEB pursuant to a), or notify the Board if no Authorization(s) were required; and<br />ii) any required <em>Species at Risk Act</em> permit(s) were obtained from the competent minister under the <em>Species at Risk Act</em> and filed with the NEB pursuant to b), or notify the Board if no permit(s) were required.(a)) for any instream activities that will require Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act,</em> Trans Mountain must file with the NEB,<strong> at least 10 days prior to commencing the respective instream activities, </strong>a copy of the Authorization under paragraph 35(2)(b) of the<em> Fisheries Act</em>.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(b)) for any instream activities that will require a permit(s) under the<em> Species at Risk Act</em>, Trans Mountain must file with the NEB, <strong>at least 10 days prior to commencing the respective instream activities, </strong>a copy of the permit(s) issued under the<em> Species at Risk Act</em>.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(c)) Trans Mountain must confirm, <strong>within 30 days after commencing operations, </strong>that:<br />i) any required <em>Fisheries Act</em> Authorization(s) were obtained from Fisheries and Oceans Canada and filed with the NEB pursuant to a), or notify the Board if no Authorization(s) were required; and<br />ii) any required <em>Species at Risk Act</em> permit(s) were obtained from the competent minister under the <em>Species at Risk Act</em> and filed with the NEB pursuant to b), or notify the Board if no permit(s) were required.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 111 | <strong>Joining</strong><strong> Programs</strong><br />Trans Mountain must develop Joining Programs and file them with the NEB <strong>at least 45 days prior to commencing welding of, respectively</strong>:<br />a) field circumferential production, tie-in, and repair pipeline welds, including the tie-in welds between existing segments and Line 1 or Line 2; and<br />b) terminals and pump stations.<br />The Joining Programs must include:<br />i) welder qualification requirements;<br />ii) requirements for welding inspector qualifications and duties;<br />iii) welding procedure specifications;<br />iv) non-destructive examination () specifications;<br />v) procedure qualification records for welding procedure specifications and NDE specifications;<br />vi) a quality assurance program for field welds and welding procedures; and<br />vii) any additional information that supports the Joining Program.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 112 | <strong>Pressure testing</strong><br />a) Trans Mountain must pressure test the new and reactivated pipeline segments, terminals, and pump stations with a liquid medium.<br />b) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing</strong>, a Pressure Testing Program that demonstrates compliance with applicable codes, standards, and regulatory requirements.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 113 | <strong>Hydrostatic Testing Plan</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing of any Project component</strong>, a Hydrostatic Testing Plan for the Project that includes:<br />a) the locations of all water withdrawal and discharge sites;<br />b) a discussion of any clearing activities or any other associated works, if required, that will allow for the transportation of the hydrostatic test water;<br />c) water withdrawal rates;<br />d) water withdrawal volumes;<br />e) the flow rate/volume of water at the withdrawal sites; and<br />f) site-specific mitigation measures to be implemented at the water withdrawal and discharge sites or at any other locations required to allow for the transportation of hydrostatic test water, including a description of the water quality monitoring methods to be used on hydrostatic testing water prior to discharge; and<br />g) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Non Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 114 | <strong>NDE of final tie-in welds</strong><br />Trans Mountain must delay NDE of final tie-in welds (i.e.: welds which will not be subjected to hydrostatic testing) and any repairs to them <strong>for at least 48 hours following weld completion</strong>. Trans Mountain must include this requirement in the NDE specification of its Joining Program required by Condition 111.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Non Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 115 | <strong>SCADA and leak detection system design</strong><br />Trans Mountain must file with the NEB, reports describing the final design of the expanded Trans Mountain Pipeline System&rsquo;s SCADA and leak detection systems. These reports must include:<br />a) for the commercially available external leak detection systems resulting from Trans Mountain&rsquo;s participation in joint industry projects, <strong>at least 45 days prior to commencing backfilling on Line 2 and the new delivery pipelines, </strong>a status update, including a timeline for implementation; and<br />b)<strong> at least 3 months prior applying for leave to open the Project</strong>:<br />i) a status update for the following complementary leak detection technologies that Trans Mountain is considering, including a timeline for implementation:<ol><li>a secondary Computational Pipeline Monitoring (CPM) system operating in parallel with the Project&rsquo;s proposed CPM; and</li><li>aerial surveillance systems resulting from Trans Mountain&rsquo;s participation in joint industry projects;</li></ol>ii) an explanation of how Trans Mountain&rsquo;s complementary leak detection system(s) supports the leak detection capabilities of the primary CPM system(s);<br />iii) for all leak detection systems applicable to the Project, performance targets for:<ol><li>sensitivity;</li><li>accuracy;</li><li>reliability; and</li><li>robustness;</li></ol>iv) a validation plan for the performance targets in iii), including alarm testing, to be implemented within the first year of Project operation;<br />v) rationale for the selected time windows(s) (i.e. averaging periods) for the CPM system(s);<br />vi) a copy of Trans Mountain&rsquo;s public awareness program on recognizing and reporting leaks;<br />vii) a description of how the leak detection system and its relevant procedures comply with CSA Z662 Annex&nbsp;E;<br />viii) a list of other best practices such as API (American Petroleum Institute) recommended practices related to leak detection and control centre management;<br />ix) a description of how Trans Mountain&rsquo;s revised procedureshave introduced a rule directing the Control Centre Operator to perform a controlled shut down of the pipeline when a leak cannot be ruled out in a given time period; and<br />x) a plan, including a timeline for implementation, for upgrading the existing measurement and data acquisition instrumentation to improve the leak detection performance of Line 1.(a)) for the commercially available external leak detection systems resulting from Trans Mountain&rsquo;s participation in joint industry projects, <strong>at least 45 days prior to commencing backfilling on Line 2 and the new delivery pipelines, </strong>a status update, including a timeline for implementation; and(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(b)) <strong>at least 3 months prior applying for leave to open the Project</strong>:<br />i) a status update for the following complementary leak detection technologies that Trans Mountain is considering, including a timeline for implementation:<ol><li>a secondary Computational Pipeline Monitoring (CPM) system operating in parallel with the Project&rsquo;s proposed CPM; and</li><li>aerial surveillance systems resulting from Trans Mountain&rsquo;s participation in joint industry projects;</li></ol>ii) an explanation of how Trans Mountain&rsquo;s complementary leak detection system(s) supports the leak detection capabilities of the primary CPM system(s);<br />iii) for all leak detection systems applicable to the Project, performance targets for:<ol><li>sensitivity;</li><li>accuracy;</li><li>reliability; and</li><li>robustness;</li></ol>iv) a validation plan for the performance targets in iii), including alarm testing, to be implemented within the first year of Project operation;<br />v) rationale for the selected time windows(s) (i.e. averaging periods) for the CPM system(s);<br />vi) a copy of Trans Mountain&rsquo;s public awareness program on recognizing and reporting leaks;<br />vii) a description of how the leak detection system and its relevant procedures comply with CSA Z662 Annex&nbsp;E;<br />viii) a list of other best practices such as API (American Petroleum Institute) recommended practices related to leak detection and control centre management;<br />ix) a description of how Trans Mountain&rsquo;s revised procedureshave introduced a rule directing the Control Centre Operator to perform a controlled shut down of the pipeline when a leak cannot be ruled out in a given time period; and<br />x) a plan, including a timeline for implementation, for upgrading the existing measurement and data acquisition instrumentation to improve the leak detection performance of Line 1.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 116 | <strong>Control system, SCADA, instruments, and communication</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to completing dry commissioning activities</strong>, the block diagrams of the control system for its proposed pipeline that include the interconnection between various devices and components such as:<ol><li>programmable logic controllers;</li><li>flow meters, and pressure and temperature measuring devices;</li><li>critical protective elements;</li><li>emergency shut-down systems;</li><li>variable frequency drives;</li><li>control valves;</li><li>block valves; and</li><li>local human machine interface.<br />The block diagrams must demonstrate the primary and backup communication systems, supervisory and control layers of software, firewalls, and how all elements are integrated with the SCADA system.</li></ol>(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 117 | <strong>Reporting on improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least</strong> <strong>2 years and 1 year prior to commencing operations</strong>, detailed updates for the company&rsquo;s review of its Emergency Management Program (toward meeting the requirements of Condition 124). This filing must include:<br />a) a summary of work undertaken to-date;<br />b) the approximate timing for completing remaining work; and<br />c) a summary of parties that were consulted (Condition 90) and how their comments and feedback were considered in improving the program.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 118 | <strong>Firefighting capacity at terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least 1 year prior to commencing operations at the terminals:</strong><br />a) the following information regarding developing appropriate firefighting capacity for a safe, timely, and effective response to a credible worst-case fire at the Westridge Marine Terminal and at the Edmonton, Sumas, and Burnaby Terminals:<br />i) an assessment of necessary resources and equipment, including an explanation of how the assessment was informed by Trans Mountain&rsquo;s terminal risk assessments;<br />ii) a summary of Trans Mountain&rsquo;s consultation with appropriate municipal authorities and first responders, that includes any issues or concerns raised regarding each municipality&rsquo;s respective firefighting capacity and how Trans Mountain has addressed or responded to them;<br />iii) a Firefighting Capacity Framework, informed by the assessment in i) and consultation in ii), and that includes a list of and timeline for completing key activities and milestones leading to the establishment of appropriate firefighting capacity; and<br />b) a plan for responding to a fire exceeding a credible worst case scenario.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 119 | <strong>Emergency Preparedness and Response Exercise and Training Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 1 year prior to commencing operations</strong>, an Emergency Preparedness and Response Exercise and Training Program for the pipeline; the Edmonton, Sumas, and Burnaby Terminals; and the Westridge Marine Terminal. The program&rsquo;s objective is to demonstrate the continual improvement of responder competencies (including control centre personnel) at all levels of the company to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type, including tank fires and earthquakes. The program must include the following:<br />a) a defined scope, other objectives in addition to those noted above, and program targets that address responder turn-over and ensure responders&rsquo; ongoing training and practice;<br />b) a list of mandatory courses for responders;<br />c) a discussion of how Trans Mountain will train its personnel to respond to all hydrocarbon spill scenarios in various seasons, including releases of hydrocarbons in mountain regions during winter conditions, into ice covered watercourses, into watercourses under varying flow conditions and into waterbodies (aquifers or streams)that are used as municipal water supply sources;<br />d) a description of, and schedule for, all emergency response exercises (full-scale, tabletop, drills, functional) that Trans Mountain will conduct prior to operations to test a variety of scenarios;<br />e) a plan, including rationales, for determining the schedule and frequency of all emergency response exercises (full-scale, tabletop, drills, functional) to test a variety of scenarios during the Project&rsquo;s operational life;<br />f) a discussion of how emergency response exercises will meet the objectives of testing Trans Mountain&rsquo;s:<br />i) emergency response procedures;<br />ii) company personnel training;<br />iii) communications systems;<br />iv) response equipment;<br />v) safety procedures; and<br />vi) the effectiveness of its liaison and continuing education programs;<br />g) a learnings implementation plan for exercises that considers how Trans Mountain will update and amend its Emergency Response Plans and related documents following exercises. The learnings implementation plan must consider three main purposes:<br />i) to validate plans;<br />ii) to develop Trans Mountain responder competencies (including control centre personnel) and provide them with the opportunity to carry out and understand their roles in emergency response; and<br />iii) to test Project-specific emergency response procedures;<br />h) a plan for addressing the training requirements contained within the <em>National Energy Board Onshore Pipeline Regulations</em>; and<br />i) confirmation that an independent third party has reviewed and assessed the Emergency Preparedness and Response Exercise and Training Program and that Trans Mountain has considered and incorporated the comments generated by that review and assessment into the program.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 12 | <strong>Training and Education Monitoring Plan</strong>(a)) Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring the implementation and outcomes of Indigenous, local, and regional training and education measures and opportunities for the Project. The plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a description of, and rationale for selecting, the indicators that will be monitored to track the implementation of training and education measures and opportunities;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the monitoring methods and schedule, including information and data sources for the indicators being monitored;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) plans for consulting and reporting on the implementation and outcomes of training and education measures and opportunities with Appropriate Government Authorities, potentially affected Indigenous groups, business, industry, and education and training organizations; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups, business, industry, and education and training organizations on the development of the plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(b)) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, any updates to the elements of the Training and Education Monitoring Plan described in a)i) through iii) above.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 120 | <strong>Notification and reporting on emergency response exercises</strong><br />For any tabletop, functional, and full-scale emergency response exercises undertaken as part of its Emergency Preparedness and Response Exercise and Training Program required by Condition 119:<br />a) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>at least 45 days prior to the date of each exercise</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />b) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after</strong> <strong>completing each</strong> <strong>full-scale exercise</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement; and<br />iii) steps to be taken to correct deficiencies.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 121 | <strong>Financial Assurances Plan &ndash; operations phase</strong><br />&nbsp;(a)) Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to applying for leave to open Line 2</strong>, a Financial Assurances Plan that includes details of the financial resources and secured sources of funds that will be necessary to pay, without limitation, all actual loss or damage, costs and expenses, including cleanup and remediation, and loss of non-use value relating to non-use of a public resource associated with an unintended or uncontrolled release from the Project during the operations phase.[1] These costs may arise from, among other things, potential accidents, malfunctions, and failures during the Project operations phase, including all spills originating from the pipeline and the terminals.<br /><br />The Financial Assurances Plan must be signed by an officer of the company, verifying that it is accurate, complete, and, at a minimum, meets the criteria and coverage levels described below:<br /><br />i) Criteria for financial assurance instruments and plan:<ol><li>Any letter of credit that forms part of the Financial Assurances Plan must be unconditional and irrevocable, segregated from Trans Mountain&#39;s day-to-day business activities, and be dedicated to providing funds to cover the costs described in sub a) above, without limitation.</li><li>Third party liability insurance must be current, and broad, respecting the scope of environmental damages covered by the policy; the policy will be consistent with provisions available in the insurance market(i.e., only exceptional/non-standard perils, taking into account the Project&#39;s nature and scope, would be excluded from coverage). Such insurance must be structured on a multi-year basis, recognizing potential loss of income by persons sustaining damage caused by Trans Mountain, over a reasonable number of years after the event.</li><li>A portion of cash reserves or a portion of future cash flows of the Project may be included as instruments in the Financial Assurances Plan, provided they are secured by a commitment letter from an officer of the company confirming that the funds will be dedicated to the Financial Assurances Plan without restrictions for the period specified by the officer.</li><li>Parental and other third party guarantors must be registered within a Canadian jurisdiction and must have financial strength that is demonstrated in balance sheet values and ratios and credit ratings. For example, total assets less total liabilities of the guarantor should be several multiples of the liability assumed in the Trans Mountain guarantee.</li></ol><br />ii) Financial assurance components and coverage levels:<br />Trans Mountain&#39;s Financial Assurances Plan must provide a total coverage, for the Project as a whole, of $1.1 billion[2] for the costs described in sub a) above, without limitation. The plan should include the following components and minimum coverage levels:<ol><li>Ready cash: Trans Mountain must have unfettered access to at least $100 million to cover costs, including compensation to third parties for losses and damages in the near term, while insurance claims are being processed. Once used, this source of cash must be replenished immediately to cover the costs of a potential future spill. This can be in the form of a letter of credit, surety bond or other form acceptable to the NEB.</li><li>Core coverage: Trans Mountain must put in effect and maintain current at all times a core financial coverage of at least $1 billion that includes third party liability insurance and other financial assurance instruments that comply with the criteria. Core coverage must be a portfolio approach with multiple financial instruments used and may not be composed of a single financial instrument (e.g., only third party liability insurance). At least one component of core coverage must be funds that are readily accessible to Trans Mountain (e.g., cash reserves held by the general partner and not distributed to the limited partners).</li></ol><br />Trans Mountain may use a number of financial and insurance instruments in its Financial Assurances Plan. However, sales of Project assets used for transporting hydrocarbon commodities will not be eligible candidates.&nbsp; Below are some illustrative financial and insurance instruments that could be potential candidates for the Financial Assurances Plan:<ul><li>Irrevocable, unfettered letter of credit.</li><li>Secured line of credit.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;</li><li>Cash reserves held by the general partner and not distributed to the limited partners (and verifiable on Trans Mountain Pipelines Limited Partnership&#39;s balance sheet).</li><li>Internal cash flow, committed by Trans Mountain to financial assurances.</li><li>Industry pooled fund.</li><li>Third party liability insurance with exclusions for only exceptional/non-standard perils.</li><li>No fault third party liability insurance.</li><li>Parental and other third party guarantees provided by parties demonstrating financial strength through balance sheets and credit ratings.</li><li>Other instruments developed by Trans Mountain and the insurance and financial markets.</li></ul>&nbsp;<br />[1]&nbsp;&nbsp;&nbsp;&nbsp; In the context of this condition, &ldquo;operations phase&rdquo; refers to the period after the Project receives leave to open approval and prior to it being fully abandoned.<br />[2]&nbsp;&nbsp;&nbsp;&nbsp; The NEB&rsquo;s basis for any final coverage level is described in its report to Governor in Council.(b)) Trans Mountain must file the following with the NEB:(i)) <strong>At least 6 months prior to applying for leave to open Line 2,</strong> a report from an independent third party that has assessed the Financial Assurances Plan and its key components against the criteria and actual experiences of industry damage claims. The report must summarize the key features of each financial and insurance instrument proposed for inclusion in the Financial Assurances Plan.(ii)) &nbsp;<strong>At least 3 months prior to applying for leave to open Line 2</strong>, a supplement to the report described in b)i) that provides verification of any third party liability insurance coverage, a copy of the insurance certificate, and a summary of the insurance policy&#39;s key features. This summary must include: limits on insurance coverage, deductible amounts, the risks and perils and properties covered by the insurance policy, the exclusions from coverage, Trans Mountain&#39;s obligations, effective dates, and names of insurers and reinsurers.(iii)) <strong>With its first leave to open application for Line 2</strong>, a report describing the steps it took to eliminate any deficiencies in its Financial Assurances Plan that were identified in the independent third party report referenced in b)i) and the NEB&#39;s subsequent review.(iv)) <strong>On or before 31 January of each year after commencing operations</strong>, a letter signed by an officer of the company verifying that all components of the Financial Assurances Plan remain as the NEB approved and sufficient to meet the financial assurance coverage levels described in ii).(First Year Report) First Year Report(v)) <strong>At least 2 months prior to any intended change(s) to the Financial Assurances Plan during the Projects operations phase</strong>, a letter, for approval, detailing the intended change(s) and how the change(s) provides the same or greater level of protection.(vi)) <strong>Within 30 days after accessing any component of the Financial Assurances Plan</strong>, a report detailing the component accessed, the reason for accessing it, and Trans Mountain&rsquo;s plan to ensure that it continues to meet the requirements of its NEB-approved Financial Assurances Plan. | In Progress | During Construction Phase | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 122 | <strong>Changing pipeline segment operating conditions (Hinton to Hargreaves; Darfield to Black Pines)</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to applying for leave to open Line 2</strong>, the following:<br />a) An engineering assessment in accordance with CSA Z662 for the above two pipeline segments which Trans Mountain proposes to change from operating on the existing TMPL to the proposed Line 2.<br />The engineering assessment must demonstrate that the two pipeline segments are fit for their intended service under the operating conditions of Line 2, and that they meet all relevant requirements of CSA Z662. The engineering assessment must include a schedule of planned integrity monitoring activities.<br />b) A certificate with a supporting report issued by an independent certification body[1], stating unconditionally that the 43-kilometre-long, 762 millimetre outside diameter (NPS 30) pipeline segment from Darfield to Black Pines, B.C. is fit for its intended service under the operating conditions[2] of Line 2.<br />The supporting report must include the qualifications of the independent certification body and the justification used to grant the certificate.<br />&nbsp;<br />[1]&nbsp; For Conditions 19, 122 and 152, an &ldquo;independent certification body&rdquo; is an internationally recognized company or organization, such as Lloyd&rsquo;s Register or Det Norske Veritas, which is able to certify compliance to statutory requirements. The independent certification body must have expertise in pipeline integrity. The NEB reserves the right to accept or reject the certificate. In addition, the NEB&rsquo;s decision is not contingent on the results of the certificate.<br />[2]&nbsp; For Conditions 19, 122 and 152, &ldquo;operating conditions&rdquo; must include the Project-specific operating conditions, possible transient flow conditions, slack flow conditions, and effects on operating pressure due to temperature changes.<br />&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 123 | <strong>Evacuation Plans</strong><br />a) Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing operations at the terminals</strong>, an Evacuation Plan for people present in areas potentially affected by an incident at each of Trans Mountain&rsquo;s Edmonton, Sumas, and Burnaby Terminals as well as at the Westridge Marine Terminal. Each Evacuation Plan must, at a minimum:<br />i) describe how areas for evacuation were determined;<br />ii) describe the circumstances under which evacuation may be required, as well as the respective methods and procedures for public notification;<br />iii) describe specific evacuation routes, methods, and destinations;<br />iv) be prepared in consultation with Appropriate Government Authorities, first responders and potentially affected Indigenous groups with the authority to issue evacuation or shelter in place orders during an emergency;<br />v) state how input from Appropriate Government Authorities, first responders and potentially affected Indigenous groups, with the authority to issue evacuation or shelter in place orders during an emergency, was considered in preparing the plan;<br />vi) define the roles, responsibilities, and jurisdictional authority of all parties involved in implementing an evacuation; and<br />vii) confirm that an independent third party has reviewed and assessed the plan and that Trans Mountain has considered and incorporated comments generated by the review and assessment into the plan.<br />b) Trans Mountain must include with its Evacuation Plan for the Burnaby Terminal, a plan specific to Simon Fraser University that includes the requirements in a) i) to vii), above.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 124 | <strong>Implementing improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing operations</strong>, a detailed summary of its review of its Emergency Response Plans (as noted in Conditions 125 and 126) and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing A3S4V5). This filing must include a description of changes made to Trans Mountain&rsquo;s Emergency Management Program, as required under the National Energy Board Onshore Pipeline Regulations, including changes to:<br />a) the Pipeline Emergency Response Plan;<br />b) Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals, as well as the Westridge Marine Terminal; and<br />c) site-specific plans and documents related to a) and b), such as Geographic Response Plans, Geographical Response Strategies, control point mapping, tactical plans for submerged and sunken oil and tactical plans for high consequence areas.<br /><br />The summary must demonstrate Trans Mountain&rsquo;s ability to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type and in any geographic region or season and must include the following:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) &nbsp;a discussion of how the updated plans conform to the requirements contained within the National Energy Board Onshore Pipeline Regulations;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a discussion of how the plans consider, and would allow coordination with relevant federal, provincial, municipal and Indigenous community emergency response plans;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a discussion of how the results of research initiatives, such as the Scientific Advisory Committee work noted in Trans Mountain&rsquo;s response to NEB Information Request No. 1.63 (Filing A3W9H8) and other research noted during the OH-001-2014 proceeding, have been considered and incorporated into Trans Mountain&rsquo;s emergency response planning;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of the models used in response planning, including oil trajectory, fate and behavior, and air dispersion models; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) confirmation that an independent third party has reviewed and assessed the Emergency Response Plans and that Trans Mountain has considered and incorporated the comments generated by the review and assessment into the plans.<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a summary of its consultations with Appropriate Government Authorities, first responders, potentially affected Indigenous groups, and affected landowners/tenants (Condition 90 and Condition 117). In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation including any recommendations from those consulted into Trans Mountain&rsquo;s Emergency Management Program, including its Emergency Response Plans.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 125 | <strong>Emergency Response Plans for the Pipeline and for the Edmonton, Sumas and Burnaby Terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least&nbsp; 6 months prior to commencing operations</strong>, updated Emergency Response Plans which must include:<br />a) the following relevant emergency preparedness and response documents:<br />i) an Emergency Response Plan to include the pipeline expansion;<br />ii) updated Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals; and<br />iii) all related and accompanying site-specific plans and documents, such as control point mapping, Geographic Response Plans, tactical response plans, volunteer management plans, and fire safety plans;<br />b) an emergency response and preparedness table for the pipeline (including facilities) indicating which plans and documents referenced in a) will be referred to in an emergency response for each 10-kilometre-long pipeline segment. For each pipeline segment, the table must also identify, at a minimum:<br />i) high consequence areas, including environmentally sensitive areas (e.g. wetlands), heritage sites and water supply wells (Condition 93);<br />ii) potentially affected persons or groups;<br />iii) available access to the right-of-way and high consequence areas;<br />iv) nearest control point(s);<br />v) nearest available equipment cache(s);<br />vi) response times for deployment of equipment and Trans Mountain personnel, mutual aid personnel, and third party contractors;<br />vii) the available equipment and trained personnel, whether employed by Trans Mountain, contracted, or available through mutual aid (including contact information); and<br />viii) geological, meteorological, and geographical hazards (e.g., snow avalanche, mud slides, rock slides, and steep slopes); and<br />c) maps depicting the information identified in b).(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 126 | <strong>Emergency Response Plan for the Westridge Marine Terminal</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing operations at Westridge Marine Terminal</strong>, an updated Emergency Response Plan for the Westridge Marine Terminal which must include:<br />a) all&nbsp;related and accompanying site-specific plans and documents, such as Geographic Response Plans, Geographic Response Strategies, tactical response plans, volunteer management plans, and fire safety plans;<!-- -->a b) list of high consequence areas, including environmentally sensitive areas;<br />c) a list of potentially affected persons or groups;<br />d) nearest available equipment cache(s);<br />e) response times for deployment of equipment and personnel to the incident location and high consequence areas; and<br />f) maps depicting the information identified in a) to e).(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 127 | <strong>Terminal fire protection and firefighting systems</strong><br />a) Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to applying for leave to open of any Project component at each respective terminal</strong>, an independent third party report confirming the adequacy of the proposed fire protection and firefighting systems implemented or planned to be implemented at the Edmonton Terminal West Tank Area, the Burnaby Terminal, the Sumas Terminal, and the Westridge Marine Terminal. The report must demonstrate that the resources and firefighting systems are capable of suppressing fires associated with all scenarios identified in the above-mentioned terminals&rsquo; final risk assessments (required by Condition 129).<br />b) Trans Mountain must file with the NEB for approval, <strong>at least 2 months prior to beginning the assessment leading to the report in a),</strong> the name and qualifications of the proposed independent third party that will prepare the report in a). | Closed | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 128 | <strong>Offset Measures Plan for residual effects on caribou habitat</strong><br />Trans Mountain must file with the NEB for approval, in accordance with the timelines below, an Offset Measures Plan for each affected caribou range, the goal of which is to offset all unavoidable and residual direct and indirect Project-related effects on caribou habitat, after taking into account the implementation of the measures identified in the relevant Environmental Protection Plan(s) for the Project and the Caribou Habitat Restoration Plan (see Condition&nbsp;37) measures. The Offset Measures Plan must include:<br />a) A preliminary version, to be filed <strong>at least 3 months prior to applying for leave to open</strong>, with the plan&rsquo;s criteria and measurable goals and that includes:<br />i) an initial quantification of the area of caribou habitat directly and indirectly disturbed by the Project;<br />ii) a list of the potential on-the-ground offset measures available;<br />iii) each potential offset measure&rsquo;s appropriate offset ratio, based on consultation with expert federal and provincial authorities and on a review of the scientific literature on conservation offsets;<br />iv) each potential offset measure&rsquo;s expected effectiveness including a discussion of uncertainty and how measures align with criteria specified in the scientific literature specific to conservation offsets;<br />v) each potential offset measure&rsquo;s relative qualitative and quantitative value toward achieving the offset; and<br />vi) a conceptual decision-making tree(s) or decision framework(s) that will be used to select which specific potential offset measures and accompanying offset ratios will be used under what circumstances.<br />b) A final version, to be filed <strong>on or before 31 January after the second complete growing season after completing final clean-up</strong>, including:<br />i) the contents of the preliminary Offset Measures Plan, with any updates identified in a revision log that includes the rationale for any changes;<br />ii) a tabular list of the potential offset measures and appropriate offset ratios to be implemented or already underway, including site-specific details and maps showing the locations, and an explanation of how they meet criteria in the scientific literature for offsets;<br />iii) a description of factors considered when determining the location of offset measures, including consideration of how the measures could maximize benefits to landscape variables;<br />iv) a schedule indicating when potential offset measures will be initiated and their estimated completion dates;<br />v)either an assessment of the predicted offset measures&rsquo; effectiveness including a discussion of uncertainty and a quantitative compilation showing how the measures would offset the previously determined residual effects, or a plan for completing an assessment of the potential offset measures&rsquo; effectiveness and value; and<br />vi) an update on the restoration success to support offset measure decisions.<br />Both the preliminary and final versions of the plan must also include the following:<ol><li>a summary of its consultations with Appropriate Government Authorities and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Offset Measures Plan;</li><li>a description of how Trans Mountain has taken any available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and</li><li>evidence of Trans Mountain&rsquo;s consideration of any updates to the applicable Recovery Strategy, as well as to range boundaries and identified critical habitat made prior and up to the date on which leave to open is granted.</li></ol>(a)) a)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(b)) b)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 129 | <strong>Final terminal risk assessments</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to applying for leave to open for each terminal</strong>, final risk assessments for the Edmonton Terminal West Tank Area, the Sumas Terminal, the Burnaby Terminal, and the Westridge Marine Terminal, respectively, including all implemented mitigation measures. Trans Mountain must demonstrate in each risk assessment that mitigation measures will reduce the risks to levels that are ALARP while complying with the MIACC criteria for risk acceptability. The Edmonton Terminal West Tank Area, Sumas Terminal, and Burnaby Terminal must include the elements listed in Condition 22.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br /><br /><br /><br /><br />&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 130 | <strong>Groundwater Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing operations</strong>, a Groundwater Monitoring Program that pertains to all terminals and pump stations, and for any vulnerable aquifers along the pipeline route. The&nbsp; program must include, at a minimum:<br />a) locations of groundwater monitoring wells, their depths, the rationales for well locations (including how groundwater flow direction was considered), groundwater flow velocity, parameters to be monitored and frequency of monitoring;<br />b) a description of any program changes required to meet this condition for facilities with an existing Groundwater Monitoring Program;<br />c) methods, criteria and rationale for identifying vulnerable aquifers along the pipeline route;<br />d) applicable regulatory criteria for comparing monitoring results, and a process outlining what steps will be followed should monitoring results indicate a negative change in groundwater quality;and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the program.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 132 | <strong>Marine Mammal Protection Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing operations</strong>, a Marine Mammal Protection Program that focuses on mitigating effects from the Project and associated cumulative effects, and on fulfilling Trans Mountain&rsquo;s commitments as a terminal operator with regard to Project-related marine shipping. The program must include:<br />a) the goals and objectives of the program, including a discussion on how they align with the objectives of applicable Fisheries and Oceans marine mammal Recovery Strategies and Action Plans;<br />b) a summary of the issues related to marine mammals from the Project and from Project-related marine vessels;<br />c) a summary of the initiatives that Trans Mountain has supported or undertaken to-date, including the goals of each initiative and how they relate to the goals and objectives of the program;<br />d) a discussion of the outcomes or progress updates of the initiatives identified in c), and how these outcomes have met or are contributing to the objectives of the program;<br />e) any other initiatives that Trans Mountain intends to undertake or support in the future that are relevant to the program; and<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the program, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 133 | <strong>Confirmation of marine spill prevention and response commitments</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to loading the first tanker at the Westridge Marine Terminal with oil transported by the Project</strong>, confirmation, signed by an officer of the company, that:<br />a) Trans Mountain has included in its Vessel Acceptance Standard and Westridge Marine Terminal Regulations and Operations Guide a requirement for tankers nominated to load at the Westridge Marine departure. The tug escort should be suitable for foreseeable meteorological and ocean conditions and be based on tanker and cargo size; and<br />b) an enhanced marine oil spill response regime is in place that is capable of:<br />i) delivering 20,000 tonnes of capacity within 36 hours of notification, with dedicated resources staged within the study area; and<br />ii) initiating a response within 2 hours for spills in Vancouver Harbour, and within 6 hours for the remainder of the Salish Sea shipping route to the 12 nautical-mile territorial sea limit.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 134 | <strong>Updated Vessel Acceptance Standard</strong><strong> and Westridge Marine Terminal Regulations and Operations Guide</strong><br />Trans Mountain must file with the NEB,<strong> at least 3 months prior to loading the first tanker at the Westridge Marine Terminal with oil transported by the Project, and thereafter on or before 31 January of each of the first five years after commencing operations, </strong>an updated Vessel Acceptance Standard and Westridge Marine Terminal Regulations and Operations Guide, and a summary of any revisions made to each.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 135 | <strong>Slack line flow conditions</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to&nbsp; commencing operation of Line 1, and at least 2 months prior to applying for leave to open Line 2, respectively</strong>, the following:<br />a) a list of locations having potential for slack line flow when each of the pipelines is operated at 100&nbsp;per&nbsp;cent of its maximum operating pressure (MOP), 80 per cent of its MOP, and 50 per cent of its MOP; and<br />b) a description of the following regarding detecting and preventing slack line flow conditions:<br />i) operational measures on Line 1 and Line 2; and<br />ii) design measures on Line 2.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 136 | <strong>Pre-operations full-scale emergency response exercises</strong><br />a) <strong>Prior to commencing operations</strong>, Trans Mountain must complete a full-scale exercise for each of the following scenarios:<br />i) a 160-cubic-metre diluted bitumen release into Burrard Inlet as a result of a release from the Westridge Marine Terminal. The exercise must also consider emergency preparedness and response planning for a release that exceeds a credible worst case scenario spill event; and<br />ii) a credible worst-case release volume at the Burnaby Terminal.<br />b) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders, and potentially affected Indigenous groups,<strong> at least 45 days prior to the date of each exercise in a)</strong>, of:<br />i) the exercise&rsquo;s date(s) and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />c) Trans Mountain must file with the NEB and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after completing each exercise in a)</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement;<br />iii) steps to be taken to correct deficiencies; and<br />iv) confirmation that an independent third party has evaluated and assessed the emergency response exercises and that Trans Mountain will consider the comments generated for future exercises.(a)) a)(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(b)) b)(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(c)) c)(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 138 | <strong>Confirmation of firefighting capacity at terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least 30 days prior to commencing operations at the terminal</strong>, confirmation that appropriate firefighting capacity, in accordance with Condition 118, is in place.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 14 | <strong>Technical working group (TWG) &ndash; Terms of Reference</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction</strong>, Terms of Reference for TWGs established in order to address specific technical and construction issues with affected municipalities. The Terms of Reference must be developed in consultation with participating municipalities, and facility owners and operators that will be affected by the Project. The Terms of Reference must, at a minimum:<br />a) identify how TWG membership will be determined;<br />b) identify the TWG structure;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />c) identify an officer of the company who will be accountable for implementing the Terms of Reference;<br />d) describe the scope and mandate to be addressed or implemented by the TWG, including:<br />&nbsp; &nbsp; &nbsp;i) the TWG&rsquo;s goals;<br />&nbsp; &nbsp; &nbsp;ii) the issues and activities that will be within the TWG&rsquo;s mandate;<br />&nbsp; &nbsp; &nbsp;iii) the protocols and mechanisms for implementing TWG recommendations or decisions; and<br />&nbsp; &nbsp; &nbsp;iv) the protocols for reporting and communicating with TWG members, and other potentially-affected or interested parties; and<br />e) provide a summary of any outstanding concerns raised by participating municipalities, and facility owners and operators regarding the Terms of Reference.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 140 | <strong>Post-construction greenhouse gas (GHG) assessment report</strong><br />Trans Mountain must file with the NEB for approval, <strong>within</strong> <strong>2 months after commencing operations</strong>, an updated GHG assessment report specific to the Project. The report must include:<br />a) the methodology used for the assessment, including the sources of GHG emissions, assumptions, and methods of estimation;<br />b) the total direct GHG emissions generated from Project construction, including land-clearing;<br />c) a breakdown of direct GHG emissions generated by the construction of individual Project components (pipeline, pump stations, tank terminals and Westridge Marine Terminal) and by land-clearing activities; and<br />d) a comparison and discussion of the direct GHG emissions calculated in b) with the predicted emissions in Trans Mountain&rsquo;s application and subsequent submissions.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) <p>For filings associated with Phase 33 (Spread 6)</p>(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 141 | <strong>Post-construction noise surveys</strong><br />Trans Mountain must file with the NEB, <strong>within 3 months after commencing operations, </strong>the results of post-construction noise surveys conducted at the Sumas and Burnaby Terminals and at the Westridge Marine Terminal, demonstrating compliance with the British Columbia Oil and Gas Commission&rsquo;s <em>British Columbia Noise Control Best Practices Guideline (2009)</em>, and any further mitigation that Trans Mountain will undertake to achieve compliance.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 142 | <strong>GHG Emissions Offset Plan &ndash; Project construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>within</strong> <strong>4 months after commencing operations, </strong>a plan for providing offsets for all direct GHG emissions generated from Project construction, as determined in Condition 140. The plan must include:<br />a) a list and discussion of all possible offset options considered;<br />b) the criteria against which each option was assessed for viability;<br />c) a description of the offset option(s) selected for direct GHG emissions generated from Project construction, and the rationale for selecting the option(s);<br />d) confirmation that the selected offset option is registered under the approved quantification protocols and has been verified by an accredited &ldquo;verification body&rdquo;<a href=#_ftn1">[1]</a>;<br />e) a schedule indicating when the selected offset options(s) will be initiated; and<br />f) an accounting of offsets confirming no net GHG emissions from Project construction.<div>&nbsp;<div><a href="#_ftnref1">[1]</a> &nbsp;&nbsp;&nbsp; In these conditions, &ldquo;verification body&rdquo; means a competent and independent person, or persons, with responsibility for performing and reporting on the verification process (as defined by ISO 14064).</div></div>(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)" | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 143 | <strong>Baseline</strong> <strong>inspections</strong><br />a) Trans Mountain must conduct the following pipeline inspections on Line 2 and the new delivery pipelines, at the times indicated:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a high-resolution in-line caliper inspection (i.e., a GEOPIG&trade; inspection) <strong>within 6 months after commencing operations</strong> to establish accurate pipeline position and to detect pipe deformations;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an in-line ultrasonic crack detection inspection <strong>within 2 years after commencing operations</strong>;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an in-line corrosion magnetic flux leakage inspection in both the circumferential and longitudinal directions <strong>within 2 years after commencing operations</strong>;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) an in-line ultrasonic wall measurement inspection <strong>within 2 years after commencing operations</strong>; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a close interval survey <strong>within 2 years after commencing operations</strong>.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) Trans Mountain must file with the NEB, <strong>within 6 months after completing each inspection in a)</strong>, a report that includes a summary of the inspection results, the proposed re-inspection interval, and mitigation measures for the anomalies detected through any of the inspections, if required.(a)) Trans Mountain must conduct the following pipeline inspections on Line 2 and the new delivery pipelines, at the times indicated(i)) a high-resolution in-line caliper inspection (i.e., a GEOPIG&trade; inspection) within 6 months after commencing operations to establish accurate pipeline position and to detect pipe deformations;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(ii)) an in-line ultrasonic crack detection inspection within 2 years after commencing operations;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(iii)) an in-line corrosion magnetic flux leakage inspection in both the circumferential and longitudinal directions within 2 years after commencing operations;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(iv)) an in-line ultrasonic wall measurement inspection within 2 years after commencing operations; and(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(v)) a close interval survey within 2 years after commencing operations.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(b)) Trans Mountain must file with the NEB, within 6 months after completing each inspection in a), a report that includes a summary of the inspection results, the proposed re-inspection interval, and mitigation measures for the anomalies detected through any of the inspections, if required.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 144 | <strong>Ongoing confirmation of marine spill prevention and response commitments</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each year after commencing operations,</strong> confirmation, signed by an officer of the company, that it is continuing to meet the requirements of Condition 133 regarding Trans Mountain&rsquo;s marine spill prevention and response commitments.<br />Trans Mountain must provide each filing to Transport Canada, the Canadian Coast Guard, the Pacific Pilotage Authority, Vancouver Fraser Port Authority, British Columbia Coast Pilots, Western Canada Marine Response Corporation, Fisheries and Oceans Canada and the Province of British Columbia at the same time as it is filed with the NEB. If a particular party mentioned above requests that it not be provided the annual filing, Trans Mountain may cease providing it to that party.<br />&nbsp;(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 145 | <strong>Community Benefits Program progress reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations, </strong>a progress report summarizing the initiatives and activities undertaken as benefits that are in addition to compensation for access and potential impacts to community lands, and/or that exceed regulatory requirements. The report must summarize initiatives supported, at a minimum, in the areas of community programs and infrastructure improvements, environmental stewardship, and education and training during the reporting period, including local emergency management enhancements, improvements to community parks, as well as support for events.<br />The filing must contain a commitment from Trans Mountain, and a description of how Trans Mountain will make progress reports publicly available until the Project is abandoned or decommissioned pursuant to the NEB Act.<br />The progress reports must include:<br />a) a description of the initiatives undertaken or supported;<br />b) a list of participants or beneficiaries, including Indigenous groups, local and regional communities, service providers, or others;<br />c) an update on the timing, status, and outcomes of each initiative, including its estimated completion date, if applicable; and<br />c) a summary of Trans Mountain&rsquo;s consultation activities regarding the Community Benefits Program initiatives.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 146 | <p><strong>Reports on engagement with Indigenous groups &ndash; operations</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations,</strong> a report on the engagement activities it has undertaken with Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;<br />b)&nbsp; the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.</p>(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 147 | <strong>Natural hazard assessment</strong><br />Trans Mountain must file with the NEB, <strong>within 1 year after commencing operations</strong>:<br />a) the results of the baseline natural hazard assessment for the Project; and<br />b) confirmation that the natural hazard assessment will be:<br />i) updated at intervals not exceeding 5 years; and<br />ii) integrated into the existing Natural Hazard Management Program for the Trans Mountain Pipeline system.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 148 | <strong>Pipeline Geographic Information System (radio) data</strong><br />Trans Mountain must file with the NEB, <strong>within 1 year after commencing operations</strong>, Geographic Information System data in the form of an Esri&reg; shape file that contains pipeline segment centre lines and right-of-way boundaries, where each pipeline segment has a unique outside diameter, wall thickness, MOP, external coating, field-applied girth weld coating, and pipe manufacturing specification. If the above values of the pipeline change at any point along the length of the Project, the pipeline(s) should be segmented at that point. Trans Mountain must also provide Geographic Information System locations and names of all Project pump stations, terminals, custody transfer meters, tunnel entrances, pipeline bridges, check valves, and block valves, as applicable.<br />The datum must be NAD83 and projection must be geographic (latitudes and longitudes).(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 149 | <strong>Caribou Habitat Restoration and Offset Measures Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the first complete growing season after commencing operations</strong>, a program for monitoring and verifying the effectiveness of caribou habitat restoration and offset measures implemented as part of the final Caribou Habitat Restoration Plan (Condition 37) and the final Offset Measures Plan (Condition 128). This program must include:<br />a) the scientific methods or protocols for short- and long-term monitoring of the restoration and offset measures, and effectiveness of the measures;<br />b) monitoring frequency, timing, and locations, and the rationale for each;<br />c) protocols for how restoration and offset measures will be adapted, as required, based on the monitoring results from the program&rsquo;s implementation;<br />d) a summary of Trans Mountain&rsquo;s consultation with Appropriate Government Authorities and any species experts on the design of the monitoring program; and<br />e) a proposed schedule for filing reports on monitoring results and adaptive management measures to the NEB, Environment and Climate Change Canada, and appropriate provincial authorities to be contained in the Caribou Habitat Restoration and Offset Measures Monitoring Program as well as at the beginning of each report filed.(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 15 | <strong>Pipeline risk assessment</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction</strong>, the following information for Line 2 and the new delivery pipelines:<br />a) the results of the updated risk assessment in a tabular format similar to that provided in its Line 2 Consequence Report (Filing A3Z8G5). The risk assessment tables must also include:<br />&nbsp;&nbsp;&nbsp; i) any updates to High Consequence Areas;<br />&nbsp;&nbsp;&nbsp; ii) the risk mitigation method(s);<br />&nbsp;&nbsp;&nbsp; iii) the mitigated Environmental Risk Scores;<br />&nbsp;&nbsp;&nbsp; iv) pre-mitigation maximum outflow volumes; and<br />&nbsp;&nbsp;&nbsp; v) the outflow volumes after mitigation;<br />b) Environmental Risk Score acceptance criteria, with supporting rationale; and<br />c) a detailed description of the adequacy of the following from its Line 2 Consequence Report (Filing A3Z8G5):<br />&nbsp;&nbsp;&nbsp; i) the coefficients used in the scoring system equations; and<br />&nbsp;&nbsp;&nbsp; ii) the values from the scoring tables.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)&nbsp;&nbsp;&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 150 | <strong>Caribou habitat restoration and offset measures monitoring report(s)</strong><br />Trans Mountain must file with the NEB, <strong>based on the approved schedule for the Caribou Habitat Restoration and Offset Measures Monitoring Program </strong>(required by Condition 149), a report(s) outlining the monitoring program&rsquo;s results, including the observed effectiveness of habitat restoration and offset measures for each affected caribou range, and how those measures will be adapted, as required, based on monitoring results. Any proposed changes to the NEB-approved reporting schedule must be included within the relevant report prior to any reporting on a revised schedule.(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 153 | <strong>Full-scale emergency response exercises during operations</strong><br />a) <strong>Within 5 years after commencing operations</strong>, Trans Mountain must complete full-scale exercises to test each of the following five scenarios:<br />i) a full-bore rupture under ice and snow conditions in the Coquihalla Mountain Range;<br />ii) a full-bore rupture into the Athabasca River during high spring flow conditions;<br />iii) a full-bore rupture into Fraser River at the Port Mann Bridge, under peak flow conditions;<br />iv) a full-bore rupture into the North Thompson River during high spring flow conditions; and<br />v) a tank fire at the Burnaby Terminal.<br />b) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups <strong>at least 45 days prior to the date of each exercise in a)</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />c) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after completing each exercise in a)</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement;<br />iii) steps to be taken to correct deficiencies; and<br />iv) confirmation that an independent third party has evaluated and assessed the emergency response exercises and that Trans Mountain will consider the comments generated for future exercises.(a)) <strong>Within 5 years after commencing operations</strong>, Trans Mountain must complete full-scale exercises to test each of the following five scenarios:<br />i) a full-bore rupture under ice and snow conditions in the Coquihalla Mountain Range;<br />ii) a full-bore rupture into the Athabasca River during high spring flow conditions;<br />iii) a full-bore rupture into Fraser River at the Port Mann Bridge, under peak flow conditions;<br />iv) a full-bore rupture into the North Thompson River during high spring flow conditions; and<br />v) a tank fire at the Burnaby Terminal.<br /><br />&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(b)) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups <strong>at least 45 days prior to the date of each exercise in a)</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br /><br />&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(c)) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after completing each exercise in a)</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement;<br />iii) steps to be taken to correct deficiencies; and<br />iv) confirmation that an independent third party has evaluated and assessed the emergency response exercises and that Trans Mountain will consider the comments generated for future exercises.(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | In Progress | Post Construction Phase | Standard | Filing Not Required | Emergency Management, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 154 | <strong>Riparian Habitat Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up,</strong> a Riparian Habitat Reclamation Evaluation Report and Offset Plan.&nbsp;<br />a) The report must include, for each defined watercourse crossed by the Project:<br />i) an evaluation of performed reclamation activities against the identified measureable goals and targets (required by Condition 71), that includes an identification of the defined watercourses whereriparian habitat that has not returned to, or trending towards a sufficient, pre-construction functionality;<br />ii) a description of the proposed enhancement measures and corrective actions selected and the rationale for the selected option(s); and<br />iii) a schedule for when the enhancement measures and corrective actions will be initiated and an estimated timeline for completion, including any monitoring that will be required.<br />b) The plan must include, for defined watercourses crossed by the Project located in watersheds identified as being above the riparian habitat disturbance threshold (&gt;18 per cent of riparian habitat disturbed in the watershed) or classified as High Sensitive fish-bearing by Trans Mountain, during the OH-001-2014 proceeding, and, where, after the fifth complete growing season, riparian habitat has not returned, or is not trending towards sufficient pre-construction functionality:<br />i) a description of the proposed offset measures selected that includes details with rationales on the amount and type of offsets required, how the offset measures would be implemented, and the location of offset sites;<br />ii) a schedule for when the offset measures will be initiated, an estimated timeline for completion, including any monitoring that will be required, and a schedule for when the results of the offsets monitoring will be filed with the Board that demonstrate offset success.<br />iii) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the report/plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />iv) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 155 | <strong>Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the <em>Species at Risk Act</em>, that includes:<br />a) an evaluation of avoidance and mitigation success with reference to the measurable goals outlined in the Rare Ecological Community and Rare Plant Population Management Plan required by Condition 40;<br />b) identification of communities, species, and critical habitats that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />c) identification of any ongoing effects to ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, or on any early draft, candidate, proposed, or final critical habitat under the <em>Species at Risk Act</em>;<br />d) for the ongoing effects identified in c), a Final Rare Ecological Community and Rare Plant Population Offset Plan that updates the Preliminary Rare Ecological Community and Rare Plant Population Offset Plan required by Condition 40, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 156 | <p><strong>Wetland Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Wetland Reclamation Evaluation Report and Offset Plan that includes:<br />a) the extent (in hectares), by wetland type, that was impacted by Project construction and associated activities;<br />b) for each wetland impacted, an evaluation of mitigation and reclamation success with reference to the measurable goals outlined in the Wetland Survey and Mitigation Plan required by Condition 41;<br />c) identification of any wetlands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, an evaluation of any temporary or ongoing loss of any individual functional condition (e.g., habitat, hydrology and biogeochemistry);<br />e) for any wetland that has not achieved reclamation success in terms of overall wetland function, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition, a Final Wetland Offset Plan that updates the Preliminary Wetland Offset Plan required by Condition 41, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.</p>(Phase 01 (Westridge Marine Terminal)) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 157 | <p><strong>Grasslands Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the tenth complete growing season after completing final clean-up</strong>, a Grasslands Reclamation Evaluation Report and Offset Plan that applies to native grasslands in the British Columbia interior and that includes:<br />a) the extent (in hectares) of grasslands that were impacted by Project construction and associated activities;<br />b) an evaluation of reclamation success with reference to the measurable goals outlined in the Grasslands Survey and Mitigation Plan required by Condition 42;<br />c) an identification of any grasslands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for those grasslands that have not yet achieved reclamation success, a Final Grasslands Offset Plan that updates the preliminary plan required by Condition 42, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.</p>(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 16 | <strong>Quantitative Geohazard Frequency Assessment</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction</strong>, an updated Quantitative Geohazard Frequency Assessment for the new Line 2 and delivery pipeline segments that contains a re-assessment of the Frequency of Loss of Containment (FLoC) values based on the results of site-specific field assessments and any required mitigation as determined in the detailed engineering and design process.<br />Trans Mountain must provide in the assessment a plan to manage and mitigate geohazards at any location where the FLoC value is greater than 10-5 events per year to reduce the level of risk to As Low As Reasonably Practicable (ALARP), including a detailed explanation of how the ALARP level has been attained at each location.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)<br />&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 17 | <strong>Valve locations on Line 2</strong><br />Trans Mountain must file with the NEB <strong>for approval</strong>, <strong>at least 6 months prior to commencing construction</strong>, its final valve location assessment for Line 2. This assessment must include:<br />a) a table showing each valve&rsquo;s location, function, and description (the description must include valve type, valve closure time, and whether the valve can be remotely controlled by the control centre);<br />b) confirmation that the valve closure times provided in a) will not cause unsafe transient pressures according to the final transient analysis, along with a summary of the analysis;<br />c) calculated volume release and elevation plots in a format similar to that provided by Trans Mountain in its Oil Spill Outflow Model Results for Line 2 for May 2014 Route (Filing A3Z8G6);<br />d) clarification of how the Outflow Volume Score for Non-Watercourse Intersects (Sv,Nonwatercourse) is considered in identifying and prioritizing pipeline segments for valve optimization;<br />e) for each 5-kilometre-long section of Line 2, information demonstrating that the release volumes are minimized to manage risks within the section to a level that is ALARP, based on the valve locations provided in a);<br />f) an outflow volume versus chainage graph illustrating the effectiveness of the valve locations provided in a) showing the outflow limit in a format similar to that provided in Figure 4 of Attachment 2 to Trans Mountain&rsquo;s response to NEB Information Request No. 3.050b) (Filing A4H2D7);<br />g) mitigation measures for the locations shown to exceed the outflow limit in the graph provided in f); and<br />h) full-bore release and spill extent mapping that identifies and plots all geohazards with a FLoC greater than 10-5 events per year after mitigation identified by Trans Mountain at the time of its submission, in a format and scale similar to the maps provided by Trans Mountain in Filing A3Z8G7(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | <strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp; &nbsp; &nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 20 | <strong>Existing NPS 24 delivery pipeline location</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction</strong>, its decision on whether it intends to &ldquo;relocate&rdquo; the existing NPS 24 delivery pipeline to the Burnaby Mountain tunnel (i.e., replace it with a new third pipeline in the Burnaby Mountain tunnel) and, if so, provide:<br />a) details of any required changes to the design, construction, and operation of the proposed Burnaby Mountain tunnel;<br />b) a discussion of the factors Trans Mountain considered in deciding to replace/relocate the existing NPS 24 delivery pipeline; and<br />c) an indication of when Trans Mountain expects to apply for NEB approval to relocate/replace the existing NPS 24 delivery pipeline.(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 21 | <strong>Transient hydraulic analysis on the existing NPS 24 delivery pipeline</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction</strong>, the conclusions of the transient hydraulic analysis undertaken on the existing NPS 24 delivery pipeline from the Burnaby Terminal to the Westridge Marine Terminal. The filed conclusions must:<br />a) demonstrate that the analysis considered the occurrences of maximum surge pressure in the existing NPS 24 delivery pipeline; and<br />b) support Trans Mountain&rsquo;s decision to either retain or eliminate the proposed relief tank at the Westridge Marine Terminal.(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 26 | <strong>Burnaby Mountain tunnel option &ndash; design, construction, and operation</strong><br />For the tunnel between the Burnaby Terminal and the Westridge Marine Terminal and related delivery pipelines,&nbsp;<strong>at least 6 months prior to commencing Burnaby Mountain tunnel construction activities</strong>, Trans Mountain must:&nbsp;<br />&nbsp;(a)) file with the NEB <strong>for approval</strong>: &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a description of the selected tunnel lining method with the rationale for its selection; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) tunnel confined space entry procedures during construction and visual inspections, and, if applicable, following construction; and(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(b) ) file with the NEB:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the results of any geotechnical or geophysical feasibility surveys completed since the evidence filed in the OH-001-2014 hearing;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a description of the tunnel portals and permanent road access, if applicable;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the selected tunnel excavation method with rationale for its selection;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of the tunnel backfilling method with rationale for its selection;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a description of the methods to be used for pipe handling and welding;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a discussion on the adequacy of the pipe support methods for the new delivery pipelines during construction, commissioning, hydrostatic testing and operation, if applicable;<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion on the adequacy of the selected leak detection methods;<br />&nbsp;&nbsp;&nbsp;&nbsp; viii) information demonstrating how the precautionary design of the new delivery pipelines would mitigate issues related to limited accessibility for future maintenance and repairs; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ix) the final tunnel cross-sectional design drawings.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 27 | <strong>Burnaby Mountain tunnel option &ndash; backfilling</strong><br />Trans Mountain must file with the NEB, at<strong> least 6 months prior to commencing Burnaby Mountain tunnel construction activities</strong>, the following information on backfilling the tunnel between the Burnaby Terminal and the Westridge Marine Terminal:<br />a) a discussion of the adequacy of the measures to be taken during tunnel backfilling to eliminate or mitigate potential damage to the delivery pipelines;<br />b) the method(s) that will be used to confirm the consistency and continuity of the tunnel backfill (i.e., backfilling is completed without any spatial gaps);<br />c) the method(s) that will be used for holiday detection and coating repair prior to backfilling;<br />d) the methods that will be used to confirm the integrity of the delivery pipelines in the tunnel, both prior to and after backfilling, but prior to commissioning; and<br />e) the methods that will be used for monitoring, maintaining, and repairing backfill during operations, considering conditions such as fill deterioration and a potential increase in permeability.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 28 | <strong>Burnaby Mountain tunnel option &ndash; cathodic protection</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing </strong><strong>Burnaby Mountain </strong><strong>tunnel construction activities</strong>, the following information on the cathodic protection system for the delivery pipelines in the tunnel between the Burnaby Terminal and the Westridge Marine Terminal:<br /><br />a) a description of the cathodic protection system design;<br />b) risk mitigation measures for all potential cathodic protection performance issues, such as shielding from the backfill material; and<br />c) a method for verifying the effectiveness of the cathodic protection system during operations.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 29 | <strong>Burnaby Mountain tunnel option &ndash; rock mass and waste rock management</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing Burnaby Mountain tunnel construction activities</strong>, the following details on rock mass expected to be encountered during construction of the tunnel between the Burnaby Terminal and the Westridge Marine Terminal:<br />a) the characterization of the rock mass quality;<br />b) waste rock management methods during construction and operations, if applicable;<br />c) proposed acid rock mitigation measures, such as the treatment or disposal of acid rock, if encountered;<br />d) the locations, sizes, and designs of all confirmed waste rock disposal areas; and<br />e) plans for disposing any waste rock that is not expected to be stored in the confirmed waste rock disposal areas.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)&nbsp; &nbsp; &nbsp; &nbsp;(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 30 | <strong>Power system protection for pump stations and terminals</strong><br />Trans Mountain must file with the NEB the following details of its electrical power system design for each pump station and each of the following: Westridge Marine Terminal, Burnaby Terminal, Edmonton Terminal, and Sumas Terminal:(a)) <div>Descriptions of the overcurrent and ground fault protection schemes including:<br />&nbsp;</div>(i)) a summary of coordination studies between the upstream and downstream protective devices, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(ii)) relay settings and time-current curves, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(iii)) the specification of neutral grounding resistors, <strong>at least 6 months prior to commencing construction</strong>;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(iv)) specifications of contactors, fuses, and circuit breakers, <strong>at least 6 months prior to commencing construction</strong>; and&nbsp;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(v)) a description of other electrical protections, relay settings, and trip characteristics, <strong>at least 3 months prior to commencing dry commissioning.</strong>&nbsp;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(b) ) Consistent with the NEB&rsquo;s Safety Advisory SA-2015-03, dated 4 May 2015, <strong>at least 6 months prior to commencing construction</strong>, information confirming that Trans Mountain has performed the ground fault and arcing fault protection designs for each pump station and terminal, including:<br /><br />i) a means to clear ground faults without intentional time delay if the fault currents exceed the design limit set by the neutral grounding resistance; and<br />ii) a means to block the stored energy from other running motors from feeding an electrical fault in another motor running from the same bus.<br /><br />This filing must include a description of the ground fault and arcing fault protection designs including the above measures.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(c) ) <strong>At least 6 months prior to commencing construction</strong>, either:&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />i) a written confirmation that Trans Mountain determined during detailed design that electrical faults will not exceed their design limits and migrate to an arcing fault; or<br />ii) for a station or a terminal for which Trans Mountain determined during detailed design that an electrical fault could exceed its design limit and migrate to an arcing fault, the electrical configuration of that station or terminal and the additional equipment and devices that will be used to mitigate the adverse effects of such arcing faults.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(d) ) Single-line diagrams of the electrical power systems<strong>, at least 6 months prior to commencing construction.</strong>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 33 | <strong>Westridge Marine Terminal Onshore Geotechnical Report</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction at the Westridge Marine Terminal</strong>, a geotechnical report that provides feasibility-level geotechnical design recommendations for the proposed new onshore facilities at the Westridge Marine Terminal, including consideration of the potential for seismic damage.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 34 | <strong>Westridge Marine Terminal Offshore Geotechnical Report</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction at the Westridge Marine Terminal</strong>, the final Preliminary Geotechnical Report on the offshore portion of the Westridge Marine Terminal, based on the selected pile design option, including consideration of the potential for seismic damage.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 35 | <strong>Marine Sediment Management Plan</strong><br />Trans Mountain must file with the NEB,<strong> at least 6 months prior to commencing construction at the Westridge Marine Terminal, </strong>confirmation whether or not dredging is required at the Westridge Marine Terminal.<br />In the event that dredging is determined to be unavoidable during the expansion of the Westridge Marine Terminal, Trans Mountain must file with the NEB for approval, at least 4 months prior to commencing construction, and also include as part of its Westridge Marine Terminal Environmental Protection Plan, a Marine Sediment Management Plan. This plan must include:<br />a) a summary of any supplemental marine sediment survey results;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) quantification of the area and the volume of marine sediment to be dredged along with an explanation of the measures that have been taken to eliminate or reduce the dredge footprint and volume proposed for disposal at sea;<br />c) results of sediment plume modelling for any areas to be dredged;<br />d) options for dredged sediment management, including the volumes of sediment that will be re-used or disposed of at sea or on land, as well the criteria and methods for determining how the dredged sediment will be disposed of at sea or on land;<br />e) criteria and methods for determining how the dredged sediment will be managed recognizing that any proposed disposal at sea will only be considered for approval under<br />the Canadian Environment Protection Act, 1999, if it is demonstrated to be the most technically and environmentally preferable option;<br />f) confirmation that Trans Mountain will update the Westridge Marine Terminal Environmental Protection Plan to include any relevant information from the Marine Sediment Management Plan;<br />g) details of monitoring that will be undertaken during construction;<br />h) details of monitoring (both abiotic and biotic parameters) that will be undertaken during operations, including a discussion on evaluating the level of contaminants in the marine environment and any changes from pre-construction levels, as well as a proposed reporting schedule; and<br />i) a summary of its consultations with Appropriate Government Authorities and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 36 | <strong>Pre-construction caribou habitat assessment</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range</strong>, a detailed caribou habitat assessment of the Project right-of-way through each caribou range traversed by the Project, including a 500 metre buffer on either side. The framework of the habitat assessment must use the updated critical habitat polygons delineated by the Southern Mountain Caribou Recovery Team and components of critical habitat outlined in the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014). The habitat assessment must include:<br />a) map(s) indicating the location of the habitat;<br />b) a description of the amount of habitat and the existing habitat alteration, in hectares;<br />c) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge into consideration into the assessment including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />d) a description of how Trans Mountain has incorporated input from Appropriate Government Authorities and species experts into the assessment methodology; and<br />e) a description of the type of habitat characterized by the biophysical attributes of critical habitat, as defined in the applicable Recovery Strategy.(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 37 | Trans Mountain must file with the NEB for approval, in accordance with the timelines below, preliminary and final versions of a CHRP for each caribou range potentially affected by the Project.(a) ) <strong>Preliminary CHRP </strong>&ndash; to be filed <strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range. </strong>This version of the CHRP must include the following:<br />i) the CHRP&rsquo;s goals and measureable targets for each caribou range, including the goal of avoidance of critical habitat destruction;<br />ii) a detailed description of measures that will be used to avoid or lessen Project activities that impact critical habitat, and the rationale for selecting the measures;<br />iii) a list of criteria used to identify potential caribou habitat restoration sites;<br />iv) conceptual decision-making tree(s) or decision framework(s) that will be used to identify and prioritize potential caribou habitat restoration sites, and mitigative actions to be used at different types of sites, including consideration of typical site factors that may constrain implementation;<br />v) a literature review upon which the decision-making tree(s) or decision framework(s) are based, including:<br />1) an identification of applicable temporal and spatial caribou habitat restoration methodologies;<br />2) an assessment of the relative effectiveness of the identified methodologies; and<br />3) a detailed methodology of how the literature review was conducted.<br />vi) the quantifiable targets and performance measures that will be used to evaluate the extent of predicted residual effects, CHRP effectiveness, the extent to which the goals and measurable targets have been met, and the need for further measures to offset unavoidable and residual effects on caribou habitat;<br />vii) a schedule indicating when mitigation measures will be initiated and their estimated completion dates;<br />viii) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge studies into consideration in identifying potential caribou habitat restoration sites including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />ix) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the preliminary CHRP.(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(b)) <strong>Final CHRP </strong>&ndash; to be filed <strong>on or before 1 November after the first complete growing season after completing final clean-up.</strong> This version of the CHRP must include the following:<br />i) the preliminary CHRP, with any updates identified in a revision log that includes the rationale for any changes to decision-making criteria;<br />ii) a complete tabular list of caribou habitat restoration sites, including locations, spatial areas, habitat quality descriptions, site-specific restoration activities, and challenges;<br />iii) a description of how selected restoration measures are consistent with the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014);<br />iv) maps or updated Environmental Alignment Sheets showing the site locations;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />v) specification drawings for the implementation of each restoration method;<br />vi) a qualitative and quantitative and assessment of the total area of direct and indirect disturbance to caribou habitat that will be restored, the duration of spatial disturbance, and the area-based extent of the resulting unavoidable and residual effects to be offset, including indirect disturbance; and<br />vii) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the final CHRP.(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 38 | <strong>Sowaqua Spotted Owl Mitigation Plan </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction of any Project component within the Sowaqua spotted owl wildlife habitat area</strong>, a Sowaqua Spotted Owl Mitigation Plan that includes:<br />a) a summary of results from supplemental surveys conducted in the Sowaqua spotted owl wildlife habitat area;<br />b) the area of habitat potentially directly and indirectly affected by the Project;<br />c) a description of how an avoidance, mitigation, and offset hierarchy was considered in the plan;<br />d) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable goals for evaluating mitigation success;<br />e) an evaluation of offset options within or outside of the Sowaqua spotted owl wildlife habitat area, an indication of the selected option, and the rationale for the selected option;<br />f) details on post-construction monitoring of mitigation measures and offset measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, any adjustments to the offset measures, and a proposed reporting schedule;<br />g) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />h) details on how the mitigation and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the mitigation plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the mitigation plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the mitigation plan.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A) &nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 39 | <strong>Hydrogeological study at Coldwater Indian Reserve (IR) No. 1</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction between Veale Road and Kingsvale Pump Station</strong>, a hydrogeological report relating to the aquifer at Coldwater IR No. 1 in British Columbia. The report must:<br />a) describe the methodology and information sources used, including any field investigations;<br />b) delineate the extent of the aquifer in the area of Coldwater IR No. 1;<br />c) characterize the aquifer recharge sources and aquifer confinement;<br />d) characterize the direction and speed of groundwater movement to wells on Coldwater IR No. 1;<br />e) quantify the risks posed to groundwater supplies on Coldwater IR No. 1 in the event of leaks, accidents or malfunctions from the Project;<br />f) based on the assessment of risks, describe proposed measures to address identified risks, including but not limited to considerations related to routing, Project design, operational measures, or monitoring;<br />g) provide justification for the measures proposed to address identified potential risks to groundwater supplies on Coldwater IR No. 1; and<br />h) include a summary of consultations undertaken with the Coldwater First Nation and Appropriate Government Authorities, as well as copies of all written comments that may be provided to Trans Mountain by the Coldwater First Nation or Appropriate Government Authorities. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from the Coldwater First Nation or Appropriate Government Authorities, into the assessment.(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 40 | <strong>Rare Ecological Community and Rare Plant Population Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, an updated Rare Ecological Community and Rare Plant Population Management Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the Species at Risk Act, that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results, and a demonstration of the overall adequacy of the rare ecological community and rare plant surveys, including the adequacy for the identification of biophysical attributes for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act;<br />b) avoidance and mitigation measures to be implemented during construction and operations, including all relevant measures committed to throughout the OH-001-2014 proceeding and any new measures resulting from supplementary surveys, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />c) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />d) details on post-construction monitoring, including survey methods, the appropriate number of years of monitoring to determine the success of each type of avoidance and mitigation measure, corrective actions that might be necessary, and the circumstances under which each such action would be taken;<br />e) a Preliminary Rare Ecological Community and Rare Plant Population Offset Plan for any ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, and for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act, and that, after five years of operations, have ongoing effects. This preliminary plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a rationale for why the community, species, or critical habitat cannot be avoided by a sufficient distance to avoid both direct and indirect residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the expected residual effects on that community, species, or critical habitat, including a discussion of the potential for time lags &nbsp;between when Project effects occur and when mitigation measures would become fully functional, and taking into account the success on past projects of the proposed mitigation and corrective measures in b) and d) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the appropriateness of offsets for the community, species or critical habitat, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of how the avoidance, mitigation, monitoring, corrective and offset measures are consistent with any applicable recovery, action or management strategies or plans for the community, species or critical habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Rare Ecological Community and Rare Plant Population Management Plan, including confirmation that the avoidance, mitigation, monitoring, corrective, and offset measures in the Rare Ecological Community and Rare Plant Population Management Plan will be implemented to the extent feasible in the case of discovery via their inclusion in the Rare Ecological Communities or Rare Plant Species Discovery Contingency Plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)<br />&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)<br />&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 41 | <strong>Wetland Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Wetland Survey and Mitigation Plan for wetlands potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results and a demonstration of the overall adequacy of the wetland surveys;<br />b) a description of any wetlands for which ground-based surveys were not possible, an explanation as to why not, attempts made to obtain access, and what further information on each wetland will be collected immediately prior to or during construction;<br />c) a description of the functional condition of each wetland for comparison during post-construction monitoring, including individual functional conditions (e.g., habitat, hydrology and biogeochemistry, including the presence and abundance of migratory birds and species at risk), and a description of the methods used to determine the type and amount of each individual wetland function and the overall functional condition;<br />d) a description of the crossing methods, mitigation measures and reclamation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each such method and measure will be applied;<br />e) measurable goals against which the success of wetland mitigation and reclamation will be evaluated, including a description of how such goals incorporate the aim of returning wetlands to their original functionality while allowing for reasonable natural variation, and including measurable goals for each of the first-, third- and fifth-year post-construction monitoring reporting stages for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies;<br />f) a description of how the<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss of wetland function, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />g) details of the post-construction monitoring plan for wetlands for the first five years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Wetland Offset Plan for any wetland that has not achieved reclamation success in terms of overall wetland function after five years of operations, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition &ndash; this plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the expected residual effects on the wetland, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in d) and g) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the wetland, taking its specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios and indicator species, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, details with rationales on the offset measures that will be implemented before or during the first five years of operations to compensate for expected temporary or ongoing losses to individual functional conditions, including the amount and type of offsets required, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wetland Survey and Mitigation Plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 42 | <strong>Grasslands Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Grasslands Survey and Mitigation Plan for native grasslands in the B.C. interior that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of survey results for such grasslands, including but not limited to native plant species diversity, species at risk, the density and distribution of existing invasive plant species, and the presence of cryptogamic crust, together with a demonstration of the adequacy of such surveys and a summary of existing and ongoing land management impacts;<br />b) a description (including quantification) of overlap of the Project with grasslands and of expected residual effects;<br />c) a description of the mitigation and reclamation measures to be implemented for grasslands during construction and operations, including the extent to which native seed will be used, with rationales and unambiguous criteria explaining under what circumstances each such measure will be applied;<br />d) measurable goals against which the success of grassland mitigation and reclamation will be evaluated, including goals related to cryptogamic crust recovery, invasive species control, and access control, and how existing and ongoing land management impacts and land-use changes by landowners outside the control of Trans Mountain will be taken into account;<br />e) a description of how the:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy, and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss for grasslands, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />f) details of the post-construction monitoring plan for grasslands for the first ten years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />g) a Preliminary Grasslands Offset Plan for those grasslands that, after ten years of operations, have not achieved reclamation success. This plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) expected residual effects on the grasslands, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in c) and f) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the grasslands, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offsets measures will be monitored, assessed, and reported on, and problems corrected;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />i) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />j) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grasslands Survey and Mitigation Plan.(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 43 | <strong>Watercourse crossing inventory</strong><br />Trans Mountain must file with the NEB, <strong>at least 5 months prior to commencing any watercourse crossing construction activities</strong>, the following:<br />a) an updated inventory of all watercourses to be crossed, including, for each crossing:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the name of the watercourse being crossed and an identifier for the crossing;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the location of the crossing;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) the primary and contingency crossing methods;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) planned construction timing;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) information on the presence of fish and fish habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) information on the composition of riparian habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) the provincial instream work window;<br />&nbsp;&nbsp;&nbsp;&nbsp; viii) the proposed least risk biological window and the rationale to support the proposed least risk biological window if it differs from the provincial instream work window; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ix) an indication of whether any of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; cannot be implemented;<br />b) detailed generic design drawings of trenchless, dry open-cut, frozen open-cut, and isolation crossings of various watercourse types;<br />c) site-specific information for each watercourse crossing where any of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; cannot be implemented for the primary pipeline construction method:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) detailed crossing-specific design drawings;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) photographs up-stream, down-stream, and at the crossing location;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the fish species and habitat that is present at the crossing location, and if fish spawning is likely to occur within the immediate area;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of the composition of the riparian habitat at the crossing location and an indication if the riparian habitat has a limiting effect on the productive capacity of the watercourse, and if its removal or disturbance represents a potential influence on fish communities;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) the site-specific mitigation and habitat enhancement measures to be used to minimize impacts;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) any potential residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) proposed reclamation measures; and<br />&nbsp;&nbsp;&nbsp;&nbsp; viii) a discussion of the potential impacts to local fisheries resources within the immediate area as a result of the crossing&rsquo;s construction;<br />d) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the inventory, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />e) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 44 | <strong>Wildlife Species at Risk Mitigation and Habitat Restoration Plans&nbsp; </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction,</strong> Wildlife Species at Risk Mitigation and Habitat Restoration Plans for each species whose draft, candidate, proposed, or final critical habitat is directly or indirectly affected by the Project. Each plan must include:<br />a) a summary of supplementary pre-construction survey results, including surveys for biophysical attributes of critical habitat;<br />b) the location and type of critical habitat, for those wildlife species with early draft and candidate critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />c) the location, types and total spatial area for each type of critical habitat for those wildlife species with proposed or final critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />d) a detailed description of measures that will be used to avoid the destruction of critical habitat;<br />e) a detailed description of mitigation and habitat restoration measures to be implemented to reduce direct and indirect Project effects on critical habitat, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation and critical habitat restoration success;<br />f) identification and review of alternative mitigation and habitat restoration measures to avoid or lessen direct and indirect Project effects on critical habitat, and the rationale for the selected measure(s);<br />g) detailed description of how selected mitigation and critical habitat restoration measures address the potential for time lags between when the Project impacts occur and when mitigation and critical habitat restoration measures are implemented and are fully functional;<br />h) details on post-construction monitoring of mitigation measures and critical habitat restoration measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />i) details on how the mitigation, critical habitat restoration measures, and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />j) a commitment to include the results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />k) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plans including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />l) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowner/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />m) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wildlife Species at Risk Mitigation and Habitat Restoration Plans.(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)<br />&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)<br />&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)<br />&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)<br />&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)<br />&nbsp;(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 47 | <strong>Access Management Plan(s)</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, an Access Management Plan(s) to be included within the updated Environmental Protection Plans required by Conditions 72 and 78. Each plan must address issues related to soil, vegetation, fish and fish habitat, and wildlife and wildlife habitat. Each plan must also describe access control measures proposed to control both human and predator access during construction and operations, and include:<br />a) objectives of the plan;<br />b) measurable goals for evaluating the plan&rsquo;s success in achieving its objectives;<br />c) a summary of any related baseline information that has been or will be collected to aid in evaluating the plan&rsquo;s success, and justification of the adequacy of this baseline information, or a rationale if no baseline information has or will be collected;<br />d) a list of sites where access control measures will be implemented for construction and those that will remain in place throughout operations, the control measure(s) proposed at those sites, and the rationale for selecting those sites and measures;<br />e) the methods for monitoring the effectiveness of access control measures implemented during construction and operations, and justification of the adequacy of such monitoring;<br />f) a description of available adaptive management measures and of the criteria Trans Mountain will use to determine if and when adaptive management measures are warranted based on monitoring results;<br />g) a commitment to report, as part of Trans Mountain&rsquo;s post-construction environmental monitoring reports (required by Condition 151), on the control measures implemented, monitoring undertaken, and the success of control measures in meeting Access Management Plan goals and objectives, as well as a schedule, with rationale, for reporting throughout operations;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />i) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Plan/Report.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 48 | <strong>Navigation and navigation safety plan</strong><br />Trans Mountain must file with the NEB, <strong>for approval</strong>, <strong>at least 4 months prior to commencing construction</strong>, a Navigation and Navigation Safety Plan that includes:<br />a) an updated list of navigable waterways to be crossed by or affected by the Project (including power lines, marine terminal, temporary or permanent bridge crossings, or other ancillary works that are physically or operationally connected to the Project);<br />b) an updated listing of effects of the Project on navigation and navigation safety for each of the identified waterways identified in a);<br />c) proposed mitigation measures to address Project effects on navigation and navigation safety for each of the identified waterways, including adherence to codes and standards (such as the CSA); and<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and waterway users, regarding their navigational use of each of the identified waterways. In its summary, Trans Mountain must:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) describe the Appropriate Government Authorities, potentially affected Indigenous groups, and commercial and recreational waterway users consulted;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) describe how Trans Mountain identified those consulted; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 49 | <strong>Technical working group (TWG) reports </strong><br />Trans Mountain must file with the NEB, <strong>at least 4 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report describing the activities undertaken by the TWGs during the reporting period and the outcomes of these activities. The reports must include, at a minimum:<br />a) a list of all members of each TWG; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the methods, dates and location of all TWG activities or meetings;<br />c) a summary of all issues or concerns raised or addressed during the TWG activities;<br />d) a description of outcomes or measures that were or will be implemented to address the issues identified or concerns raised; or, if any measures will not be implemented, a rationale for why not; and<br />e) a description of any unresolved issues or concerns, and a description of how these will be addressed, or a rationale for why no further measures will be required.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)&nbsp; &nbsp; &nbsp; &nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 50 | <strong>High-voltage alternating current (AC) interference</strong><br />Trans Mountain must file with the NEB, <strong>at least 4 months prior to commencing construction</strong>:<br />a) a report confirming that Trans Mountain has achieved an engineered solution to mitigate possible damage to pipeline segments caused by the power line fault current from power line footings and other below ground fault current discharge facilities of B.C. Hydro&rsquo;s unshielded transmission power lines that are located less than 30 metres from those segments. The report must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a summary of the above-mentioned engineered solution and an explanation of how the engineered solution adequately mitigates possible damage to the pipeline;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a list of pipeline segments where mitigation will be applied; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation of measures taken by Trans Mountain to reach an agreement with B.C. Hydro towards implementing the engineered solution.<br />Trans Mountain must provide a copy of the report to B.C. Hydro at the same time that it is filed with the NEB;<br />b) a report detailing how Trans Mountain&rsquo;s design reduces hazardous induced voltages on its pipeline segments to meet a maximum 15 VAC under all steady state operating conditions; and<br />c) a report demonstrating how Trans Mountain would comply with the requirements of IEEE Standard 80 to limit touch and step potentials to all points of contacts to pipeline segments due to power line faults or switching surges, and include a list of affected&nbsp; pipeline segments.<br />&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 51 | <strong>Field changes manual for geohazard mitigation</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a field changes manual for geohazard mitigation. This manual must include:<br />a) decision criteria for implementing mitigation for any geohazards identified during construction;<br />b) specific criteria for implementing changes to the designs, grading, special materials, protective structures, burial depth, installation procedures, erosion mitigation measures, and monitoring; and<br />c) details regarding the required qualifications of the field staff that will implement the manual.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 52 | <strong>Air Emissions Management Plan for the Westridge Marine Terminal</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction at the Westridge Marine Terminal, </strong>an Air Emissions Management Plan for the Westridge Marine Terminal that includes:<br />a) locations of air monitoring sites (on a map or diagram), including the rationale for the locations selected;<br />b) confirmation that the new fixed air monitoring stations will be installed and operating at least one year prior to commencing operations at the Westridge Marine Terminal to establish robust local baseline data;<br />c) the methods and schedule for ambient monitoring of contaminants of potential concern in air (e.g., particulate matter [including diesel particulate matter and speciation of PM2.5], nitrogen oxides (including NO2), sulphur dioxide, hydrogen sulphide, ozone, mercaptans, reduced visibility and volatile organic compounds) following a recognized protocol (e.g. National Air Pollution Surveillance program or U.S. Environmental Protection Agency), and emissions source tracking;<br />d) representative meteorological data (e.g. wind speed, wind direction, air temperature and relative humidity) for the monitoring period;<br />e) description of monitoring equipment and procedures for monitoring station data recording, assessment, quality assurance and reporting details, including a description of how the real time and non-continuous air quality monitoring data will be made available to the public;<br />f) a particulate matter management plan;<br />g) a description of the public and Indigenous communication and complaint response processes;<br />h) the criteria or thresholds that, if triggered or exceeded, would require implementing additional mitigation measures;<br />i) a description of additional mitigation measures that would be implemented as a result of the monitoring data or ongoing concerns; and<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 53 | <strong>Fugitive Emissions Management Plan for the Westridge Marine Terminal</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction at the Westridge Marine Terminal</strong>, a Fugitive Emissions Management Plan for the Westridge Marine Terminal that includes:<br />a) a description of the sources of the fugitive emissions that will be generated from the Westridge Marine Terminal during construction and operations;<br />b) a description of the emission and odour controls that will be employed to reduce fugitive emissions during tanker loading and other sources identified in a);<br />c) procedures for verifying, tracking, and reporting on:&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp; i) fugitive emissions during tanker loading;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) volatile organic compound collection efficiency;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) the vapour recovery unit&rsquo;s hydrogen sulphide and mercaptan removal efficiency, as well as its BTEX reduction efficiency; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the vapour combustion unit&rsquo;s hydrogen sulphide and mercaptan; removal efficiency, as well as its combustion efficiency;<br />d) procedures for identifying any leaks or equipment malfunctions during operation of the vapour recovery and vapour combustion units;<br />e) methods for quantifying emissions of particulate matter and volatile organic compounds (with vapour recovery and vapour combustion units in operation);<br />f) any additional mitigation measures that will be employed to further reduce fugitive emissions;<br />g) a description of Trans Mountain&rsquo;s program for addressing complaints with respect to fugitive emissions, including a communication and notification plan; and<br />h) a summary of its consultations with Appropriate Government Authorities. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.<br />&nbsp;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 56 | <strong>Grizzly Bear Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction in each vulnerable grizzly bear population unit / grizzly bear management area</strong>, a Grizzly Bear Mitigation Plan for each of these areas. Trans Mountain must provide a rationale for why any vulnerable grizzly bear population units / grizzly bear management units potentially affected by the Project are not addressed in the plan. The Grizzly Bear Mitigation Plan(s) must include:<br />a) a summary of results from any supplemental surveys conducted;<br />b) potential direct and indirect effects of Project activities on vulnerable grizzly bear population units and grizzly bear management units;<br />c) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation success;<br />d) details on post-construction monitoring of mitigation measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />e) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan(s); and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grizzly Bear Mitigation Plan, including confirmation that the mitigation, monitoring, and corrective measures in this plan will be implemented in the case of discovery via their inclusion in Trans Mountain&rsquo;s Wildlife Species of Concern Discovery Contingency Plan.(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 57 | <strong>Commercial Support for the Project </strong><br />Trans Mountain must file with the Board, <strong>at least 3 months prior to commencing construction</strong>, confirmation, signed by an officer of the company, that:<br />a) the Project has secured agreements or contracts that remain in force with shippers for a minimum term of 15-years for no less than 60 per cent of its total capacity (890,000 barrels per day); and<br />b) any rights to terminate held by shippers that may have existed in any agreements or contracts between Trans Mountain and shippers (which may have reduced the Project&rsquo;s contracted total capacity to less than 60 per cent for a minimum term of 15 years) have lapsed and or expired because their conditions precedent have been satisfied or waived.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 58 | <strong>Training and education monitoring reports</strong><br />&nbsp;(a) ) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction, and every 6 months thereafter until after commencing operations, </strong>monitoring reports for the implementation and outcomes of Indigenous, local, and regional training and education measures and opportunities for the Project. The reports must include the following:<br />&nbsp; &nbsp; &nbsp;i) a description of each training and education measure and opportunity indicator that was monitored, including duration, participant groups, education and training organization, and intended outcomes;<br />&nbsp; &nbsp; &nbsp;ii) a summary and analysis of the progress made toward achieving intended outcomes of each training and education measure and opportunity, including an explanation for why any intended outcomes were not achieved; and<br />&nbsp; &nbsp; &nbsp;iii) a description of identified or potential training or education gaps, and any proposed measures to address them or to support or increase training and education measures and opportunities.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(b) ) Trans Mountain must file with the NEB, <strong>within 6 months after commencing operations</strong>, a final report.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 59 | <strong>Worker accommodation strategy</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a worker accommodation strategy, developed in consultation with appropriate municipal or provincial authorities. The strategy must include:<br />a) a final summary of all proposed accommodations, including the location of any temporary camp(s);<br />b) the number of workers that will be housed; and<br />c) a description of how the strategy addresses any concerns or requests raised in consultation with municipal or provincial authorities.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the event that temporary camp(s) are to be used, the strategy must also include:<br />i) a description of how the potential environmental and socio-economic impacts have been assessed, and a description of all associated mitigation measures;<br />ii) copies of, or reference to, any mitigation or operational plans that will be required or implemented for the camp(s), including a description of how Trans Mountain has incorporated any additional mitigation measures into relevant Environmental Protection Plan(s);<br />iii) copies of any necessary municipal or provincial permits for any camp(s) that have been received 3 months prior to construction. &nbsp;If camp permits are not yet in place 3 months prior to commencing construction, provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a list of the outstanding camp permits and a schedule for when these camp permits will be in place; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) copies of any outstanding camp permits prior to commencing construction;<br />iv) copies or excerpts of all policies relating to the rules of conduct for workers housed at the camp(s);<br />v) confirmation that all policies relating to the camp(s) will be provided to workers;<br />vi) confirmation that all policies relating to the camp(s) were made available to all local communities and other relevant service providers in proximity to any camp(s) that will be used for the Project; and<br />vii) a summary of its consultations with affected landowners/tenants where any camp(s) will be located. Trans Mountain must provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a description of the information provided to landowners/tenants; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Strategy.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:<br />&nbsp;(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with&nbsp;Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(b)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <strong>within 3 months after the [certificate/order] date;</strong>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(ii)) <strong>at least 30 days prior to commencing construction;</strong>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(iii)) <strong>monthly, from the commencement of construction until the first month after commencing operations; and</strong>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong> (superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(n/a) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(n/a) <div><strong>at least 30 days prior to commencing construction</strong>;</div>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(n/a) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(c) and d)) c) post on its company website the same information required by a) and b),<strong> using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i). | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 31 (c.39 Coldwater Hydrological – Spread 5A)) For filings associated with Phase 31 (c.39 Coldwater Hydrological &ndash; Spread 5A)(Phase 32 (c.7 Omahil – Spread 5B)) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp; &nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp; &nbsp;&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp; &nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp; &nbsp;&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)&nbsp;(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 65 | <strong>Hydrology &ndash; notable watercourse crossings</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, revised flood frequency estimates for all notable watercourse crossings, as defined by Trans Mountain in its application. These estimates must incorporate the results of field investigations and bathymetric surveys completed since the Project application was filed, and be presented in a format similar to that presented in Application Volume 4A, Appendix I &ndash; Route Physiography and Hydrology Report, Appendix B &ndash; Notable Water Crossing Catchment Details (Filing A56000).(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 66 | <strong>Risk Management Plan for geohazards</strong><br />Trans Mountain must develop and file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, an updated Risk Management Plan for addressing the threats of existing and potential geohazards during construction of the Project.<br />This plan must be updated as additional site-specific geotechnical information is obtained through detailed investigations, and modified as geohazards are encountered during construction. Trans Mountain must make any updates or modifications available to the NEB upon request.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 67 | <strong>Outstanding horizontal directional drilling geotechnical and feasibility reports</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, Geotechnical Reports and Horizontal Directional Drilling Feasibility and Design Reports, along with final design drawings, for each of the following crossings:(a) ) Coldwater River 4 crossing;&nbsp;(b) ) North Thompson River 6 crossing;(c) ) North Thompson River 7 crossing;(d) ) Pembina River crossing;(e) ) Raft River crossing;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(f) ) Sumas River crossing (suitability for Direct Pipe&reg; installation);(g)) any additional river crossing along the new Line 2 pipeline segments where horizontal directional drilling or other trenchless crossing method is being considered; and&nbsp;(Blackmud Creek) Blackmud&nbsp;Creek(Center Creek) Center&nbsp;Creek(Hardisty Creek) Hardisty&nbsp;Creek(Raft River) Raft River(Salmon River) Salmon&nbsp;River(South Fraser Perimeter Road) South Fraser Perimeter Road(Wedgewood Creek) Wedgewood Creek(Whitemud Creek) Whitemud&nbsp;Creek(h) ) the Coquitlam Landfill, if Horizontal Directional Drilling or other trenchless crossing method is being considered. | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 68 | <strong>Seismic reports &ndash; liquefaction potential</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a final report that identifies all sites along the Project , that have &ldquo;Very High,&rdquo; &ldquo;High,&rdquo; and &ldquo;Moderate&rdquo; liquefaction-triggered ground movement potential, and that describes how the potential for liquefaction-triggered ground movement will be mitigated at each site.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7) | Closed | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 69 | <strong>Fault studies</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, the results of fault-mapping studies that were ongoing during or undertaken after the OH-001-2014 proceeding, for use in the detailed design of the Project. This filing must include conclusions regarding possible seismic activity during the Holocene epoch for Sumas Fault, Vedder Mountain Fault, Fraser River-Straight Creek Fault and Rocky Mountain Trench, and other possible hidden faults, as well as the potential for compounding risks due to the proximity of the Vedder Mountain and Sumas Faults.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 7 | <strong>Environmental and socio-economic assessment - route re-alignments</strong><br />As applicable, Trans Mountain must file with the NEB for approval, <strong>concurrent with its filing of the Plan, Profile and Book of Reference pursuant to section 33 of the <em>National Energy Board Act</em></strong>, an environmental and socio-economic assessment for each proposed detailed route re-alignment that extends beyond the applied-for corridor width of Trans Mountain&rsquo;s preferred route in proximity to:<br />&bull; Ohamil Indian Reserve 1;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&bull; Tzeachten Indian Reserve 13; and<br />&bull; Surrey Bend Regional Park.<br />Any assessment must include:<br />a) environmental alignment sheets at an appropriate scale, clearly depicting the proposed route re-alignments;<br />b) results of any pre-construction surveys within the areas that were not previously subject to such surveys, and an indication of potential residual effects;<br />c) all associated mitigation measures that are beyond those identified during the OH-001-2014 proceeding;<br />d) analysis supporting the use of the measures in c), including any supplementary reports;<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information based on any supplemental surveys completed; and<br />f) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants, as well as copies of all written comments that may be provided to Trans Mountain by those consulted. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the assessment.(n/a) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 32 (c.7 Omahil – Spread 5B) ) For filings associated with Phase 32 (c.7 Omahil &ndash; Spread 5B)(Phase 34 (c.7 Tzeachten – Spread 6)) For filings associated with Phase 34 (c.7 Tzeachten &ndash; Spread 6)(Phase 37 (c.7 Surrey Bend – Spread 7)) For filings associated with Phase 37 (c.7 Surrey Bend &ndash; Spread 7) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 70 | <strong>Strain-based design</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, the following information related to strain-based design, where it is applied:<br />a) the location and rationale for selecting strain-based design in each location;<br />b) a report summarizing the adequacy of the strain-based design for various loading scenarios during pipeline construction and operation for each location provided in a); and<br />c) a list of standards and Project-specific specifications, including testing procedures, used in the strain-based design.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(n/a) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 71 | <strong>Riparian Habitat Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a Riparian Habitat Management Plan that would apply to all defined watercourses crossed by the Project. The plan must be supported with rationales and unambiguous criteria explaining under what circumstances each such measure and strategy would apply, and must include the following.<br />a) a description of&nbsp; the methods used to determine pre-construction functionality (e.g., for fish, wildlife, and rare plants) of the riparian habitat, including a justification how such functionality is assessed;<br />b) a description of the mitigation measures and the watercourse reclamation strategies (reclamation method, reclamation measures, and application criteria) for the range of defined watercourses crossed by the Project;<br />c) a description of the generalized vegetation planting plans for the range of defined watercourses crossed by the Project; that includes the diversity and density of species to be planted, planting locations, and application criteria;<br />d) clearly defined measureable reclamation goals and targets for years 1, 3, and 5, post-construction, to determine whether riparian habitat has returned, or is on a sufficient trajectory to return, to pre-construction functionality;<br />e) a discussion of how the mitigation measures, reclamation strategies, and vegetation planting plans are anticipated to return riparian habitat to pre-construction functionality, using the goals and targets provided in d);<br />f) a summary of the information in a)-d) for each defined watercourse crossing, that includes:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) watercourse crossing ID;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a defined riparian habitat buffer;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a catalogue of the pre-construction species diversity and density of the riparian habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) classification of riparian habitat functionality;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) area of the riparian habitat to be impacted;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the mitigation measures, reclamation strategy, and vegetation planting plan to be implemented; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) the measureable goals and targets;<br />g) details of the post-construction monitoring plan for the first five years of operations, including evaluations of reclamation activities, and potential corrective actions and enhancement measures that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Riparian Habitat Offset Plan, that would apply to all defined watercourse crossings located in watersheds identified as being above the riparian habitat disturbance threshold (&gt;18 per cent of riparian habitat disturbed in the watershed) or classified as High Sensitive fish-bearing by Trans Mountain&nbsp; during the OH-001-2014 proceeding, and, where, after the fifth complete growing season, riparian habitat has not returned, or is not trending towards sufficient pre-construction functionality.&nbsp; The plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) how the need for offset measures will be determined, including offset ratios;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) potential offset measures, the process for selecting which will be implemented, and an evaluation of the probability of their success; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) how the effectiveness of offset measures will be assessed, monitored, and reported on;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />j) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its plan, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan of updates.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 72 | <strong>Pipeline Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval<strong>, at least 3 months prior to commencing construction</strong>, an updated Project-specific Pipeline Environmental Protection Plan for the construction of the pipeline.<br />The updated Pipeline Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Pipeline Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Pipeline Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Pipeline Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;<br />e) updated alignment sheets;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Pipeline Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Pipeline Environmental Protection Plan.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 74 | <strong>Horizontal directional drilling (HDD) Noise Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction of each HDD crossing</strong>, a site-specific HDD Noise Management Plan that includes:<br />a) proposed hours of daytime and nighttime work;<br />b) baseline daytime and nighttime ambient sound levels at noise sensitive areas within 500 metres of the HDD entry and exit sites;<br />c) predicted noise levels caused by HDD at the most affected receptors without mitigation measures implemented;<br />d) proposed HDD noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />e) predicted noise levels at the most affected receptors with mitigation measures implemented, including noise contour map(s) showing potentially affected receptors;<br />f) an HDD noise monitoring program, including locations, methodology, and schedule;<br />g) a description of the public and Indigenous communication and complaint response process;<br />h) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents; and<br />i) confirmation that Trans Mountain will provide notice to nearby residents in the event that a planned blowdown is required, and that the planned blowdown will be completed during daytime hours whenever possible.(HDDs in Phase 26 (Spread 1)) For filings associated with&nbsp;HDDs in Phase 26 (Spread 1)(HDDs in Phase 27 (Spread 2) ) For filings associated with&nbsp;HDDs in Phase 27 (Spread 2)&nbsp;(HDDs in Phase 28 (Spread 3) ) For filings associated with&nbsp;HDDs in Phase 28 (Spread 3)&nbsp;(HDDs in Phase 29 (Spread 4) ) For filings associated with&nbsp;HDDs in Phase 29 (Spread 4)&nbsp;(HDDs in Phase 30 (Spread 5A) ) For filings associated with&nbsp;HDDs in Phase 30 (Spread 5A)&nbsp;(HDDs in Phase 30 (Spread 5B) ) For filings associated with&nbsp;HDDs in Phase 30 (Spread 5B)&nbsp;(HDDs in Phase 33 (Spread 6)) For filings associated with&nbsp;HDDs in Phase 33 (Spread 6)(HDDs in Phase 36 (Spread 7)) For filings associated with&nbsp;HDDs in Phase 36 (Spread 7) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 75 | <strong>Nooksack Dace and Salish Sucker Management Plan</strong><br />a) Trans Mountain must construct all watercourse crossings located within nooksack dace or salish sucker proposed or final critical habitat, as defined by Fisheries and Oceans Canada Recovery Strategies for the species, using trenchless crossing methods with entry and exit points located outside of the riparian habitat area, unless demonstrated to be not feasible.(?c)) For each watercourse crossing in b) where a trenchless crossing method is not feasible, <strong>at least 3 months prior to commencing construction of that crossing</strong>, Trans Mountain must file the following with the NEB for approval:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a summary of the trenchless crossing feasibility studies completed and a discussion of the risks and constraints associated with the trenchless watercourse crossing, and the rationale for not employing a trenchless method;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the updated watercourse crossing method, location of crossing, planned construction timing, and the provincial instream work window;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) any site-specific mitigation and reclamation measures, and species-specific habitat enhancement measures;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include measures listed in iii);<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the site-specific mitigation and reclamation measures, and species-specific enhancement measures, relate to Fisheries and Oceans Canada Recovery Strategies and Action Plans;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) details on any monitoring to be undertaken and a commitment to include any results in the post-construction environmental monitoring reports filed under Condition 151;<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />&nbsp;&nbsp;&nbsp;&nbsp; viii) a summary of consultations with Appropriate Government Authorities and any species experts. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.<br />&nbsp;(b) ) b) <strong>At least 3 months prior to commencing construction of any watercourse crossing located within nooksack dace or salish sucker proposed or final critical habitat</strong>, Trans Mountain must file a list of these watercourse crossings, and, for each, indicate whether or not a trenchless crossing method is feasible.(d)) For any watercourse crossing identified in b) where Trans Mountain will employ a trenched contingency crossing method, Trans Mountain must file with the NEB, for approval, the information listed in c), <strong>at least 30 days prior to commencing construction of the contingency watercourse crossing</strong>. | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 76 | <strong>Old Growth Management Areas Mitigation and Replacement Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction within old growth management areas</strong>, an Old Growth Management Areas Mitigation and Replacement Plan for these areas that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) avoidance and mitigation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />b) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />c) details on post-construction monitoring, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />d) the expected residual effects (including quantification) on old growth management areas, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional;<br />e) replacement or other offset measures that will be implemented to compensate for residual effects with the aim of no-net-loss to old growth forests within old growth management areas overall, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) discussion of the appropriateness of compensation for the old growth management area, taking its specific features into account, and of any potential limitations of the effectiveness of such replacement or offset measures;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an explanation with rationales on the amount and type of replacements or other offsets required;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a timeline for their implementation;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv)&nbsp; the selection of compensation sites;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) identification of the parties involved in planning and implementation and their respective roles and responsibilities, and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a description of the methods and schedule for monitoring and reporting to demonstrate compensation success;<br />f) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />g) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Old Growth Management Areas Mitigation and Replacement Plan.(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 77 | <strong>Archaeological and cultural heritage assessment &ndash; Lightning Rock </strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline between the Sumas Terminal and the Sumas Pump Station,</strong> a report on archaeological and cultural heritage field investigations undertaken to assess the potential impacts of Project construction and operations on the Lightning Rock site at Sumas, British Columbia. The report must include:<br />a) a detailed description of the assessment plan that was developed, in consultation with the St&oacute;:lo Collective, for the involvement of the St&oacute;:lo Collective in designing and undertaking surveys;<br />b) a description of the pre-construction archaeological and cultural heritage surveys conducted at the site, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) survey methodologies used; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) data and information sources, including information and Indigenous traditional knowledge provided by the St&oacute;:lo Collective;<br />c) a site description, including maps at appropriate scales and levels of detail, confirming the site boundaries;<br />d) an assessment of the potential environmental and socio-economic impacts of Project construction and operations on the archaeological resources and cultural heritage of the site;<br />e) all associated mitigation measures that are beyond those identified during the OH-001-2014 proceeding to address any identified impacts;<br />f) analysis supporting the use of the measures in e), including any additional relevant reports;<br />g) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) and Environmental Alignment Sheets to include any relevant information based on the surveys completed; and<br />h) a summary of consultations undertaken with the St&oacute;:lo Collective, and Appropriate Government Authorities, as well as copies of all written comments that may be provided to Trans Mountain by the St&oacute;:lo Collective or government authorities. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from the St&oacute;:lo Collective or government authorities, into the assessment.(Phase 35 (c.77 Lightning Rock – Spread 6)) For filings associated with Phase 35 (c.77 Lightning Rock &ndash; Spread 6) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 8 | <strong>Design temperatures &ndash; terminals and pump stations</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 3 months prior to ordering pipe for terminals and pump stations</strong>, confirmation, with rationale, that:<br />a) the selected maximum and minimum design temperatures are in accordance with CSA Z662-15, Clause 5.2.1;<br />b) the selected design temperatures are based on historical, location-specific extreme daily maximum and minimum temperatures, as opposed to average temperatures; and<br />c) the extent of the historical weather data used is commensurate with the expected operational life of the Project.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 80 | <strong>Noise Management Plan for construction at terminals and pump stations</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 3 months prior to commencing construction at each terminal and pump station</strong>, a Noise Management Plan for construction, where residences are within 300 metres of the proposed construction activities. The plan must include:<br />a) proposed hours of daytime and nighttime work;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />c) a noise monitoring program, including locations, methodology, and schedule;<br />d) a description of the public and Indigenous communication and noise complaint response process; and<br />e) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents.<div>&nbsp;</div><div>&nbsp;</div>(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 81 | <strong>Westridge Marine Terminal Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the Westridge Marine Terminal</strong>, an updated Project-specific Westridge Marine Terminal Environmental Protection Plan for the construction at the Westridge Marine Terminal.<br />The updated Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Westridge Marine Terminal Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Westridge Marine Terminal Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Westridge Marine Terminal Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Westridge Marine Terminal Environmental Protection Plan.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 82 | <strong>Light Emissions Management Plan for the Westridge Marine Terminal</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction at the Westridge Marine Terminal</strong>, a Light Emissions Management Plan for the Westridge Marine Terminal that includes:<br />a) a summary of the results of an area lighting study, including how potential impacts on surrounding communities and safety and operational requirements were considered;<br />b) a description of the mitigation and best practice measures considered for the terminal lighting design and how the proposed design and operation will minimize the impacts from light on land-based residents and marine users;<br />c) a summary of its consultations with Port Metro Vancouver, as well as copies of all written comments that may be provided to Trans Mountain by Port Metro Vancouver. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from Port Metro Vancouver, into the plan; and<br />d) a plan for how Trans Mountain will communicate its proposed terminal lighting design and associated mitigation measures to limit any nuisance lighting disturbances to land-based residents and marine users.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 83 | <strong>Westridge Marine Terminal (offshore) &ndash; pile design</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction at the Westridge Marine Terminal</strong>, the final design basis for the offshore pile foundation layout of the Westridge Marine Terminal.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 84 | <strong>Emergency release system at the Westridge Marine Terminal</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction at the Westridge Marine Terminal</strong>, its conclusions on the necessity of an emergency release system for the loading arms at the Westridge Marine Terminal. The conclusions must be supported by a comprehensive study describing the advantages and disadvantages of incorporating an emergency release system. This study must:<br />a) consider the application of: &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp; i) emergency release couplers; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an emergency release system, during both normal operating conditions and under abnormal conditions such as seismic events; and<br />b) include a description of the final emergency release system design, if applicable.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 85 | <strong>Air Emissions Management Plan &ndash; Burnaby Mountain tunnel construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing Burnaby Mountain tunnel construction activities</strong>, an Air Emissions Management Plan for tunnel construction. The plan must include:<br />a) proposed hours for daytime and nighttime work;<br />b) sources that would generate air emissions;<br />c) an Air Emissions and Dust Emissions Management Plan that includes mitigation measures, their predicted effectiveness, and implementation timeframes; and<br />d) a description of Trans Mountain&rsquo;s program for addressing complaints received during tunnel construction with respect to air and dust emissions, including a communication and notification plan.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 86 | <strong>Burnaby Mountain Tunnel Construction Noise Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing Burnaby Mountain tunnel construction activities</strong>, a Burnaby Mountain Tunnel Construction Noise Management Plan that includes:<br />a) proposed hours of daytime and nighttime work;<br />b) baseline daytime and nighttime ambient sound levels at noise sensitive areas within 500 metres of the entry and exit sites for the tunnel;<br />c) predicted noise levels at the most affected receptors caused by tunnel construction without mitigation measures implemented;<br />d) proposed noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />e) predicted noise levels at the most affected receptors with mitigation measures implemented, including noise contour map(s) showing the potentially affected receptors;<br />f) a tunnel construction noise monitoring program, including locations, methodology, and schedule;<br />g) criteria that will be used to determine when tunnel construction would be shut down due to noise;<br />h) a summary of its consultations with Appropriate Government Authorities and any potentially affected receptors (residences and businesses), as well as copies of all written comments that may be provided to Trans Mountain by those consulted. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan;<br />i) a description of the public and Indigenous communication and noise complaint response processes; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />j) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 87 | <strong>Groundwater Seepage Management Plan &ndash; Burnaby Mountain tunnel construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing Burnaby Mountain tunnel construction activities</strong>, a Groundwater Seepage Management Plan for tunnel construction. The plan must include:<br />a) an estimate quantifying the anticipated average and maximum amounts of groundwater seepage into the tunnel, and an assessment of any potential impacts on the water table;<br />b) a discussion of Trans Mountain&rsquo;s proposed pumping, treatment, and disposal options;<br />c) a description of the potential effects of dewatering of bedrock aquifers, springs and streams on local groundwater and surface water resources, and of measures that Trans Mountain would implement to mitigate such effects; &nbsp;and<br />d) a description of measures that Trans Mountain would implement during the operations phase in the event that there is groundwater seepage into the tunnel.(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 88 | <strong>Project organizational structure for Project construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a diagram of the Project&rsquo;s organizational structure (i.e., project management, design, and field staff) that clearly identifies roles, accountabilities, responsibilities, and reporting relationships for construction of the applicable Project components.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative, Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 9 | <strong>Quality Management Plan</strong><br />Trans Mountain must file with the NEB, <strong>at least 4 months prior to manufacturing any pipe and major components for the Project</strong>, a Project-specific Quality Management Plan that includes:<br />a) material/vendor qualification requirements;<br />b) quality control and assurance of pipe, fittings, and components that ensure all materials meet Trans Mountain&rsquo;s specifications (i.e., processes, procedures, specifications, random testing, inspection, and test reports);<br />c) mandatory documentation of process conditions during manufacture and verification of the conformance of manufacturer material test reports with Trans Mountain&rsquo;s requirements;<br />d) mandatory inspection requirements, inspector competency training, and qualifications;<br />e) non-conformance reporting and correction procedures;<br />f) change management process;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />g) commissioning requirements; and<br />h) material handling requirements during transportation.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal)&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)&nbsp;&nbsp;&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)&nbsp;&nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 90 | <strong>Consultation on improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a consultation plan for its review of its Emergency Response Plans and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing A3S4V5). This plan must include:<br />a) the consultation plan&rsquo;s scope;<br />b) the consultation plan&rsquo;s objectives;<br />c) a preliminary list of Appropriate Government Authorities, first responders, potentially affected Indigenous groups and affected landowners/tenants with whom Trans Mountain will consult;<br />d) a preliminary list of consultation locations and timing; and<br />e) the methods that will be used to track commitments made during consultations and to incorporate them into Trans Mountain&rsquo;s Emergency Management Program, including its Emergency Response Plans.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 91 | <strong>Plan for marine spill prevention and response commitments</strong><br />Trans Mountain must file with the NEB, <strong>within 6 months from the issuance date of the Certificate</strong>, a plan describing how it will ensure that it will meet the requirements of Condition 133 regarding marine spill prevention and response. The plan must be prepared in consultation with Transport Canada, the Canadian Coast Guard, the Pacific Pilotage Authority, Vancouver Fraser Port Authority, British Columbia Coast Pilots, Western Canada Marine Response Corporation, Fisheries and Oceans Canada, the Province of British Columbia, and potentially affected Indigenous groups, and must identify any issues or concerns raised and how Trans Mountain has addressed or responded to them.<br />Trans Mountain must provide a summary of its consultations for this purpose, including a description and rationale for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />Trans Mountain must provide the plan to the above-mentioned parties at the same time as it is filed with the NEB.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 92 | <strong>Updates under the <em>Species at Risk Act</em></strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a summary of any relevant updates under the <em>Species at Risk Act</em>, including new Schedule 1 listings and new or amended Recovery Strategies, Action Plans, and Management Plans for species that have the potential to be affected by the Project. For each species-specific update, the summary must include:<br />a) a discussion of the Project activities&rsquo; potential effects on the listed species or its critical habitat, including an explanation as to whether additional surveys are required to locate such critical habitat;&nbsp;<br />b) identification of all reasonable alternatives to the Project activities referred to in a), including avoidance measures, and a discussion on the potential effects of the alternatives, the chosen approach, and the rationale for selecting the chosen approach;<br />c) any additional site-specific mitigation;<br />d) any monitoring to be undertaken and a commitment to include monitoring results as part of the post-construction environmental monitoring reports filed under Condition 151;<br />e) an explanation as to how the responses to b), c) and d) above are consistent with applicable Recovery Strategies and Actions Plans; and<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the summary of updates, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 93 | <strong>Water well inventory</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, an inventory of physically verified (&ldquo;ground-truthed&rdquo;) water wells that are within 150 metres of either side of the centre of the pipeline right-of-way.<br />The filing must contain confirmation that Trans Mountain will maintain and update the inventory until the Project is abandoned or decommissioned pursuant to the NEB Act.<br />The inventory must include a description of the methods used to identify and physically verify wells, including:<br />a) each well&rsquo;s location in proximity to the right-of-way, including its GPS coordinates;<br />b) a description of each well&rsquo;s type or use (e.g., drinking water, agricultural use, use by Indigenous groups, any other uses);<br />c) each well&rsquo;s tenure or ownership (e.g., private, municipal, Indigenous community);<br />d) each well&rsquo;s operational status, including abandoned or decommissioned wells, and information about each well, including well depth, lithology, and water depth, if available;<br />e) a plan for updating the inventory over the life of the Project, including:&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the methods for identifying and verifying abandoned or decommissioned wells, and new or replacement wells; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the frequency of inventory updates;<br />f) a list of any properties or sections of the right-of-way that were not physically verified, including;<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the reason why properties or right-of-way sections were not physically accessed;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an estimate of the potential number of wells that have not been physically verified; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a proposed schedule for accessing properties or right-of-way sections; and<br />g) a description of Trans Mountain&rsquo;s plans for communicating information about the locations of water wells to owners or affected users.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2) ) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3) ) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4) ) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A) ) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B) ) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 94 | <strong>Consultation reports &ndash; protection of municipal water sources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, <strong>and on or before 31 January of each year during construction and of the first 5 years after commencing operations,</strong> a report on Trans Mountain&rsquo;s consultations with municipalities and regional districts, communities, and Indigenous groups related to the protection of municipal and community water sources, including those sources currently relied upon and sources identified for potential future use. Each report must include:<br />a) the name of the municipality, regional district, community, or Indigenous group consulted;<br />b) the methods, dates, and locations of all meetings or consultations;<br />c) a summary of all issues or concerns raised; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />d) a summary of any steps or measures that have been or will be undertaken, including groundwater modelling or monitoring, as a result of consultations with municipalities, regional districts, communities, or Indigenous groups. This summary must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) any updates or amendments to maintenance policies, systems, programs, procedures, practices, and activities aimed at preventing pipeline releases;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the criteria used to identify and select modelling or monitoring locations and parameters;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) results of any modelling or monitoring;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) any measures that have been taken to address modelling or monitoring results; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) any measures to share or to make accessible to municipalities, regional districts, communities, or Indigenous groups data or issues that arise regarding drinking water (aquifers, groundwater, and well water supplies); or<br />in the alternative to i)-v) above, an explanation why no further action is required to address or respond to issues or concerns raised.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3) &nbsp; &nbsp;&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 95 | <strong>Visual Impact Plan </strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Visual Impact Plan that includes:<br />a) the results of any supplemental visual modelling surveys conducted of select locations that are highly visible to the public, identified in consultation with Appropriate Government Authorities, and potentially affected Indigenous groups and affected landowners/tenants, where the proposed pipeline corridor deviates from the existing TMPL system right-of-way; and<br />b) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, and any new mitigation measures resulting from supplementary surveys.(n/a) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)&nbsp;&nbsp;&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 33 (Spread 6)) For filings associated with Phase 30 (Spread 6)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel)&nbsp; &nbsp; &nbsp;(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 97 | <strong>Traditional Land Use (TLU) and Traditional Marine Resource Use (TMRU) Investigation Report</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 2 months prior to commencing construction</strong>, a report describing pre-construction TLU and TMRU investigations that were not reported during the OH-001-2014 proceedings and that relate specifically to the Project (up to and including the foreshore lands and boundaries of the water lease for the Westridge Marine Terminal). The report must include:<br />a) the name of the potentially affected Indigenous group to which each investigation pertains;<br />b) a description of any identified potentially affected TLU or TMRU sites, resources, or activities;<br />c) the methods used to identify the potentially affected TLU or TMRU sites, resources or activities;<br />d) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate (to the extent possible) Project effects on TLU or TMRU sites, resources or activities;<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include mitigation measures (summarized in (d)) to reduce or eliminate (to the extent possible) Project effects on TLU or TMRU sites, resources or activities;<br />f) a summary of consultations undertaken with or concerns raised by potentially affected Indigenous groups regarding investigations on Project effects on the current use of lands and resources or marine resource use for traditional purposes, as well as copies of all written comments provided to Trans Mountain by potentially affected Indigenous groups to which each investigation pertains. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those Indigenous groups to which each investigation pertains, into the report;<br />g) a description of any outstanding concerns raised regarding potential Project effects on the current use of lands and resources or marine resource use for traditional purposes, including a description of how Trans Mountain will or address or respond to them, or an explanation why it will not address or respond to them; and<br />h) a summary of any outstanding TLU or TMRU investigations or follow-up activities that will not be completed prior to commencing construction, including estimated completion date(s), if applicable, and a description of how Trans Mountain has already identified, or will identify, any potentially affected TLU and TMRU sites, resources or activities for these outstanding investigations.<br />Trans Mountain must provide a copy of the report to each potentially affected group identified in a) at the same time that it is filed with the NEB.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a description and justification for how Trans Mountain has incorporated the results of its engagements, including any recommendations, into the plan;<br />c) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />d) the scope, methodology, and rationale for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />e) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and<br />f) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to potentially affected Indigenous groups, subject to appropriate protections for confidential information.<br />Trans Mountain must provide a copy of the report to all potentially affected groups at the same time that it is filed with the NEB.(Phase 01 (Westridge Marine Terminal) ) For filings associated with Phase 01 (Westridge Marine Terminal) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OC-065 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 99 | <strong>Landowner and tenant consultation reports&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, <strong>and every 6 months thereafter until 5 years after commencing Project operations</strong>:<br />a) a description of landowner and tenant consultations, including the consultation methods, dates, and a summary of any issues or concerns raised by landowners and tenants;<br />b) a summary of actions that Trans Mountain has undertaken to address or respond to each of the issues or concerns raised, or an explanation for why no actions were taken, and any outstanding concerns; and<br />c) confirmation that Trans Mountain will make available to a landowner or tenant, upon request, a copy of the consultation records related to that landowner or tenant.(Phase 26 (Spread 1)) For filings associated with Phase 26 (Spread 1)(Phase 27 (Spread 2)) For filings associated with Phase 27 (Spread 2)(Phase 28 (Spread 3)) For filings associated with Phase 28 (Spread 3)(Phase 29 (Spread 4)) For filings associated with Phase 29 (Spread 4)(Phase 30 (Spread 5A)) For filings associated with Phase 30 (Spread 5A)(Phase 30 (Spread 5B)) For filings associated with Phase 30 (Spread 5B)(Phase 33 (Spread 6)) For filings associated with Phase 33 (Spread 6)(Phase 36 (Spread 7)) For filings associated with Phase 36 (Spread 7)(Phase 38 (Westridge Delivery Lines)) For filings associated with Phase 38 (Westridge Delivery Lines)(Phase 39 (Burnaby Tunnel)) For filings associated with Phase 39 (Burnaby Tunnel) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.(Hinton to Hargreaves (150 km from TMX-Anchor Loop)) For filings associated with&nbsp;Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with&nbsp;Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with&nbsp;Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with&nbsp;Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with&nbsp;Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with&nbsp;Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with&nbsp;Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with&nbsp;Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(n/a) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB <strong>at least thirty days prior to commencing construction</strong> of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 110 | <strong>Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act</em> and <em>Species at Risk Act</em> permit(s) &ndash; pipeline</strong><br />For instream activities, except for those related to the Westridge Marine Terminal:<br />a) for any instream activities that will require Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act,</em> Trans Mountain must file with the NEB,<strong> at least 10 days prior to commencing the respective instream activities, </strong>a copy of the Authorization under paragraph 35(2)(b) of the<em> Fisheries Act</em>.<br />b) for any instream activities that will require a permit(s) under the<em> Species at Risk Act</em>, Trans Mountain must file with the NEB, <strong>at least 10 days prior to commencing the respective instream activities, </strong>a copy of the permit(s) issued under the<em> Species at Risk Act</em>.<br />c) Trans Mountain must confirm, <strong>within 30 days after commencing operations, </strong>that:<br />i) any required <em>Fisheries Act</em> Authorization(s) were obtained from Fisheries and Oceans Canada and filed with the NEB pursuant to a), or notify the Board if no Authorization(s) were required; and<br />ii) any required <em>Species at Risk Act</em> permit(s) were obtained from the competent minister under the <em>Species at Risk Act</em> and filed with the NEB pursuant to b), or notify the Board if no permit(s) were required.(a)) for any instream activities that will require Authorization(s) under paragraph 35(2)(b) of the <em>Fisheries Act,</em> Trans Mountain must file with the NEB,<strong> at least 10 days prior to commencing the respective instream activities, </strong>a copy of the Authorization under paragraph 35(2)(b) of the<em> Fisheries Act</em>.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(b)) for any instream activities that will require a permit(s) under the<em> Species at Risk Act</em>, Trans Mountain must file with the NEB, <strong>at least 10 days prior to commencing the respective instream activities, </strong>a copy of the permit(s) issued under the<em> Species at Risk Act</em>.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(c)) Trans Mountain must confirm, <strong>within 30 days after commencing operations, </strong>that:<br />i) any required <em>Fisheries Act</em> Authorization(s) were obtained from Fisheries and Oceans Canada and filed with the NEB pursuant to a), or notify the Board if no Authorization(s) were required; and<br />ii) any required <em>Species at Risk Act</em> permit(s) were obtained from the competent minister under the <em>Species at Risk Act</em> and filed with the NEB pursuant to b), or notify the Board if no permit(s) were required.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 111 | <strong>Joining Programs</strong><br />Trans Mountain must develop Joining Programs and file them with the NEB <strong>at least 45 days prior to commencing welding of, respectively</strong>:<br />a) field circumferential production, tie-in, and repair pipeline welds, including the tie-in welds between existing segments and Line 1 or Line 2; and<br />b) terminals and pump stations.<br />The Joining Programs must include:<br />i) welder qualification requirements;<br />ii) requirements for welding inspector qualifications and duties;<br />iii) welding procedure specifications;<br />iv) non-destructive examination () specifications;<br />v) procedure qualification records for welding procedure specifications and NDE specifications;<br />vi) a quality assurance program for field welds and welding procedures; and<br />vii) any additional information that supports the Joining Program.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)<br />&nbsp;(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 112 | <strong>Pressure testing</strong><br />a) Trans Mountain must pressure test the new and reactivated pipeline segments, terminals, and pump stations with a liquid medium.<br />b) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing</strong>, a Pressure Testing Program that demonstrates compliance with applicable codes, standards, and regulatory requirements.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 113 | <strong>Hydrostatic Testing Plan</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing of any Project component</strong>, a Hydrostatic Testing Plan for the Project that includes:<br />a) the locations of all water withdrawal and discharge sites;<br />b) a discussion of any clearing activities or any other associated works, if required, that will allow for the transportation of the hydrostatic test water;<br />c) water withdrawal rates;<br />d) water withdrawal volumes;<br />e) the flow rate/volume of water at the withdrawal sites; and<br />f) site-specific mitigation measures to be implemented at the water withdrawal and discharge sites or at any other locations required to allow for the transportation of hydrostatic test water, including a description of the water quality monitoring methods to be used on hydrostatic testing water prior to discharge; and<br />g) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 114 | <strong>NDE of final tie-in welds</strong><br />Trans Mountain must delay NDE of final tie-in welds (i.e.: welds which will not be subjected to hydrostatic testing) and any repairs to them <strong>for at least 48 hours following weld completion</strong>. Trans Mountain must include this requirement in the NDE specification of its Joining Program required by Condition 111.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 115 | <strong>SCADA and leak detection system design</strong><br />Trans Mountain must file with the NEB, reports describing the final design of the expanded Trans Mountain Pipeline System&rsquo;s SCADA and leak detection systems. These reports must include:<br />a) for the commercially available external leak detection systems resulting from Trans Mountain&rsquo;s participation in joint industry projects, <strong>at least 45 days prior to commencing backfilling on Line 2 and the new delivery pipelines, </strong>a status update, including a timeline for implementation; and<br />b)<strong> at least 3 months prior applying for leave to open the Project</strong>:<br />i) a status update for the following complementary leak detection technologies that Trans Mountain is considering, including a timeline for implementation:<ol><li>a secondary Computational Pipeline Monitoring (CPM) system operating in parallel with the Project&rsquo;s proposed CPM; and</li><li>aerial surveillance systems resulting from Trans Mountain&rsquo;s participation in joint industry projects;</li></ol>ii) an explanation of how Trans Mountain&rsquo;s complementary leak detection system(s) supports the leak detection capabilities of the primary CPM system(s);<br />iii) for all leak detection systems applicable to the Project, performance targets for:<ol><li>sensitivity;</li><li>accuracy;</li><li>reliability; and</li><li>robustness;</li></ol>iv) a validation plan for the performance targets in iii), including alarm testing, to be implemented within the first year of Project operation;<br />v) rationale for the selected time windows(s) (i.e. averaging periods) for the CPM system(s);<br />vi) a copy of Trans Mountain&rsquo;s public awareness program on recognizing and reporting leaks;<br />vii) a description of how the leak detection system and its relevant procedures comply with CSA Z662 Annex&nbsp;E;<br />viii) a list of other best practices such as API (American Petroleum Institute) recommended practices related to leak detection and control centre management;<br />ix) a description of how Trans Mountain&rsquo;s revised procedureshave introduced a rule directing the Control Centre Operator to perform a controlled shut down of the pipeline when a leak cannot be ruled out in a given time period; and<br />x) a plan, including a timeline for implementation, for upgrading the existing measurement and data acquisition instrumentation to improve the leak detection performance of Line 1.(a)) for the commercially available external leak detection systems resulting from Trans Mountain&rsquo;s participation in joint industry projects, <strong>at least 45 days prior to commencing backfilling on Line 2 and the new delivery pipelines, </strong>a status update, including a timeline for implementation; and(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(b)) <strong>at least 3 months prior applying for leave to open the Project</strong>:<br />i) a status update for the following complementary leak detection technologies that Trans Mountain is considering, including a timeline for implementation:<ol><li>a secondary Computational Pipeline Monitoring (CPM) system operating in parallel with the Project&rsquo;s proposed CPM; and</li><li>aerial surveillance systems resulting from Trans Mountain&rsquo;s participation in joint industry projects;</li></ol>ii) an explanation of how Trans Mountain&rsquo;s complementary leak detection system(s) supports the leak detection capabilities of the primary CPM system(s);<br />iii) for all leak detection systems applicable to the Project, performance targets for:<ol><li>sensitivity;</li><li>accuracy;</li><li>reliability; and</li><li>robustness;</li></ol>iv) a validation plan for the performance targets in iii), including alarm testing, to be implemented within the first year of Project operation;<br />v) rationale for the selected time windows(s) (i.e. averaging periods) for the CPM system(s);<br />vi) a copy of Trans Mountain&rsquo;s public awareness program on recognizing and reporting leaks;<br />vii) a description of how the leak detection system and its relevant procedures comply with CSA Z662 Annex&nbsp;E;<br />viii) a list of other best practices such as API (American Petroleum Institute) recommended practices related to leak detection and control centre management;<br />ix) a description of how Trans Mountain&rsquo;s revised procedureshave introduced a rule directing the Control Centre Operator to perform a controlled shut down of the pipeline when a leak cannot be ruled out in a given time period; and<br />x) a plan, including a timeline for implementation, for upgrading the existing measurement and data acquisition instrumentation to improve the leak detection performance of Line 1.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 121 | <strong>Financial Assurances Plan &ndash; operations phase</strong><br />a) Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to applying for leave to open Line 2,</strong> a Financial Assurances Plan that includes details of the financial resources and secured sources of funds that will be necessary to pay, without limitation, all actual loss or damage, costs and expenses, including cleanup and remediation, and loss of non-use value relating to non-use of a public resource associated with an unintended or uncontrolled release from the Project during the operations phase.<a href=http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn1">[1]</a> These costs may arise from, among other things, potential accidents, malfunctions, and failures during the Project operations phase, including all spills originating from the pipeline and the terminals.<br />The Financial Assurances Plan must be signed by an officer of the company, verifying that it is accurate, complete, and, at a minimum, meets the criteria and coverage levels described below:<br />i) Criteria for financial assurance instruments and plan:<ol><li>Any letter of credit that forms part of the Financial Assurances Plan must be unconditional and irrevocable, segregated from Trans Mountain&#39;s day-to-day business activities, and be dedicated to providing funds to cover the costs described in sub a) above, without limitation.</li><li>Third party liability insurance must be current, and broad, respecting the scope of environmental damages covered by the policy; the policy will be consistent with provisions available in the insurance market(i.e., only exceptional/non-standard perils, taking into account the Project&#39;s nature and scope, would be excluded from coverage). Such insurance must be structured on a multi-year basis, recognizing potential loss of income by persons sustaining damage caused by Trans Mountain, over a reasonable number of years after the event.</li><li>A portion of cash reserves or a portion of future cash flows of the Project may be included as instruments in the Financial Assurances Plan, provided they are secured by a commitment letter from an officer of the company confirming that the funds will be dedicated to the Financial Assurances Plan without restrictions for the period specified by the officer.</li><li>Parental and other third party guarantors must be registered within a Canadian jurisdiction and must have financial strength that is demonstrated in balance sheet values and ratios and credit ratings. For example, total assets less total liabilities of the guarantor should be several multiples of the liability assumed in the Trans Mountain guarantee.</li></ol>ii) Financial assurance components and coverage levels:<br />Trans Mountain&#39;s Financial Assurances Plan must provide a total coverage, for the Project as a whole, of $1.1 billion<a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn2">[2]</a> for the costs described in sub a) above, without limitation. The plan should include the following components and minimum coverage levels:<ol><li>Ready cash: Trans Mountain must have unfettered access to at least $100 million to cover costs, including compensation to third parties for losses and damages in the near term, while insurance claims are being processed. Once used, this source of cash must be replenished immediately to cover the costs of a potential future spill. This can be in the form of a letter of credit, surety bond or other form acceptable to the NEB.</li><li>Core coverage: Trans Mountain must put in effect and maintain current at all times a core financial coverage of at least $1 billion that includes third party liability insurance and other financial assurance instruments that comply with the criteria. Core coverage must be a portfolio approach with multiple financial instruments used and may not be composed of a single financial instrument (e.g., only third party liability insurance). At least one component of core coverage must be funds that are readily accessible to Trans Mountain (e.g., cash reserves held by the general partner and not distributed to the limited partners).<br />Trans Mountain may use a number of financial and insurance instruments in its Financial Assurances Plan. However, sales of Project assets used for transporting hydrocarbon commodities will not be eligible candidates.&nbsp; Below are some illustrative financial and insurance instruments that could be potential candidates for the Financial Assurances Plan:</li></ol><ul><li>Irrevocable, unfettered letter of credit.</li><li>Secured line of credit.</li><li>Cash reserves held by the general partner and not distributed to the limited partners (and verifiable on Trans Mountain Pipelines Limited Partnership&#39;s balance sheet).</li><li>Internal cash flow, committed by Trans Mountain to financial assurances.</li><li>Industry pooled fund.</li><li>Third party liability insurance with exclusions for only exceptional/non-standard perils.</li><li>No fault third party liability insurance.</li><li>Parental and other third party guarantees provided by parties demonstrating financial strength through balance sheets and credit ratings.</li><li>Other instruments developed by Trans Mountain and the insurance and financial markets.</li></ul>b) Trans Mountain must file the following with the NEB:<br />i) <strong>At least 6 months prior to applying for leave to open Line 2</strong>, a report from an independent third party that has assessed the Financial Assurances Plan and its key components against the criteria and actual experiences of industry damage claims. The report must summarize the key features of each financial and insurance instrument proposed for inclusion in the Financial Assurances Plan.<br />ii) <strong>At least 3 months prior to applying for leave to open Line 2</strong>, a supplement to the report described in b)i) that provides verification of any third party liability insurance coverage, a copy of the insurance certificate, and a summary of the insurance policy&#39;s key features. This summary must include: limits on insurance coverage, deductible amounts, the risks and perils and properties covered by the insurance policy, the exclusions from coverage, Trans Mountain&#39;s obligations, effective dates, and names of insurers and reinsurers.<br />iii) <strong>With its first leave to open application for Line 2</strong>, a report describing the steps it took to eliminate any deficiencies in its Financial Assurances Plan that were identified in the independent third party report referenced in b)i) and the NEB&#39;s subsequent review.<br />iv) <strong>On or before 31 January of each year after commencing operations</strong>, a letter signed by an officer of the company verifying that all components of the Financial Assurances Plan remain as the NEB approved and sufficient to meet the financial assurance coverage levels described in ii).<br />v) <strong>At least 2 months prior to any intended change(s) to the Financial Assurances Plan during the Projects operations phase</strong>, a letter, for approval, detailing the intended change(s) and how the change(s) provides the same or greater level of protection.<br />vi) <strong>Within 30 days after accessing any component of the Financial Assurances Plan</strong>, a report detailing the component accessed, the reason for accessing it, and Trans Mountain&rsquo;s plan to ensure that it continues to meet the requirements of its NEB-approved Financial Assurances Plan.<br />&nbsp;<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref1">[1]</a> &nbsp;&nbsp;&nbsp; In the context of this condition, &ldquo;operations phase&rdquo; refers to the period after the Project receives leave to open approval and prior to it being fully abandoned.<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref2">[2]</a> &nbsp;&nbsp;&nbsp; The NEB&rsquo;s basis for any final coverage level is described in its report to Governor in Council.<br />&nbsp;" | In Progress | During Construction Phase | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 128 | <strong>Offset Measures Plan for residual effects on caribou habitat</strong><br />Trans Mountain must file with the NEB for approval, in accordance with the timelines below, an Offset Measures Plan for each affected caribou range, the goal of which is to offset all unavoidable and residual direct and indirect Project-related effects on caribou habitat, after taking into account the implementation of the measures identified in the relevant Environmental Protection Plan(s) for the Project and the Caribou Habitat Restoration Plan (see Condition&nbsp;37) measures. The Offset Measures Plan must include:<br />a) A preliminary version, to be filed <strong>at least 3 months prior to applying for leave to open</strong>, with the plan&rsquo;s criteria and measurable goals and that includes:<br />i) an initial quantification of the area of caribou habitat directly and indirectly disturbed by the Project;<br />ii) a list of the potential on-the-ground offset measures available;<br />iii) each potential offset measure&rsquo;s appropriate offset ratio, based on consultation with expert federal and provincial authorities and on a review of the scientific literature on conservation offsets;<br />iv) each potential offset measure&rsquo;s expected effectiveness including a discussion of uncertainty and how measures align with criteria specified in the scientific literature specific to conservation offsets;<br />v) each potential offset measure&rsquo;s relative qualitative and quantitative value toward achieving the offset; and<br />vi) a conceptual decision-making tree(s) or decision framework(s) that will be used to select which specific potential offset measures and accompanying offset ratios will be used under what circumstances.<br />b) A final version, to be filed <strong>on or before 31 January after the second complete growing season after completing final clean-up</strong>, including:<br />i) the contents of the preliminary Offset Measures Plan, with any updates identified in a revision log that includes the rationale for any changes;<br />ii) a tabular list of the potential offset measures and appropriate offset ratios to be implemented or already underway, including site-specific details and maps showing the locations, and an explanation of how they meet criteria in the scientific literature for offsets;<br />iii) a description of factors considered when determining the location of offset measures, including consideration of how the measures could maximize benefits to landscape variables;<br />iv) a schedule indicating when potential offset measures will be initiated and their estimated completion dates;<br />v)either an assessment of the predicted offset measures&rsquo; effectiveness including a discussion of uncertainty and a quantitative compilation showing how the measures would offset the previously determined residual effects, or a plan for completing an assessment of the potential offset measures&rsquo; effectiveness and value; and<br />vi) an update on the restoration success to support offset measure decisions.<br />Both the preliminary and final versions of the plan must also include the following:<ol><li>a summary of its consultations with Appropriate Government Authorities and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Offset Measures Plan;</li><li>a description of how Trans Mountain has taken any available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and</li><li>evidence of Trans Mountain&rsquo;s consideration of any updates to the applicable Recovery Strategy, as well as to range boundaries and identified critical habitat made prior and up to the date on which leave to open is granted.</li></ol>(a)) a)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(b)) b)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)<br />&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)<br />&nbsp;(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)<br />&nbsp;(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 130 | <strong>Groundwater Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing operations</strong>, a Groundwater Monitoring Program that pertains to all terminals and pump stations, and for any vulnerable aquifers along the pipeline route. The&nbsp; program must include, at a minimum:<br />a) locations of groundwater monitoring wells, their depths, the rationales for well locations (including how groundwater flow direction was considered), groundwater flow velocity, parameters to be monitored and frequency of monitoring;<br />b) a description of any program changes required to meet this condition for facilities with an existing Groundwater Monitoring Program;<br />c) methods, criteria and rationale for identifying vulnerable aquifers along the pipeline route;<br />d) applicable regulatory criteria for comparing monitoring results, and a process outlining what steps will be followed should monitoring results indicate a negative change in groundwater quality;and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the program.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 135 | <strong>Slack line flow conditions</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to&nbsp; commencing operation of Line 1, and at least 2 months prior to applying for leave to open Line 2, respectively</strong>, the following:<br />a) a list of locations having potential for slack line flow when each of the pipelines is operated at 100&nbsp;per&nbsp;cent of its maximum operating pressure (MOP), 80 per cent of its MOP, and 50 per cent of its MOP; and<br />b) a description of the following regarding detecting and preventing slack line flow conditions:<br />i) operational measures on Line 1 and Line 2; and<br />ii) design measures on Line 2.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 146 | <strong>Reports on engagement with Indigenous groups &ndash; operations</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations,</strong> a report on the engagement activities it has undertaken with Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;<br />b)&nbsp; the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 149 | <strong>Caribou Habitat Restoration and Offset Measures Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the first complete growing season after commencing operations</strong>, a program for monitoring and verifying the effectiveness of caribou habitat restoration and offset measures implemented as part of the final Caribou Habitat Restoration Plan (Condition 37) and the final Offset Measures Plan (Condition 128). This program must include:<br />a) the scientific methods or protocols for short- and long-term monitoring of the restoration and offset measures, and effectiveness of the measures;<br />b) monitoring frequency, timing, and locations, and the rationale for each;<br />c) protocols for how restoration and offset measures will be adapted, as required, based on the monitoring results from the program&rsquo;s implementation;<br />d) a summary of Trans Mountain&rsquo;s consultation with Appropriate Government Authorities and any species experts on the design of the monitoring program; and<br />e) a proposed schedule for filing reports on monitoring results and adaptive management measures to the NEB, Environment and Climate Change Canada, and appropriate provincial authorities to be contained in the Caribou Habitat Restoration and Offset Measures Monitoring Program as well as at the beginning of each report filed.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation) | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 150 | <strong>Caribou habitat restoration and offset measures monitoring report(s)</strong><br />Trans Mountain must file with the NEB, <strong>based on the approved schedule for the Caribou Habitat Restoration and Offset Measures Monitoring Program </strong>(required by Condition 149), a report(s) outlining the monitoring program&rsquo;s results, including the observed effectiveness of habitat restoration and offset measures for each affected caribou range, and how those measures will be adapted, as required, based on monitoring results. Any proposed changes to the NEB-approved reporting schedule must be included within the relevant report prior to any reporting on a revised schedule.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up, </strong>a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants.<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />i) an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />ii) a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />iii) an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)<br />&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 152 | <strong>Pipeline segment reactivation (Hinton to Hargreaves; Darfield to Black Pines) &ndash; new certificate and certificate validation</strong><br />Trans Mountain must file with the NEB<strong>, before expiry of the previous certificate identified in Condition 19</strong>, a new certificate with a supporting report issued by an independent certification body<a href=#_ftn1">[1]</a> for the two pipeline segments identified in Condition 19. The certificate and report must demonstrate that the two pipeline segments:<br />a) are fit for service for the specified operating conditions;<a href="#_ftn2">[2]</a><br />b) meet all applicable requirements of CSA Z662; and<br />c) will meet the hydrostatic test requirements outlined in CSA Z662, at any time during the certified period.<br />The certificate must be valid for at least 5 years and be validated on an annual basis during the certified period.<br />The supporting report must include the qualifications of the independent certification body, the justification used to grant the certificate, and the expiry date of the certificate.<div>&nbsp;<div><a href="#_ftnref1">[1]</a> &nbsp; For Conditions 19, 122 and 152, an &ldquo;independent certification body&rdquo; is an internationally recognized company or organization, such as Lloyd&rsquo;s Register or Det Norske Veritas, which is able to certify compliance to statutory requirements. The independent certification body must have expertise in pipeline integrity. The NEB reserves the right to accept or reject the certificate. In addition, the NEB&rsquo;s decision is not contingent on the results of the certificate.</div><div><a href="#_ftnref2">[2]</a>&nbsp; For Conditions 19, 122 and 152, &ldquo;operating conditions&rdquo; must include the Project-specific operating conditions, possible transient flow conditions, slack flow conditions, and effects on operating pressure due to temperature changes.</div></div>(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)" | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 154 | <strong>Riparian Habitat Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up,</strong> a Riparian Habitat Reclamation Evaluation Report and Offset Plan.&nbsp;<br />a) The report must include, for each defined watercourse crossed by the Project:<br />i) an evaluation of performed reclamation activities against the identified measureable goals and targets (required by Condition 71), that includes an identification of the defined watercourses whereriparian habitat that has not returned to, or trending towards a sufficient, pre-construction functionality;<br />ii) a description of the proposed enhancement measures and corrective actions selected and the rationale for the selected option(s); and<br />iii) a schedule for when the enhancement measures and corrective actions will be initiated and an estimated timeline for completion, including any monitoring that will be required.<br />b) The plan must include, for defined watercourses crossed by the Project located in watersheds identified as being above the riparian habitat disturbance threshold (&gt;18 per cent of riparian habitat disturbed in the watershed) or classified as High Sensitive fish-bearing by Trans Mountain, during the OH-001-2014 proceeding, and, where, after the fifth complete growing season, riparian habitat has not returned, or is not trending towards sufficient pre-construction functionality:<br />i) a description of the proposed offset measures selected that includes details with rationales on the amount and type of offsets required, how the offset measures would be implemented, and the location of offset sites;<br />ii) a schedule for when the offset measures will be initiated, an estimated timeline for completion, including any monitoring that will be required, and a schedule for when the results of the offsets monitoring will be filed with the Board that demonstrate offset success.<br />iii) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the report/plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />iv) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 155 | <strong>Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the <em>Species at Risk Act</em>, that includes:<br />a) an evaluation of avoidance and mitigation success with reference to the measurable goals outlined in the Rare Ecological Community and Rare Plant Population Management Plan required by Condition 40;<br />b) identification of communities, species, and critical habitats that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />c) identification of any ongoing effects to ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, or on any early draft, candidate, proposed, or final critical habitat under the <em>Species at Risk Act</em>;<br />d) for the ongoing effects identified in c), a Final Rare Ecological Community and Rare Plant Population Offset Plan that updates the Preliminary Rare Ecological Community and Rare Plant Population Offset Plan required by Condition 40, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 156 | <strong>Wetland Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Wetland Reclamation Evaluation Report and Offset Plan that includes:<br />a) the extent (in hectares), by wetland type, that was impacted by Project construction and associated activities;<br />b) for each wetland impacted, an evaluation of mitigation and reclamation success with reference to the measurable goals outlined in the Wetland Survey and Mitigation Plan required by Condition 41;<br />c) identification of any wetlands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, an evaluation of any temporary or ongoing loss of any individual functional condition (e.g., habitat, hydrology and biogeochemistry);<br />e) for any wetland that has not achieved reclamation success in terms of overall wetland function, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition, a Final Wetland Offset Plan that updates the Preliminary Wetland Offset Plan required by Condition 41, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 157 | <strong>Grasslands Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the tenth complete growing season after completing final clean-up</strong>, a Grasslands Reclamation Evaluation Report and Offset Plan that applies to native grasslands in the British Columbia interior and that includes:<br />a) the extent (in hectares) of grasslands that were impacted by Project construction and associated activities;<br />b) an evaluation of reclamation success with reference to the measurable goals outlined in the Grasslands Survey and Mitigation Plan required by Condition 42;<br />c) an identification of any grasslands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for those grasslands that have not yet achieved reclamation success, a Final Grasslands Offset Plan that updates the preliminary plan required by Condition 42, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 18 | <strong>Valve locations and upgrades &ndash; Line 1</strong><br />Trans Mountain must file with the NEB <strong>for approval</strong>, <strong>at least 6 months prior to commencing construction</strong>, its final valve location assessment for Line 1. This assessment must include:<br />a) a plan for upgrading existing manual block valves to automated or remotely operable valves, and a plan for adding new valves, including initiation and completion dates for the required activities;<br />b) a table showing each valve&rsquo;s location, function, and description (the description must include valve type, valve closure time, and whether the valve can be remotely controlled by the control centre);<br />c) confirmation that the valve closure times provided in b) will not cause unsafe transient pressures according to the final transient analysis, along with a summary of the analysis;<br />d) calculated volume release and elevation plots in a format similar to that provided by Trans Mountain in its Oil Spill Outflow Model Results for Line 2 for May 2014 Route (Filing A3Z8G6);<br />e) an outflow volume versus chainage graph illustrating the effectiveness of the valve locations provided in&nbsp; b), in a format similar to that provided in Figure 4 of Attachment 2 to Trans Mountain&rsquo;s response to NEB Information Request No. 3.050b) (Filing A4H2D7);<br />f) full-bore release and spill extent mapping that identifies and plots all geohazards identified by Trans Mountain in its Natural Hazards Management Program or otherwise, at the time of its submission, in a format and scale similar to the maps provided by Trans Mountain in Filing A3Z8G7; and<br />g) the associated Line 1 risk assessment used to determine the new valve locations and planned valve upgrades in a).(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves) &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 19 | <strong>Pipeline segment reactivation (Hinton to Hargreaves; Darfield to Black Pines) &ndash; engineering assessment and certificate </strong><br />&nbsp;<br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>:<br />a) an engineering assessment for the above two pipeline segments, in accordance with Canadian Standards Association (CSA) Z662-15, Clauses 3.3 and 10.15.2; and<br />b) a certificate with a supporting report issued by an independent certification body[1],&nbsp; stating unconditionally that the above two pipeline segments:<br />i) are fit for service for the specified operating conditions; [2]<br />ii) meet all applicable requirements of CSA Z662-15; and<br />iii) will meet the hydrostatic test requirements outlined in CSA Z662-15, Clause 8, at any time during the certified period.<br />&nbsp;<br />The certificate must be valid for at least 5 years and be validated on an annual basis during the certified period.<br />The supporting report must include the qualifications of the independent certification body, the justification used to grant the certificate, and the expiry date of the certificate.<br />&nbsp;<br />&nbsp;<br />[1] For Conditions 19, 122 and 152, an &ldquo;independent certification body&rdquo; is an internationally recognized company or organization, such as Lloyd&rsquo;s Register or Det Norske Veritas, which is able to certify compliance to statutory requirements. The independent certification body must have expertise in pipeline integrity. The NEB reserves the right to accept or reject the certificate. In addition, the NEB&rsquo;s decision is not contingent on the results of the certificate.<br />&nbsp;<br />[2] For Conditions 19, 122 and 152, &ldquo;operating conditions&rdquo; must include the Project-specific operating conditions, possible transient flow conditions, slack flow conditions, and effects on operating pressure due to temperature changes.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 2 | <strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Hinton to Hargreaves (150 km from TMX-Anchor Loop)) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Hinton to Hargreaves (150 km from TMX-Anchor Loop)) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 31 | <strong>Reactivation of the Niton Pump Station</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing any pump station construction</strong>, an engineering assessment for the Niton Pump Station, in accordance with CSA Z662. The engineering assessment must demonstrate that the pump station is fit for its intended service, and meets all applicable requirements of CSA Z662.(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 36 | <strong>Pre-construction caribou habitat assessment</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range</strong>, a detailed caribou habitat assessment of the Project right-of-way through each caribou range traversed by the Project, including a 500 metre buffer on either side. The framework of the habitat assessment must use the updated critical habitat polygons delineated by the Southern Mountain Caribou Recovery Team and components of critical habitat outlined in the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014). The habitat assessment must include:<br />a) map(s) indicating the location of the habitat;<br />b) a description of the amount of habitat and the existing habitat alteration, in hectares;<br />c) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge into consideration into the assessment including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />d) a description of how Trans Mountain has incorporated input from Appropriate Government Authorities and species experts into the assessment methodology; and<br />e) a description of the type of habitat characterized by the biophysical attributes of critical habitat, as defined in the applicable Recovery Strategy.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 37 | Trans Mountain must file with the NEB for approval, in accordance with the timelines below, preliminary and final versions of a CHRP for each caribou range potentially affected by the Project.(a)) <strong>Preliminary CHRP </strong>&ndash; to be filed <strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range. </strong>This version of the CHRP must include the following:<br />i) the CHRP&rsquo;s goals and measureable targets for each caribou range, including the goal of avoidance of critical habitat destruction;<br />ii) a detailed description of measures that will be used to avoid or lessen Project activities that impact critical habitat, and the rationale for selecting the measures;<br />iii) a list of criteria used to identify potential caribou habitat restoration sites;<br />iv) conceptual decision-making tree(s) or decision framework(s) that will be used to identify and prioritize potential caribou habitat restoration sites, and mitigative actions to be used at different types of sites, including consideration of typical site factors that may constrain implementation;<br />v) a literature review upon which the decision-making tree(s) or decision framework(s) are based, including:<br />1) an identification of applicable temporal and spatial caribou habitat restoration methodologies;<br />2) an assessment of the relative effectiveness of the identified methodologies; and<br />3) a detailed methodology of how the literature review was conducted.<br />vi) the quantifiable targets and performance measures that will be used to evaluate the extent of predicted residual effects, CHRP effectiveness, the extent to which the goals and measurable targets have been met, and the need for further measures to offset unavoidable and residual effects on caribou habitat;<br />vii) a schedule indicating when mitigation measures will be initiated and their estimated completion dates;<br />viii) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge studies into consideration in identifying potential caribou habitat restoration sites including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />ix) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the preliminary CHRP.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(b)) <strong>Final CHRP </strong>&ndash; to be filed <strong>on or before 1 November after the first complete growing season after completing final clean-up.</strong> This version of the CHRP must include the following:<br />i) the preliminary CHRP, with any updates identified in a revision log that includes the rationale for any changes to decision-making criteria;<br />ii) a complete tabular list of caribou habitat restoration sites, including locations, spatial areas, habitat quality descriptions, site-specific restoration activities, and challenges;<br />iii) a description of how selected restoration measures are consistent with the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014);<br />iv) maps or updated Environmental Alignment Sheets showing the site locations;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />v) specification drawings for the implementation of each restoration method;<br />vi) a qualitative and quantitative and assessment of the total area of direct and indirect disturbance to caribou habitat that will be restored, the duration of spatial disturbance, and the area-based extent of the resulting unavoidable and residual effects to be offset, including indirect disturbance; and<br />vii) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the final CHRP.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 38 | <strong>Sowaqua Spotted Owl Mitigation Plan </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction of any Project component within the Sowaqua spotted owl wildlife habitat area</strong>, a Sowaqua Spotted Owl Mitigation Plan that includes:<br />a) a summary of results from supplemental surveys conducted in the Sowaqua spotted owl wildlife habitat area;<br />b) the area of habitat potentially directly and indirectly affected by the Project;<br />c) a description of how an avoidance, mitigation, and offset hierarchy was considered in the plan;<br />d) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable goals for evaluating mitigation success;<br />e) an evaluation of offset options within or outside of the Sowaqua spotted owl wildlife habitat area, an indication of the selected option, and the rationale for the selected option;<br />f) details on post-construction monitoring of mitigation measures and offset measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, any adjustments to the offset measures, and a proposed reporting schedule;<br />g) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />h) details on how the mitigation and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the mitigation plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the mitigation plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the mitigation plan.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Hinton to Hargreaves (150 km from TMX-Anchor Loop)) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 40 | <strong>Rare Ecological Community and Rare Plant Population Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, an updated Rare Ecological Community and Rare Plant Population Management Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the Species at Risk Act, that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results, and a demonstration of the overall adequacy of the rare ecological community and rare plant surveys, including the adequacy for the identification of biophysical attributes for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act;<br />b) avoidance and mitigation measures to be implemented during construction and operations, including all relevant measures committed to throughout the OH-001-2014 proceeding and any new measures resulting from supplementary surveys, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />c) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />d) details on post-construction monitoring, including survey methods, the appropriate number of years of monitoring to determine the success of each type of avoidance and mitigation measure, corrective actions that might be necessary, and the circumstances under which each such action would be taken;<br />e) a Preliminary Rare Ecological Community and Rare Plant Population Offset Plan for any ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, and for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act, and that, after five years of operations, have ongoing effects. This preliminary plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a rationale for why the community, species, or critical habitat cannot be avoided by a sufficient distance to avoid both direct and indirect residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the expected residual effects on that community, species, or critical habitat, including a discussion of the potential for time lags &nbsp;between when Project effects occur and when mitigation measures would become fully functional, and taking into account the success on past projects of the proposed mitigation and corrective measures in b) and d) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the appropriateness of offsets for the community, species or critical habitat, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of how the avoidance, mitigation, monitoring, corrective and offset measures are consistent with any applicable recovery, action or management strategies or plans for the community, species or critical habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Rare Ecological Community and Rare Plant Population Management Plan, including confirmation that the avoidance, mitigation, monitoring, corrective, and offset measures in the Rare Ecological Community and Rare Plant Population Management Plan will be implemented to the extent feasible in the case of discovery via their inclusion in the Rare Ecological Communities or Rare Plant Species Discovery Contingency Plan.(n/a) n/a(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 41 | <strong>Wetland Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Wetland Survey and Mitigation Plan for wetlands potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results and a demonstration of the overall adequacy of the wetland surveys;<br />b) a description of any wetlands for which ground-based surveys were not possible, an explanation as to why not, attempts made to obtain access, and what further information on each wetland will be collected immediately prior to or during construction;<br />c) a description of the functional condition of each wetland for comparison during post-construction monitoring, including individual functional conditions (e.g., habitat, hydrology and biogeochemistry, including the presence and abundance of migratory birds and species at risk), and a description of the methods used to determine the type and amount of each individual wetland function and the overall functional condition;<br />d) a description of the crossing methods, mitigation measures and reclamation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each such method and measure will be applied;<br />e) measurable goals against which the success of wetland mitigation and reclamation will be evaluated, including a description of how such goals incorporate the aim of returning wetlands to their original functionality while allowing for reasonable natural variation, and including measurable goals for each of the first-, third- and fifth-year post-construction monitoring reporting stages for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies;<br />f) a description of how the<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss of wetland function, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />g) details of the post-construction monitoring plan for wetlands for the first five years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Wetland Offset Plan for any wetland that has not achieved reclamation success in terms of overall wetland function after five years of operations, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition &ndash; this plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the expected residual effects on the wetland, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in d) and g) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the wetland, taking its specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios and indicator species, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, details with rationales on the offset measures that will be implemented before or during the first five years of operations to compensate for expected temporary or ongoing losses to individual functional conditions, including the amount and type of offsets required, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wetland Survey and Mitigation Plan.(n/a) n/a(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 42 | <strong>Grasslands Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Grasslands Survey and Mitigation Plan for native grasslands in the B.C. interior that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of survey results for such grasslands, including but not limited to native plant species diversity, species at risk, the density and distribution of existing invasive plant species, and the presence of cryptogamic crust, together with a demonstration of the adequacy of such surveys and a summary of existing and ongoing land management impacts;<br />b) a description (including quantification) of overlap of the Project with grasslands and of expected residual effects;<br />c) a description of the mitigation and reclamation measures to be implemented for grasslands during construction and operations, including the extent to which native seed will be used, with rationales and unambiguous criteria explaining under what circumstances each such measure will be applied;<br />d) measurable goals against which the success of grassland mitigation and reclamation will be evaluated, including goals related to cryptogamic crust recovery, invasive species control, and access control, and how existing and ongoing land management impacts and land-use changes by landowners outside the control of Trans Mountain will be taken into account;<br />e) a description of how the:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy, and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss for grasslands, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />f) details of the post-construction monitoring plan for grasslands for the first ten years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />g) a Preliminary Grasslands Offset Plan for those grasslands that, after ten years of operations, have not achieved reclamation success. This plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) expected residual effects on the grasslands, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in c) and f) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the grasslands, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offsets measures will be monitored, assessed, and reported on, and problems corrected;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />i) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />j) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grasslands Survey and Mitigation Plan.(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 43 | <strong>Watercourse crossing inventory</strong><br />Trans Mountain must file with the NEB, <strong>at least 5 months prior to commencing any watercourse crossing construction activities</strong>, the following:<br />a) an updated inventory of all watercourses to be crossed, including, for each crossing:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the name of the watercourse being crossed and an identifier for the crossing;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the location of the crossing;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) the primary and contingency crossing methods;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) planned construction timing;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) information on the presence of fish and fish habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) information on the composition of riparian habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) the provincial instream work window;<br />&nbsp;&nbsp;&nbsp;&nbsp; viii) the proposed least risk biological window and the rationale to support the proposed least risk biological window if it differs from the provincial instream work window; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ix) an indication of whether any of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; cannot be implemented;<br />b) detailed generic design drawings of trenchless, dry open-cut, frozen open-cut, and isolation crossings of various watercourse types;<br />c) site-specific information for each watercourse crossing where any of Fisheries and Oceans Canada&rsquo;s applicable &ldquo;Measures to Avoid Causing Harm to Fish and Fish Habitat&rdquo; cannot be implemented for the primary pipeline construction method:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) detailed crossing-specific design drawings;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) photographs up-stream, down-stream, and at the crossing location;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the fish species and habitat that is present at the crossing location, and if fish spawning is likely to occur within the immediate area;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of the composition of the riparian habitat at the crossing location and an indication if the riparian habitat has a limiting effect on the productive capacity of the watercourse, and if its removal or disturbance represents a potential influence on fish communities;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) the site-specific mitigation and habitat enhancement measures to be used to minimize impacts;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) any potential residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) proposed reclamation measures; and<br />&nbsp;&nbsp;&nbsp;&nbsp; viii) a discussion of the potential impacts to local fisheries resources within the immediate area as a result of the crossing&rsquo;s construction;<br />d) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the inventory, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />e) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 44 | <strong>Wildlife Species at Risk Mitigation and Habitat Restoration Plans&nbsp; </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction,</strong> Wildlife Species at Risk Mitigation and Habitat Restoration Plans for each species whose draft, candidate, proposed, or final critical habitat is directly or indirectly affected by the Project. Each plan must include:<br />a) a summary of supplementary pre-construction survey results, including surveys for biophysical attributes of critical habitat;<br />b) the location and type of critical habitat, for those wildlife species with early draft and candidate critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />c) the location, types and total spatial area for each type of critical habitat for those wildlife species with proposed or final critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />d) a detailed description of measures that will be used to avoid the destruction of critical habitat;<br />e) a detailed description of mitigation and habitat restoration measures to be implemented to reduce direct and indirect Project effects on critical habitat, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation and critical habitat restoration success;<br />f) identification and review of alternative mitigation and habitat restoration measures to avoid or lessen direct and indirect Project effects on critical habitat, and the rationale for the selected measure(s);<br />g) detailed description of how selected mitigation and critical habitat restoration measures address the potential for time lags between when the Project impacts occur and when mitigation and critical habitat restoration measures are implemented and are fully functional;<br />h) details on post-construction monitoring of mitigation measures and critical habitat restoration measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />i) details on how the mitigation, critical habitat restoration measures, and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />j) a commitment to include the results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />k) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plans including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />l) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowner/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />m) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wildlife Species at Risk Mitigation and Habitat Restoration Plans.(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 47 | <strong>Access Management Plan(s)</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, an Access Management Plan(s) to be included within the updated Environmental Protection Plans required by Conditions 72 and 78. Each plan must address issues related to soil, vegetation, fish and fish habitat, and wildlife and wildlife habitat. Each plan must also describe access control measures proposed to control both human and predator access during construction and operations, and include:<br />a) objectives of the plan;<br />b) measurable goals for evaluating the plan&rsquo;s success in achieving its objectives;<br />c) a summary of any related baseline information that has been or will be collected to aid in evaluating the plan&rsquo;s success, and justification of the adequacy of this baseline information, or a rationale if no baseline information has or will be collected;<br />d) a list of sites where access control measures will be implemented for construction and those that will remain in place throughout operations, the control measure(s) proposed at those sites, and the rationale for selecting those sites and measures;<br />e) the methods for monitoring the effectiveness of access control measures implemented during construction and operations, and justification of the adequacy of such monitoring;<br />f) a description of available adaptive management measures and of the criteria Trans Mountain will use to determine if and when adaptive management measures are warranted based on monitoring results;<br />g) a commitment to report, as part of Trans Mountain&rsquo;s post-construction environmental monitoring reports (required by Condition 151), on the control measures implemented, monitoring undertaken, and the success of control measures in meeting Access Management Plan goals and objectives, as well as a schedule, with rationale, for reporting throughout operations;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />i) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Plan/Report.(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 48 | <strong>Navigation and navigation safety plan</strong><br />Trans Mountain must file with the NEB, <strong>for approval</strong>, <strong>at least 4 months prior to commencing construction</strong>, a Navigation and Navigation Safety Plan that includes:<br />a) an updated list of navigable waterways to be crossed by or affected by the Project (including power lines, marine terminal, temporary or permanent bridge crossings, or other ancillary works that are physically or operationally connected to the Project);<br />b) an updated listing of effects of the Project on navigation and navigation safety for each of the identified waterways identified in a);<br />c) proposed mitigation measures to address Project effects on navigation and navigation safety for each of the identified waterways, including adherence to codes and standards (such as the CSA); and<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and waterway users, regarding their navigational use of each of the identified waterways. In its summary, Trans Mountain must:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) describe the Appropriate Government Authorities, potentially affected Indigenous groups, and commercial and recreational waterway users consulted;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) describe how Trans Mountain identified those consulted; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Hinton to Hargreaves (150 km from TMX-Anchor Loop)) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Hinton to Hargreaves (150 km from TMX-Anchor Loop)) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 55 | <strong>Fugitive Emissions Management Plan for pump stations</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction at any pump stations</strong>, a Fugitive Emissions Management Plan for the pump stations associated with the Project that includes:<br />a) a description of the procedures implemented for leak detection and the criteria used in selecting target leaking components;<br />b) quantification methods considered and the rationale for the selected method(s);<br />c) monitoring frequency for each target leaking component and the parameters that will be measured;<br />d) a decision framework that will be implemented to repair or replace leaking components;<br />e) a description of record-keeping procedures; and<br />f) a discussion of additional mitigation measures that will be employed to minimize fugitive emissions.(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 56 | <strong>Grizzly Bear Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction in each vulnerable grizzly bear population unit / grizzly bear management area</strong>, a Grizzly Bear Mitigation Plan for each of these areas. Trans Mountain must provide a rationale for why any vulnerable grizzly bear population units / grizzly bear management units potentially affected by the Project are not addressed in the plan. The Grizzly Bear Mitigation Plan(s) must include:<br />a) a summary of results from any supplemental surveys conducted;<br />b) potential direct and indirect effects of Project activities on vulnerable grizzly bear population units and grizzly bear management units;<br />c) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation success;<br />d) details on post-construction monitoring of mitigation measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />e) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan(s); and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grizzly Bear Mitigation Plan, including confirmation that the mitigation, monitoring, and corrective measures in this plan will be implemented in the case of discovery via their inclusion in Trans Mountain&rsquo;s Wildlife Species of Concern Discovery Contingency Plan.(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 59 | <strong>Worker accommodation strategy</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a worker accommodation strategy, developed in consultation with appropriate municipal or provincial authorities. The strategy must include:<br />a) a final summary of all proposed accommodations, including the location of any temporary camp(s);<br />b) the number of workers that will be housed; and<br />c) a description of how the strategy addresses any concerns or requests raised in consultation with municipal or provincial authorities.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the event that temporary camp(s) are to be used, the strategy must also include:<br />i) a description of how the potential environmental and socio-economic impacts have been assessed, and a description of all associated mitigation measures;<br />ii) copies of, or reference to, any mitigation or operational plans that will be required or implemented for the camp(s), including a description of how Trans Mountain has incorporated any additional mitigation measures into relevant Environmental Protection Plan(s);<br />iii) copies of any necessary municipal or provincial permits for any camp(s) that have been received 3 months prior to construction. &nbsp;If camp permits are not yet in place 3 months prior to commencing construction, provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a list of the outstanding camp permits and a schedule for when these camp permits will be in place; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) copies of any outstanding camp permits prior to commencing construction;<br />iv) copies or excerpts of all policies relating to the rules of conduct for workers housed at the camp(s);<br />v) confirmation that all policies relating to the camp(s) will be provided to workers;<br />vi) confirmation that all policies relating to the camp(s) were made available to all local communities and other relevant service providers in proximity to any camp(s) that will be used for the Project; and<br />vii) a summary of its consultations with affected landowners/tenants where any camp(s) will be located. Trans Mountain must provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a description of the information provided to landowners/tenants; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Strategy.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)&nbsp;&nbsp;&nbsp;(b)) <div>file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:</div>(i)) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(n/a) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(ii)) <div><strong>at least 30 days prior to commencing construction</strong>;</div>(n/a) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(n/a) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(n/a) For filings associated with Hinton to Hargreaves (150 km from TMX-Anchor Loop)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(c) and d)) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i). | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)<br />&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 21 (Line 1 Valves)) For filings associated with Phase 21 (Line 1 Valves)<br />&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 71 | <strong>Riparian Habitat Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 3 months prior to commencing construction</strong>, a Riparian Habitat Management Plan that would apply to all defined watercourses crossed by the Project. The plan must be supported with rationales and unambiguous criteria explaining under what circumstances each such measure and strategy would apply, and must include the following.<br />a) a description of&nbsp; the methods used to determine pre-construction functionality (e.g., for fish, wildlife, and rare plants) of the riparian habitat, including a justification how such functionality is assessed;<br />b) a description of the mitigation measures and the watercourse reclamation strategies (reclamation method, reclamation measures, and application criteria) for the range of defined watercourses crossed by the Project;<br />c) a description of the generalized vegetation planting plans for the range of defined watercourses crossed by the Project; that includes the diversity and density of species to be planted, planting locations, and application criteria;<br />d) clearly defined measureable reclamation goals and targets for years 1, 3, and 5, post-construction, to determine whether riparian habitat has returned, or is on a sufficient trajectory to return, to pre-construction functionality;<br />e) a discussion of how the mitigation measures, reclamation strategies, and vegetation planting plans are anticipated to return riparian habitat to pre-construction functionality, using the goals and targets provided in d);<br />f) a summary of the information in a)-d) for each defined watercourse crossing, that includes:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) watercourse crossing ID;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a defined riparian habitat buffer;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a catalogue of the pre-construction species diversity and density of the riparian habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) classification of riparian habitat functionality;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) area of the riparian habitat to be impacted;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the mitigation measures, reclamation strategy, and vegetation planting plan to be implemented; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) the measureable goals and targets;<br />g) details of the post-construction monitoring plan for the first five years of operations, including evaluations of reclamation activities, and potential corrective actions and enhancement measures that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Riparian Habitat Offset Plan, that would apply to all defined watercourse crossings located in watersheds identified as being above the riparian habitat disturbance threshold (&gt;18 per cent of riparian habitat disturbed in the watershed) or classified as High Sensitive fish-bearing by Trans Mountain&nbsp; during the OH-001-2014 proceeding, and, where, after the fifth complete growing season, riparian habitat has not returned, or is not trending towards sufficient pre-construction functionality.&nbsp; The plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) how the need for offset measures will be determined, including offset ratios;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) potential offset measures, the process for selecting which will be implemented, and an evaluation of the probability of their success; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) how the effectiveness of offset measures will be assessed, monitored, and reported on;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />j) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its plan, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan of updates.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 72 | <strong>Pipeline Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval<strong>, at least 3 months prior to commencing construction</strong>, an updated Project-specific Pipeline Environmental Protection Plan for the construction of the pipeline.<br />The updated Pipeline Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Pipeline Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Pipeline Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Pipeline Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;<br />e) updated alignment sheets;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Pipeline Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Pipeline Environmental Protection Plan.(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | Closed | Prior to the Construction Phase | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 92 | <strong>Updates under the <em>Species at Risk Act</em></strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a summary of any relevant updates under the <em>Species at Risk Act</em>, including new Schedule 1 listings and new or amended Recovery Strategies, Action Plans, and Management Plans for species that have the potential to be affected by the Project. For each species-specific update, the summary must include:<br />a) a discussion of the Project activities&rsquo; potential effects on the listed species or its critical habitat, including an explanation as to whether additional surveys are required to locate such critical habitat;&nbsp;<br />b) identification of all reasonable alternatives to the Project activities referred to in a), including avoidance measures, and a discussion on the potential effects of the alternatives, the chosen approach, and the rationale for selecting the chosen approach;<br />c) any additional site-specific mitigation;<br />d) any monitoring to be undertaken and a commitment to include monitoring results as part of the post-construction environmental monitoring reports filed under Condition 151;<br />e) an explanation as to how the responses to b), c) and d) above are consistent with applicable Recovery Strategies and Actions Plans; and<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the summary of updates, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 94 | <strong>Consultation reports &ndash; protection of municipal water sources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, <strong>and on or before 31 January of each year during construction and of the first 5 years after commencing operations,</strong> a report on Trans Mountain&rsquo;s consultations with municipalities and regional districts, communities, and Indigenous groups related to the protection of municipal and community water sources, including those sources currently relied upon and sources identified for potential future use. Each report must include:<br />a) the name of the municipality, regional district, community, or Indigenous group consulted;<br />b) the methods, dates, and locations of all meetings or consultations;<br />c) a summary of all issues or concerns raised; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />d) a summary of any steps or measures that have been or will be undertaken, including groundwater modelling or monitoring, as a result of consultations with municipalities, regional districts, communities, or Indigenous groups. This summary must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) any updates or amendments to maintenance policies, systems, programs, procedures, practices, and activities aimed at preventing pipeline releases;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the criteria used to identify and select modelling or monitoring locations and parameters;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) results of any modelling or monitoring;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) any measures that have been taken to address modelling or monitoring results; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) any measures to share or to make accessible to municipalities, regional districts, communities, or Indigenous groups data or issues that arise regarding drinking water (aquifers, groundwater, and well water supplies); or<br />in the alternative to i)-v) above, an explanation why no further action is required to address or respond to issues or concerns raised.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-005-OC-2 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a description and justification for how Trans Mountain has incorporated the results of its engagements, including any recommendations, into the plan;<br />c) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />d) the scope, methodology, and rationale for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />e) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and<br />f) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to potentially affected Indigenous groups, subject to appropriate protections for confidential information.<br />Trans Mountain must provide a copy of the report to all potentially affected groups at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Phase 20 (Niton Pump Station Reactivation)) For filings associated with Phase 20 (Niton Pump Station Reactivation)(Phase 22 (Hinton to BC Border Reactivation)) For filings associated with Phase 22 (Hinton to BC Border Reactivation)(Phase 23 (BC Border to Hargreaves Reactivation)) For filings associated with Phase 23 (BC Border to Hargreaves Reactivation)(Phase 24 (Darfield to Blackpines Reactivation)) For filings associated with Phase 24 (Darfield to Blackpines Reactivation) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.<div>&nbsp;</div><div>&nbsp;</div>(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB <strong>at least thirty days prior to commencing construction</strong> of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 2 | <strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(b)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(ii)) <div><strong>at least 30 days prior to commencing construction</strong>;</div>(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(c) and d)) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i). | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(n/a) n/a(n/a) n/a(n/a) n/a(n/a) n/a(n/a) n/a(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(n/a) n/a(n/a) n/a(n/a) n/a(n/a) n/a(n/a) n/a(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-004-OC-049 |  | 2019-06-20 | 2019-06-21 |  | In Progress | Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 25 (Wolf Pump Station)) For filings associated with Phase 25 (Wolf Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)<br />&nbsp;(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)<br />&nbsp;(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)<br />&nbsp;(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)<br />&nbsp;(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)<br />&nbsp;(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)<br />&nbsp;(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)<br />&nbsp;(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)<br />&nbsp;(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)<br />&nbsp; | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 100 | <strong>Heritage resources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction of individual Project components as described in Condition 10(a)</strong>:<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b); and<br />d) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c).(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 103 | <strong>Utility crossings </strong><br />Trans Mountain must file with the Board, <strong>at least 30 days prior to commencing construction</strong>, a list of all underground utilities to be crossed by the Project. The list must include the location and owners of the utilities to be crossed, as well as confirmation that all the agreements or crossing permits for those utilities to be crossed have been acquired or will be acquired prior to construction.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Temp. Inf. Sites (Spread 5A)) <p>For filings associated with Temp. Inf. Sites (Spread 5A)</p><p>&nbsp;</p><br />&nbsp;(Temp. Inf. Sites (Spread 5B)) For filings associated with Temp. Inf. Sites (Spread 5B)<br />&nbsp;(Temp. Inf. Sites (Spread 6)) For filings associated with Temp. Inf. Sites (Spread 6)<br />&nbsp;(Temp. Inf. Sites (Spread 7)) For filings associated with Temp. Inf. Sites (Spread 7) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 128 | <strong>Offset Measures Plan for residual effects on caribou habitat</strong><br />Trans Mountain must file with the NEB for approval, in accordance with the timelines below, an Offset Measures Plan for each affected caribou range, the goal of which is to offset all unavoidable and residual direct and indirect Project-related effects on caribou habitat, after taking into account the implementation of the measures identified in the relevant Environmental Protection Plan(s) for the Project and the Caribou Habitat Restoration Plan (see Condition&nbsp;37) measures. The Offset Measures Plan must include:<br />a) A preliminary version, to be filed <strong>at least 3 months prior to applying for leave to open</strong>, with the plan&rsquo;s criteria and measurable goals and that includes:<br />i) an initial quantification of the area of caribou habitat directly and indirectly disturbed by the Project;<br />ii) a list of the potential on-the-ground offset measures available;<br />iii) each potential offset measure&rsquo;s appropriate offset ratio, based on consultation with expert federal and provincial authorities and on a review of the scientific literature on conservation offsets;<br />iv) each potential offset measure&rsquo;s expected effectiveness including a discussion of uncertainty and how measures align with criteria specified in the scientific literature specific to conservation offsets;<br />v) each potential offset measure&rsquo;s relative qualitative and quantitative value toward achieving the offset; and<br />vi) a conceptual decision-making tree(s) or decision framework(s) that will be used to select which specific potential offset measures and accompanying offset ratios will be used under what circumstances.<br />b) A final version, to be filed <strong>on or before 31 January after the second complete growing season after completing final clean-up</strong>, including:<br />i) the contents of the preliminary Offset Measures Plan, with any updates identified in a revision log that includes the rationale for any changes;<br />ii) a tabular list of the potential offset measures and appropriate offset ratios to be implemented or already underway, including site-specific details and maps showing the locations, and an explanation of how they meet criteria in the scientific literature for offsets;<br />iii) a description of factors considered when determining the location of offset measures, including consideration of how the measures could maximize benefits to landscape variables;<br />iv) a schedule indicating when potential offset measures will be initiated and their estimated completion dates;<br />v)either an assessment of the predicted offset measures&rsquo; effectiveness including a discussion of uncertainty and a quantitative compilation showing how the measures would offset the previously determined residual effects, or a plan for completing an assessment of the potential offset measures&rsquo; effectiveness and value; and<br />vi) an update on the restoration success to support offset measure decisions.<br />Both the preliminary and final versions of the plan must also include the following:<ol><li>a summary of its consultations with Appropriate Government Authorities and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Offset Measures Plan;</li><li>a description of how Trans Mountain has taken any available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and</li><li>evidence of Trans Mountain&rsquo;s consideration of any updates to the applicable Recovery Strategy, as well as to range boundaries and identified critical habitat made prior and up to the date on which leave to open is granted.</li></ol> | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance. | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 140 | <strong>Post-construction greenhouse gas (GHG) assessment report</strong><br />Trans Mountain must file with the NEB for approval, <strong>within</strong> <strong>2 months after commencing operations</strong>, an updated GHG assessment report specific to the Project. The report must include:<br />a) the methodology used for the assessment, including the sources of GHG emissions, assumptions, and methods of estimation;<br />b) the total direct GHG emissions generated from Project construction, including land-clearing;<br />c) a breakdown of direct GHG emissions generated by the construction of individual Project components (pipeline, pump stations, tank terminals and Westridge Marine Terminal) and by land-clearing activities; and<br />d) a comparison and discussion of the direct GHG emissions calculated in b) with the predicted emissions in Trans Mountain&rsquo;s application and subsequent submissions. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 142 | <strong>GHG Emissions Offset Plan &ndash; Project construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>within 4 months after commencing operations</strong>, a plan for providing offsets for all direct GHG emissions generated from Project construction, as determined in Condition 140. The plan must include:<br />a) a list and discussion of all possible offset options considered;<br />b) the criteria against which each option was assessed for viability;<br />c) a description of the offset option(s) selected for direct GHG emissions generated from Project construction, and the rationale for selecting the option(s);<br />d) confirmation that the selected offset option is registered under the approved quantification protocols and has been verified by an accredited &ldquo;verification body&rdquo; ;<br />e) a schedule indicating when the selected offset options(s) will be initiated; and<br />f) an accounting of offsets confirming no net GHG emissions from Project construction. | In Progress | Post Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 146 | <strong>Reports on engagement with Indigenous groups &ndash; operations</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations,</strong> a report on the engagement activities it has undertaken with Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;<br />b)&nbsp; the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB. | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 149 | <strong>Caribou Habitat Restoration and Offset Measures Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the first complete growing season after commencing operations</strong>, a program for monitoring and verifying the effectiveness of caribou habitat restoration and offset measures implemented as part of the final Caribou Habitat Restoration Plan (Condition 37) and the final Offset Measures Plan (Condition 128). This program must include:<br />a) the scientific methods or protocols for short- and long-term monitoring of the restoration and offset measures, and effectiveness of the measures;<br />b) monitoring frequency, timing, and locations, and the rationale for each;<br />c) protocols for how restoration and offset measures will be adapted, as required, based on the monitoring results from the program&rsquo;s implementation;<br />d) a summary of Trans Mountain&rsquo;s consultation with Appropriate Government Authorities and any species experts on the design of the monitoring program; and<br />e) a proposed schedule for filing reports on monitoring results and adaptive management measures to the NEB, Environment and Climate Change Canada, and appropriate provincial authorities to be contained in the Caribou Habitat Restoration and Offset Measures Monitoring Program as well as at the beginning of each report filed. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 150 | <strong>Caribou habitat restoration and offset measures monitoring report(s)</strong><br />Trans Mountain must file with the NEB, <strong>based on the approved schedule for the Caribou Habitat Restoration and Offset Measures Monitoring Program </strong>(required by Condition 149), a report(s) outlining the monitoring program&rsquo;s results, including the observed effectiveness of habitat restoration and offset measures for each affected caribou range, and how those measures will be adapted, as required, based on monitoring results. Any proposed changes to the NEB-approved reporting schedule must be included within the relevant report prior to any reporting on a revised schedule. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up, </strong>a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants.<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />i) an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />ii) a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />iii) an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 155 | <strong>Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the <em>Species at Risk Act</em>, that includes:<br />a) an evaluation of avoidance and mitigation success with reference to the measurable goals outlined in the Rare Ecological Community and Rare Plant Population Management Plan required by Condition 40;<br />b) identification of communities, species, and critical habitats that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />c) identification of any ongoing effects to ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, or on any early draft, candidate, proposed, or final critical habitat under the <em>Species at Risk Act</em>;<br />d) for the ongoing effects identified in c), a Final Rare Ecological Community and Rare Plant Population Offset Plan that updates the Preliminary Rare Ecological Community and Rare Plant Population Offset Plan required by Condition 40, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 156 | <strong>Wetland Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Wetland Reclamation Evaluation Report and Offset Plan that includes:<br />a) the extent (in hectares), by wetland type, that was impacted by Project construction and associated activities;<br />b) for each wetland impacted, an evaluation of mitigation and reclamation success with reference to the measurable goals outlined in the Wetland Survey and Mitigation Plan required by Condition 41;<br />c) identification of any wetlands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, an evaluation of any temporary or ongoing loss of any individual functional condition (e.g., habitat, hydrology and biogeochemistry);<br />e) for any wetland that has not achieved reclamation success in terms of overall wetland function, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition, a Final Wetland Offset Plan that updates the Preliminary Wetland Offset Plan required by Condition 41, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 157 | <strong>Grasslands Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the tenth complete growing season after completing final clean-up</strong>, a Grasslands Reclamation Evaluation Report and Offset Plan that applies to native grasslands in the British Columbia interior and that includes:<br />a) the extent (in hectares) of grasslands that were impacted by Project construction and associated activities;<br />b) an evaluation of reclamation success with reference to the measurable goals outlined in the Grasslands Survey and Mitigation Plan required by Condition 42;<br />c) an identification of any grasslands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for those grasslands that have not yet achieved reclamation success, a Final Grasslands Offset Plan that updates the preliminary plan required by Condition 42, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | <strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 36 | <strong>Pre-construction caribou habitat assessment</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range</strong>, a detailed caribou habitat assessment of the Project right-of-way through each caribou range traversed by the Project, including a 500 metre buffer on either side. The framework of the habitat assessment must use the updated critical habitat polygons delineated by the Southern Mountain Caribou Recovery Team and components of critical habitat outlined in the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014). The habitat assessment must include:<br />a) map(s) indicating the location of the habitat;<br />b) a description of the amount of habitat and the existing habitat alteration, in hectares;<br />c) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge into consideration into the assessment including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />d) a description of how Trans Mountain has incorporated input from Appropriate Government Authorities and species experts into the assessment methodology; and<br />e) a description of the type of habitat characterized by the biophysical attributes of critical habitat, as defined in the applicable Recovery Strategy.(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 37 | Trans Mountain must file with the NEB for approval, in accordance with the timelines below, preliminary and final versions of a CHRP for each caribou range potentially affected by the Project.(a)) <strong>Preliminary CHRP </strong>&ndash; to be filed <strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range. </strong>This version of the CHRP must include the following:<br />i) the CHRP&rsquo;s goals and measureable targets for each caribou range, including the goal of avoidance of critical habitat destruction;<br />ii) a detailed description of measures that will be used to avoid or lessen Project activities that impact critical habitat, and the rationale for selecting the measures;<br />iii) a list of criteria used to identify potential caribou habitat restoration sites;<br />iv) conceptual decision-making tree(s) or decision framework(s) that will be used to identify and prioritize potential caribou habitat restoration sites, and mitigative actions to be used at different types of sites, including consideration of typical site factors that may constrain implementation;<br />v) a literature review upon which the decision-making tree(s) or decision framework(s) are based, including:<br />1) an identification of applicable temporal and spatial caribou habitat restoration methodologies;<br />2) an assessment of the relative effectiveness of the identified methodologies; and<br />3) a detailed methodology of how the literature review was conducted.<br />vi) the quantifiable targets and performance measures that will be used to evaluate the extent of predicted residual effects, CHRP effectiveness, the extent to which the goals and measurable targets have been met, and the need for further measures to offset unavoidable and residual effects on caribou habitat;<br />vii) a schedule indicating when mitigation measures will be initiated and their estimated completion dates;<br />viii) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge studies into consideration in identifying potential caribou habitat restoration sites including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />ix) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the preliminary CHRP.(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(b)) <strong>Final CHRP </strong>&ndash; to be filed <strong>on or before 1 November after the first complete growing season after completing final clean-up.</strong> This version of the CHRP must include the following:<br />i) the preliminary CHRP, with any updates identified in a revision log that includes the rationale for any changes to decision-making criteria;<br />ii) a complete tabular list of caribou habitat restoration sites, including locations, spatial areas, habitat quality descriptions, site-specific restoration activities, and challenges;<br />iii) a description of how selected restoration measures are consistent with the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014);<br />iv) maps or updated Environmental Alignment Sheets showing the site locations;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />v) specification drawings for the implementation of each restoration method;<br />vi) a qualitative and quantitative and assessment of the total area of direct and indirect disturbance to caribou habitat that will be restored, the duration of spatial disturbance, and the area-based extent of the resulting unavoidable and residual effects to be offset, including indirect disturbance; and<br />vii) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the final CHRP.(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 38 | <strong>Sowaqua Spotted Owl Mitigation Plan </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction of any Project component within the Sowaqua spotted owl wildlife habitat area</strong>, a Sowaqua Spotted Owl Mitigation Plan that includes:<br />a) a summary of results from supplemental surveys conducted in the Sowaqua spotted owl wildlife habitat area;<br />b) the area of habitat potentially directly and indirectly affected by the Project;<br />c) a description of how an avoidance, mitigation, and offset hierarchy was considered in the plan;<br />d) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable goals for evaluating mitigation success;<br />e) an evaluation of offset options within or outside of the Sowaqua spotted owl wildlife habitat area, an indication of the selected option, and the rationale for the selected option;<br />f) details on post-construction monitoring of mitigation measures and offset measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, any adjustments to the offset measures, and a proposed reporting schedule;<br />g) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />h) details on how the mitigation and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the mitigation plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the mitigation plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the mitigation plan.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 39 | <strong>Hydrogeological study at Coldwater Indian Reserve (IR) No. 1</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction between Veale Road and Kingsvale Pump Station</strong>, a hydrogeological report relating to the aquifer at Coldwater IR No. 1 in British Columbia. The report must:<br />a) describe the methodology and information sources used, including any field investigations;<br />b) delineate the extent of the aquifer in the area of Coldwater IR No. 1;<br />c) characterize the aquifer recharge sources and aquifer confinement;<br />d) characterize the direction and speed of groundwater movement to wells on Coldwater IR No. 1;<br />e) quantify the risks posed to groundwater supplies on Coldwater IR No. 1 in the event of leaks, accidents or malfunctions from the Project;<br />f) based on the assessment of risks, describe proposed measures to address identified risks, including but not limited to considerations related to routing, Project design, operational measures, or monitoring;<br />g) provide justification for the measures proposed to address identified potential risks to groundwater supplies on Coldwater IR No. 1; and<br />h) include a summary of consultations undertaken with the Coldwater First Nation and Appropriate Government Authorities, as well as copies of all written comments that may be provided to Trans Mountain by the Coldwater First Nation or Appropriate Government Authorities. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from the Coldwater First Nation or Appropriate Government Authorities, into the assessment.(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 40 | <strong>Rare Ecological Community and Rare Plant Population Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, an updated Rare Ecological Community and Rare Plant Population Management Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the Species at Risk Act, that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results, and a demonstration of the overall adequacy of the rare ecological community and rare plant surveys, including the adequacy for the identification of biophysical attributes for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act;<br />b) avoidance and mitigation measures to be implemented during construction and operations, including all relevant measures committed to throughout the OH-001-2014 proceeding and any new measures resulting from supplementary surveys, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />c) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />d) details on post-construction monitoring, including survey methods, the appropriate number of years of monitoring to determine the success of each type of avoidance and mitigation measure, corrective actions that might be necessary, and the circumstances under which each such action would be taken;<br />e) a Preliminary Rare Ecological Community and Rare Plant Population Offset Plan for any ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, and for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act, and that, after five years of operations, have ongoing effects. This preliminary plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a rationale for why the community, species, or critical habitat cannot be avoided by a sufficient distance to avoid both direct and indirect residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the expected residual effects on that community, species, or critical habitat, including a discussion of the potential for time lags &nbsp;between when Project effects occur and when mitigation measures would become fully functional, and taking into account the success on past projects of the proposed mitigation and corrective measures in b) and d) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the appropriateness of offsets for the community, species or critical habitat, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of how the avoidance, mitigation, monitoring, corrective and offset measures are consistent with any applicable recovery, action or management strategies or plans for the community, species or critical habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Rare Ecological Community and Rare Plant Population Management Plan, including confirmation that the avoidance, mitigation, monitoring, corrective, and offset measures in the Rare Ecological Community and Rare Plant Population Management Plan will be implemented to the extent feasible in the case of discovery via their inclusion in the Rare Ecological Communities or Rare Plant Species Discovery Contingency Plan.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 41 | <strong>Wetland Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Wetland Survey and Mitigation Plan for wetlands potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results and a demonstration of the overall adequacy of the wetland surveys;<br />b) a description of any wetlands for which ground-based surveys were not possible, an explanation as to why not, attempts made to obtain access, and what further information on each wetland will be collected immediately prior to or during construction;<br />c) a description of the functional condition of each wetland for comparison during post-construction monitoring, including individual functional conditions (e.g., habitat, hydrology and biogeochemistry, including the presence and abundance of migratory birds and species at risk), and a description of the methods used to determine the type and amount of each individual wetland function and the overall functional condition;<br />d) a description of the crossing methods, mitigation measures and reclamation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each such method and measure will be applied;<br />e) measurable goals against which the success of wetland mitigation and reclamation will be evaluated, including a description of how such goals incorporate the aim of returning wetlands to their original functionality while allowing for reasonable natural variation, and including measurable goals for each of the first-, third- and fifth-year post-construction monitoring reporting stages for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies;<br />f) a description of how the<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss of wetland function, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />g) details of the post-construction monitoring plan for wetlands for the first five years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Wetland Offset Plan for any wetland that has not achieved reclamation success in terms of overall wetland function after five years of operations, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition &ndash; this plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the expected residual effects on the wetland, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in d) and g) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the wetland, taking its specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios and indicator species, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, details with rationales on the offset measures that will be implemented before or during the first five years of operations to compensate for expected temporary or ongoing losses to individual functional conditions, including the amount and type of offsets required, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wetland Survey and Mitigation Plan.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 42 | <strong>Grasslands Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Grasslands Survey and Mitigation Plan for native grasslands in the B.C. interior that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of survey results for such grasslands, including but not limited to native plant species diversity, species at risk, the density and distribution of existing invasive plant species, and the presence of cryptogamic crust, together with a demonstration of the adequacy of such surveys and a summary of existing and ongoing land management impacts;<br />b) a description (including quantification) of overlap of the Project with grasslands and of expected residual effects;<br />c) a description of the mitigation and reclamation measures to be implemented for grasslands during construction and operations, including the extent to which native seed will be used, with rationales and unambiguous criteria explaining under what circumstances each such measure will be applied;<br />d) measurable goals against which the success of grassland mitigation and reclamation will be evaluated, including goals related to cryptogamic crust recovery, invasive species control, and access control, and how existing and ongoing land management impacts and land-use changes by landowners outside the control of Trans Mountain will be taken into account;<br />e) a description of how the:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy, and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss for grasslands, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />f) details of the post-construction monitoring plan for grasslands for the first ten years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />g) a Preliminary Grasslands Offset Plan for those grasslands that, after ten years of operations, have not achieved reclamation success. This plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) expected residual effects on the grasslands, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in c) and f) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the grasslands, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offsets measures will be monitored, assessed, and reported on, and problems corrected;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />i) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />j) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grasslands Survey and Mitigation Plan.(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 44 | <strong>Wildlife Species at Risk Mitigation and Habitat Restoration Plans&nbsp; </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction,</strong> Wildlife Species at Risk Mitigation and Habitat Restoration Plans for each species whose draft, candidate, proposed, or final critical habitat is directly or indirectly affected by the Project. Each plan must include:<br />a) a summary of supplementary pre-construction survey results, including surveys for biophysical attributes of critical habitat;<br />b) the location and type of critical habitat, for those wildlife species with early draft and candidate critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />c) the location, types and total spatial area for each type of critical habitat for those wildlife species with proposed or final critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />d) a detailed description of measures that will be used to avoid the destruction of critical habitat;<br />e) a detailed description of mitigation and habitat restoration measures to be implemented to reduce direct and indirect Project effects on critical habitat, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation and critical habitat restoration success;<br />f) identification and review of alternative mitigation and habitat restoration measures to avoid or lessen direct and indirect Project effects on critical habitat, and the rationale for the selected measure(s);<br />g) detailed description of how selected mitigation and critical habitat restoration measures address the potential for time lags between when the Project impacts occur and when mitigation and critical habitat restoration measures are implemented and are fully functional;<br />h) details on post-construction monitoring of mitigation measures and critical habitat restoration measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />i) details on how the mitigation, critical habitat restoration measures, and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />j) a commitment to include the results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />k) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plans including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />l) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowner/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />m) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wildlife Species at Risk Mitigation and Habitat Restoration Plans.(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 47 | <strong>Access Management Plan(s)</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, an Access Management Plan(s) to be included within the updated Environmental Protection Plans required by Conditions 72 and 78. Each plan must address issues related to soil, vegetation, fish and fish habitat, and wildlife and wildlife habitat. Each plan must also describe access control measures proposed to control both human and predator access during construction and operations, and include:<br />a) objectives of the plan;<br />b) measurable goals for evaluating the plan&rsquo;s success in achieving its objectives;<br />c) a summary of any related baseline information that has been or will be collected to aid in evaluating the plan&rsquo;s success, and justification of the adequacy of this baseline information, or a rationale if no baseline information has or will be collected;<br />d) a list of sites where access control measures will be implemented for construction and those that will remain in place throughout operations, the control measure(s) proposed at those sites, and the rationale for selecting those sites and measures;<br />e) the methods for monitoring the effectiveness of access control measures implemented during construction and operations, and justification of the adequacy of such monitoring;<br />f) a description of available adaptive management measures and of the criteria Trans Mountain will use to determine if and when adaptive management measures are warranted based on monitoring results;<br />g) a commitment to report, as part of Trans Mountain&rsquo;s post-construction environmental monitoring reports (required by Condition 151), on the control measures implemented, monitoring undertaken, and the success of control measures in meeting Access Management Plan goals and objectives, as well as a schedule, with rationale, for reporting throughout operations;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />i) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Plan/Report.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 48 | <strong>Navigation and navigation safety plan</strong><br />Trans Mountain must file with the NEB, <strong>for approval</strong>, <strong>at least 4 months prior to commencing construction</strong>, a Navigation and Navigation Safety Plan that includes:<br />a) an updated list of navigable waterways to be crossed by or affected by the Project (including power lines, marine terminal, temporary or permanent bridge crossings, or other ancillary works that are physically or operationally connected to the Project);<br />b) an updated listing of effects of the Project on navigation and navigation safety for each of the identified waterways identified in a);<br />c) proposed mitigation measures to address Project effects on navigation and navigation safety for each of the identified waterways, including adherence to codes and standards (such as the CSA); and<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and waterway users, regarding their navigational use of each of the identified waterways. In its summary, Trans Mountain must:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) describe the Appropriate Government Authorities, potentially affected Indigenous groups, and commercial and recreational waterway users consulted;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) describe how Trans Mountain identified those consulted; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 56 | <strong>Grizzly Bear Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction in each vulnerable grizzly bear population unit / grizzly bear management area</strong>, a Grizzly Bear Mitigation Plan for each of these areas. Trans Mountain must provide a rationale for why any vulnerable grizzly bear population units / grizzly bear management units potentially affected by the Project are not addressed in the plan. The Grizzly Bear Mitigation Plan(s) must include:<br />a) a summary of results from any supplemental surveys conducted;<br />b) potential direct and indirect effects of Project activities on vulnerable grizzly bear population units and grizzly bear management units;<br />c) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation success;<br />d) details on post-construction monitoring of mitigation measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />e) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan(s); and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grizzly Bear Mitigation Plan, including confirmation that the mitigation, monitoring, and corrective measures in this plan will be implemented in the case of discovery via their inclusion in Trans Mountain&rsquo;s Wildlife Species of Concern Discovery Contingency Plan.(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 59 | <strong>Worker accommodation strategy</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a worker accommodation strategy, developed in consultation with appropriate municipal or provincial authorities. The strategy must include:<br />a) a final summary of all proposed accommodations, including the location of any temporary camp(s);<br />b) the number of workers that will be housed; and<br />c) a description of how the strategy addresses any concerns or requests raised in consultation with municipal or provincial authorities.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the event that temporary camp(s) are to be used, the strategy must also include:<br />i) a description of how the potential environmental and socio-economic impacts have been assessed, and a description of all associated mitigation measures;<br />ii) copies of, or reference to, any mitigation or operational plans that will be required or implemented for the camp(s), including a description of how Trans Mountain has incorporated any additional mitigation measures into relevant Environmental Protection Plan(s);<br />iii) copies of any necessary municipal or provincial permits for any camp(s) that have been received 3 months prior to construction. &nbsp;If camp permits are not yet in place 3 months prior to commencing construction, provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a list of the outstanding camp permits and a schedule for when these camp permits will be in place; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) copies of any outstanding camp permits prior to commencing construction;<br />iv) copies or excerpts of all policies relating to the rules of conduct for workers housed at the camp(s);<br />v) confirmation that all policies relating to the camp(s) will be provided to workers;<br />vi) confirmation that all policies relating to the camp(s) were made available to all local communities and other relevant service providers in proximity to any camp(s) that will be used for the Project; and<br />vii) a summary of its consultations with affected landowners/tenants where any camp(s) will be located. Trans Mountain must provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a description of the information provided to landowners/tenants; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Strategy.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table and must:(a)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)(ii)) <div><strong>at least 30 days prior to commencing construction</strong>;</div>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)(b) and c)) b) post on its company website the same information required by a),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />c) maintain at each of its construction offices:<ul><li>i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;</li><li>ii) copies of any permits, authorizations, and approvals referenced in i); and</li><li>iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).</li></ul> | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 60 | <strong>Environmental and socio-economic assessment - s.58 temporary construction lands and infrastructure</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, an environmental and socio-economic assessment for all temporary construction lands and infrastructure approved pursuant to this Order. The assessments must include:<br />a) a list of the locations and dimensions of all temporary construction lands and infrastructure;<br />b) environmental alignment sheets or as-built drawings at an appropriate scale, clearly depicting temporary construction lands and infrastructure;<br />c) results of any pre-construction surveys within the areas that were not previously subject to such surveys, and an indication of potential residual effects;<br />d) all associated mitigation measures that are beyond those identified during the OH 001 2014 proceeding;<br />e) analysis supporting the use of the measures in d), including any supplementary reports;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information based on any supplemental surveys completed; and<br />g) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants, as well as copies of all written comments that may be provided to Trans Mountain by those consulted. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the assessment.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 61 | <strong>List of temporary infrastructure sites</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a complete list of all temporary infrastructure sites to be constructed for the Project, and must file any updates as they become available. This list must include information on each site&rsquo;s location, structures to be installed, the anticipated date for commencing construction, and activities involved in its construction. The initial list and any updates must also include the condition numbers (those under the &ldquo;prior to commencing construction&rdquo; phase heading) that are applicable to each site and an indication of whether each of those conditions has been or remains to be satisfied.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)&nbsp;(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 66 | <strong>Risk Management Plan for geohazards</strong><br />Trans Mountain must develop and file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, an updated Risk Management Plan for addressing the threats of existing and potential geohazards during construction of the Project.<br />This plan must be updated as additional site-specific geotechnical information is obtained through detailed investigations, and modified as geohazards are encountered during construction. Trans Mountain must make any updates or modifications available to the NEB upon request.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 7 | <strong>Environmental and socio-economic assessment - route re-alignments</strong><br />As applicable, Trans Mountain must file with the NEB for approval,&nbsp;<strong>concurrent with its filing of the Plan, Profile and Book of Reference pursuant to section 33 of the&nbsp;<em>National Energy Board Act</em></strong>, an environmental and socio-economic assessment for each proposed detailed route re-alignment that extends beyond the applied-for corridor width of Trans Mountain&rsquo;s preferred route in proximity to:<br />&bull; Ohamil Indian Reserve 1;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&bull; Tzeachten Indian Reserve 13; and<br />&bull; Surrey Bend Regional Park.<br />Any assessment must include:<br />a) environmental alignment sheets at an appropriate scale, clearly depicting the proposed route re-alignments;<br />b) results of any pre-construction surveys within the areas that were not previously subject to such surveys, and an indication of potential residual effects;<br />c) all associated mitigation measures that are beyond those identified during the OH-001-2014 proceeding;<br />d) analysis supporting the use of the measures in c), including any supplementary reports;<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information based on any supplemental surveys completed; and<br />f) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants, as well as copies of all written comments that may be provided to Trans Mountain by those consulted. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the assessment.<div>&nbsp;</div>(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)<br />&nbsp;(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7) | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 76 | <strong>Old Growth Management Areas Mitigation and Replacement Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction within old growth management areas</strong>, an Old Growth Management Areas Mitigation and Replacement Plan for these areas that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) avoidance and mitigation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />b) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />c) details on post-construction monitoring, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />d) the expected residual effects (including quantification) on old growth management areas, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional;<br />e) replacement or other offset measures that will be implemented to compensate for residual effects with the aim of no-net-loss to old growth forests within old growth management areas overall, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) discussion of the appropriateness of compensation for the old growth management area, taking its specific features into account, and of any potential limitations of the effectiveness of such replacement or offset measures;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an explanation with rationales on the amount and type of replacements or other offsets required;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a timeline for their implementation;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv)&nbsp; the selection of compensation sites;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) identification of the parties involved in planning and implementation and their respective roles and responsibilities, and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a description of the methods and schedule for monitoring and reporting to demonstrate compensation success;<br />f) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />g) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Old Growth Management Areas Mitigation and Replacement Plan.(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 77 | <strong>Archaeological and cultural heritage assessment &ndash; Lightning Rock </strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline between the Sumas Terminal and the Sumas Pump Station,</strong> a report on archaeological and cultural heritage field investigations undertaken to assess the potential impacts of Project construction and operations on the Lightning Rock site at Sumas, British Columbia. The report must include:<br />a) a detailed description of the assessment plan that was developed, in consultation with the St&oacute;:lo Collective, for the involvement of the St&oacute;:lo Collective in designing and undertaking surveys;<br />b) a description of the pre-construction archaeological and cultural heritage surveys conducted at the site, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) survey methodologies used; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) data and information sources, including information and Indigenous traditional knowledge provided by the St&oacute;:lo Collective;<br />c) a site description, including maps at appropriate scales and levels of detail, confirming the site boundaries;<br />d) an assessment of the potential environmental and socio-economic impacts of Project construction and operations on the archaeological resources and cultural heritage of the site;<br />e) all associated mitigation measures that are beyond those identified during the OH-001-2014 proceeding to address any identified impacts;<br />f) analysis supporting the use of the measures in e), including any additional relevant reports;<br />g) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) and Environmental Alignment Sheets to include any relevant information based on the surveys completed; and<br />h) a summary of consultations undertaken with the St&oacute;:lo Collective, and Appropriate Government Authorities, as well as copies of all written comments that may be provided to Trans Mountain by the St&oacute;:lo Collective or government authorities. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from the St&oacute;:lo Collective or government authorities, into the assessment.(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 92 | <strong>Updates under the <em>Species at Risk Act</em></strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a summary of any relevant updates under the <em>Species at Risk Act</em>, including new Schedule 1 listings and new or amended Recovery Strategies, Action Plans, and Management Plans for species that have the potential to be affected by the Project. For each species-specific update, the summary must include:<br />a) a discussion of the Project activities&rsquo; potential effects on the listed species or its critical habitat, including an explanation as to whether additional surveys are required to locate such critical habitat;&nbsp;<br />b) identification of all reasonable alternatives to the Project activities referred to in a), including avoidance measures, and a discussion on the potential effects of the alternatives, the chosen approach, and the rationale for selecting the chosen approach;<br />c) any additional site-specific mitigation;<br />d) any monitoring to be undertaken and a commitment to include monitoring results as part of the post-construction environmental monitoring reports filed under Condition 151;<br />e) an explanation as to how the responses to b), c) and d) above are consistent with applicable Recovery Strategies and Actions Plans; and<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the summary of updates, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-007-2016 | Authorization for temporary construction lands and infrastructure: • development of camp locations, stockpile sites, • contractor staging areas (i.e., co-located with camps or stockpile sites), • construction yards, borrow pits, and • access roads for the first 10 km of each pipeline spread (including temporary, clear-span bridges associated with these access roads) | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />c) the scope, methodology, and justification for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />d) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to the participating Indigenous group.<br />Trans Mountain must provide a copy of the report to each potentially affected group identified in b) above at the same time that it is filed with the NEB.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 100 | <strong>Heritage resources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction of individual Project components as described in Condition 10(a)</strong>:<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b); and<br />d) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c).(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 101 | <strong>Uninterruptible Power Supply (UPS) and battery systems</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction at each terminal and pump station</strong>, confirmation that the UPS system design and planned operation related to that facility, is in compliance with the requirements of CSA 22.1 &ndash; 15 or other applicable standard(s) that exceeds the requirements of CSA 22.1 &ndash; 15. If another standard is used, this filing must include the name of the standard and an explanation of why the standard was used and how it meets or exceeds the requirements of CSA 22.1 1 &ndash; 15.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)<br />&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 105 | <strong>Quality assurance verification</strong><br />Trans Mountain must file <strong>monthly summary reports, </strong><strong>from commencing </strong><strong>construction until after commencing operations, </strong>outlining non-conformances with its design, materials, and construction specifications and the disposition of these non-conformances.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br /><br />&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)<br />&nbsp;(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)<br />&nbsp;(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;<br />&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)<br />&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 111 | <strong>Joining Programs</strong><br />Trans Mountain must develop Joining Programs and file them with the NEB <strong>at least 45 days prior to commencing welding of, respectively</strong>:<br />a) field circumferential production, tie-in, and repair pipeline welds, including the tie-in welds between existing segments and Line 1 or Line 2; and<br />b) terminals and pump stations.<br />The Joining Programs must include:<br />i) welder qualification requirements;<br />ii) requirements for welding inspector qualifications and duties;<br />iii) welding procedure specifications;<br />iv) non-destructive examination () specifications;<br />v) procedure qualification records for welding procedure specifications and NDE specifications;<br />vi) a quality assurance program for field welds and welding procedures; and<br />vii) any additional information that supports the Joining Program.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 112 | <strong>Pressure testing</strong><br />a) Trans Mountain must pressure test the new and reactivated pipeline segments, terminals, and pump stations with a liquid medium.<br />b) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing</strong>, a Pressure Testing Program that demonstrates compliance with applicable codes, standards, and regulatory requirements.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)<br />&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 113 | <strong>Hydrostatic Testing Plan</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing of any Project component</strong>, a Hydrostatic Testing Plan for the Project that includes:<br />a) the locations of all water withdrawal and discharge sites;<br />b) a discussion of any clearing activities or any other associated works, if required, that will allow for the transportation of the hydrostatic test water;<br />c) water withdrawal rates;<br />d) water withdrawal volumes;<br />e) the flow rate/volume of water at the withdrawal sites; and<br />f) site-specific mitigation measures to be implemented at the water withdrawal and discharge sites or at any other locations required to allow for the transportation of hydrostatic test water, including a description of the water quality monitoring methods to be used on hydrostatic testing water prior to discharge; and<br />g) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 114 | <strong>NDE of final tie-in welds</strong><br />Trans Mountain must delay NDE of final tie-in welds (i.e.: welds which will not be subjected to hydrostatic testing) and any repairs to them <strong>for at least 48 hours following weld completion</strong>. Trans Mountain must include this requirement in the NDE specification of its Joining Program required by Condition 111.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 117 | <strong>Reporting on improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least</strong> <strong>2 years and 1 year prior to commencing operations</strong>, detailed updates for the company&rsquo;s review of its Emergency Management Program (toward meeting the requirements of Condition 124). This filing must include:<br />a) a summary of work undertaken to-date;<br />b) the approximate timing for completing remaining work; and<br />c) a summary of parties that were consulted (Condition 90) and how their comments and feedback were considered in improving the program.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 119 | <strong>Emergency Preparedness and Response Exercise and Training Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 1 year prior to commencing operations</strong>, an Emergency Preparedness and Response Exercise and Training Program for the pipeline; the Edmonton, Sumas, and Burnaby Terminals; and the Westridge Marine Terminal. The program&rsquo;s objective is to demonstrate the continual improvement of responder competencies (including control centre personnel) at all levels of the company to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type, including tank fires and earthquakes. The program must include the following:<br />a) a defined scope, other objectives in addition to those noted above, and program targets that address responder turn-over and ensure responders&rsquo; ongoing training and practice;<br />b) a list of mandatory courses for responders;<br />c) a discussion of how Trans Mountain will train its personnel to respond to all hydrocarbon spill scenarios in various seasons, including releases of hydrocarbons in mountain regions during winter conditions, into ice covered watercourses, into watercourses under varying flow conditions and into waterbodies (aquifers or streams)that are used as municipal water supply sources;<br />d) a description of, and schedule for, all emergency response exercises (full-scale, tabletop, drills, functional) that Trans Mountain will conduct prior to operations to test a variety of scenarios;<br />e) a plan, including rationales, for determining the schedule and frequency of all emergency response exercises (full-scale, tabletop, drills, functional) to test a variety of scenarios during the Project&rsquo;s operational life;<br />f) a discussion of how emergency response exercises will meet the objectives of testing Trans Mountain&rsquo;s:<br />i) emergency response procedures;<br />ii) company personnel training;<br />iii) communications systems;<br />iv) response equipment;<br />v) safety procedures; and<br />vi) the effectiveness of its liaison and continuing education programs;<br />g) a learnings implementation plan for exercises that considers how Trans Mountain will update and amend its Emergency Response Plans and related documents following exercises. The learnings implementation plan must consider three main purposes:<br />i) to validate plans;<br />ii) to develop Trans Mountain responder competencies (including control centre personnel) and provide them with the opportunity to carry out and understand their roles in emergency response; and<br />iii) to test Project-specific emergency response procedures;<br />h) a plan for addressing the training requirements contained within the <em>National Energy Board Onshore Pipeline Regulations</em>; and<br />i) confirmation that an independent third party has reviewed and assessed the Emergency Preparedness and Response Exercise and Training Program and that Trans Mountain has considered and incorporated the comments generated by that review and assessment into the program.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 120 | <strong>Notification and reporting on emergency response exercises</strong><br />For any tabletop, functional, and full-scale emergency response exercises undertaken as part of its Emergency Preparedness and Response Exercise and Training Program required by Condition 119:<br />a) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>at least 45 days prior to the date of each exercise</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />b) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after</strong> <strong>completing each</strong> <strong>full-scale exercise</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement; and<br />iii) steps to be taken to correct deficiencies.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 121 | <strong>Financial Assurances Plan &ndash; operations phase</strong><br />a) Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to applying for leave to open Line 2,</strong> a Financial Assurances Plan that includes details of the financial resources and secured sources of funds that will be necessary to pay, without limitation, all actual loss or damage, costs and expenses, including cleanup and remediation, and loss of non-use value relating to non-use of a public resource associated with an unintended or uncontrolled release from the Project during the operations phase.<a href=http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn1">[1]</a> These costs may arise from, among other things, potential accidents, malfunctions, and failures during the Project operations phase, including all spills originating from the pipeline and the terminals.<br />The Financial Assurances Plan must be signed by an officer of the company, verifying that it is accurate, complete, and, at a minimum, meets the criteria and coverage levels described below:<br />i) Criteria for financial assurance instruments and plan:<ol><li>Any letter of credit that forms part of the Financial Assurances Plan must be unconditional and irrevocable, segregated from Trans Mountain&#39;s day-to-day business activities, and be dedicated to providing funds to cover the costs described in sub a) above, without limitation.</li><li>Third party liability insurance must be current, and broad, respecting the scope of environmental damages covered by the policy; the policy will be consistent with provisions available in the insurance market(i.e., only exceptional/non-standard perils, taking into account the Project&#39;s nature and scope, would be excluded from coverage). Such insurance must be structured on a multi-year basis, recognizing potential loss of income by persons sustaining damage caused by Trans Mountain, over a reasonable number of years after the event.</li><li>A portion of cash reserves or a portion of future cash flows of the Project may be included as instruments in the Financial Assurances Plan, provided they are secured by a commitment letter from an officer of the company confirming that the funds will be dedicated to the Financial Assurances Plan without restrictions for the period specified by the officer.</li><li>Parental and other third party guarantors must be registered within a Canadian jurisdiction and must have financial strength that is demonstrated in balance sheet values and ratios and credit ratings. For example, total assets less total liabilities of the guarantor should be several multiples of the liability assumed in the Trans Mountain guarantee.</li></ol>ii) Financial assurance components and coverage levels:<br />Trans Mountain&#39;s Financial Assurances Plan must provide a total coverage, for the Project as a whole, of $1.1 billion<a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn2">[2]</a> for the costs described in sub a) above, without limitation. The plan should include the following components and minimum coverage levels:<ol><li>Ready cash: Trans Mountain must have unfettered access to at least $100 million to cover costs, including compensation to third parties for losses and damages in the near term, while insurance claims are being processed. Once used, this source of cash must be replenished immediately to cover the costs of a potential future spill. This can be in the form of a letter of credit, surety bond or other form acceptable to the NEB.</li><li>Core coverage: Trans Mountain must put in effect and maintain current at all times a core financial coverage of at least $1 billion that includes third party liability insurance and other financial assurance instruments that comply with the criteria. Core coverage must be a portfolio approach with multiple financial instruments used and may not be composed of a single financial instrument (e.g., only third party liability insurance). At least one component of core coverage must be funds that are readily accessible to Trans Mountain (e.g., cash reserves held by the general partner and not distributed to the limited partners).<br />Trans Mountain may use a number of financial and insurance instruments in its Financial Assurances Plan. However, sales of Project assets used for transporting hydrocarbon commodities will not be eligible candidates.&nbsp; Below are some illustrative financial and insurance instruments that could be potential candidates for the Financial Assurances Plan:</li></ol><ul><li>Irrevocable, unfettered letter of credit.</li><li>Secured line of credit.</li><li>Cash reserves held by the general partner and not distributed to the limited partners (and verifiable on Trans Mountain Pipelines Limited Partnership&#39;s balance sheet).</li><li>Internal cash flow, committed by Trans Mountain to financial assurances.</li><li>Industry pooled fund.</li><li>Third party liability insurance with exclusions for only exceptional/non-standard perils.</li><li>No fault third party liability insurance.</li><li>Parental and other third party guarantees provided by parties demonstrating financial strength through balance sheets and credit ratings.</li><li>Other instruments developed by Trans Mountain and the insurance and financial markets.</li></ul>b) Trans Mountain must file the following with the NEB:<br />i) <strong>At least 6 months prior to applying for leave to open Line 2</strong>, a report from an independent third party that has assessed the Financial Assurances Plan and its key components against the criteria and actual experiences of industry damage claims. The report must summarize the key features of each financial and insurance instrument proposed for inclusion in the Financial Assurances Plan.<br />ii) <strong>At least 3 months prior to applying for leave to open Line 2</strong>, a supplement to the report described in b)i) that provides verification of any third party liability insurance coverage, a copy of the insurance certificate, and a summary of the insurance policy&#39;s key features. This summary must include: limits on insurance coverage, deductible amounts, the risks and perils and properties covered by the insurance policy, the exclusions from coverage, Trans Mountain&#39;s obligations, effective dates, and names of insurers and reinsurers.<br />iii) <strong>With its first leave to open application for Line 2</strong>, a report describing the steps it took to eliminate any deficiencies in its Financial Assurances Plan that were identified in the independent third party report referenced in b)i) and the NEB&#39;s subsequent review.<br />iv) <strong>On or before 31 January of each year after commencing operations</strong>, a letter signed by an officer of the company verifying that all components of the Financial Assurances Plan remain as the NEB approved and sufficient to meet the financial assurance coverage levels described in ii).<br />v) <strong>At least 2 months prior to any intended change(s) to the Financial Assurances Plan during the Projects operations phase</strong>, a letter, for approval, detailing the intended change(s) and how the change(s) provides the same or greater level of protection.<br />vi) <strong>Within 30 days after accessing any component of the Financial Assurances Plan</strong>, a report detailing the component accessed, the reason for accessing it, and Trans Mountain&rsquo;s plan to ensure that it continues to meet the requirements of its NEB-approved Financial Assurances Plan.<br />&nbsp;<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref1">[1]</a> &nbsp;&nbsp;&nbsp; In the context of this condition, &ldquo;operations phase&rdquo; refers to the period after the Project receives leave to open approval and prior to it being fully abandoned.<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref2">[2]</a> &nbsp;&nbsp;&nbsp; The NEB&rsquo;s basis for any final coverage level is described in its report to Governor in Council." | In Progress | During Construction Phase | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 124 | <strong>Implementing improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing operations</strong>, a detailed summary of its review of its Emergency Response Plans (as noted in Conditions 125 and 126) and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing <a href=https://docs.neb-one.gc.ca/ll-eng/llisapi.dll/fetch/2000/90464/90552/548311/956726/2392873/2451003/2393783/B18-1_-_V7_1.0_TO_5.2.8.3_RISK_ASSESS_MGMT_SPILLS_-_A3S4V5.pdf?nodeid=2393784&amp;vernum=-2">A3S4V5</a>). This filing must include a description of changes made to Trans Mountain&rsquo;s Emergency Management Program, as required under the <em>National Energy Board Onshore Pipeline Regulations</em>, including changes to:<br />a) the Pipeline Emergency Response Plan;<br />b) Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals, as well as the Westridge Marine Terminal; and<br />c) site-specific plans and documents related to a) and b), such as Geographic Response Plans, Geographical Response Strategies, control point mapping, tactical plans for submerged and sunken oil and tactical plans for high consequence areas.<br />The summary must demonstrate Trans Mountain&rsquo;s ability to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type and in any geographic region or season and must include the following:<br />i) a discussion of how the updated plans conform to the requirements contained within the <em>National Energy Board Onshore Pipeline Regulations</em>;<br />ii) a discussion of how the plans consider, and would allow coordination with relevant federal, provincial, municipal and Indigenous community emergency response plans;<br />iii) a discussion of how the results of research initiatives, such as the Scientific Advisory Committee work noted in Trans Mountain&rsquo;s response to NEB Information Request No. 1.63 (Filing <a href="https://docs.neb-one.gc.ca/ll-eng/llisapi.dll/fetch/2000/90464/90552/548311/956726/2392873/2451003/2454322/B32-2_-_Trans_Mountain_Response_to_NEB_IR_No._1_1_of_2_-_A3W9H8.pdf?nodeid=2456419&amp;vernum=-2">A3W9H8</a>) and other research noted during the OH-001-2014 proceeding, have been considered and incorporated into Trans Mountain&rsquo;s emergency response planning;<br />iv) a description of the models used in response planning, including oil trajectory, fate and behavior, and air dispersion models; and<br />v) confirmation that an independent third party has reviewed and assessed the Emergency Response Plans and that Trans Mountain has considered and incorporated the comments generated by the review and assessment into the plans.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)" | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 125 | <strong>Emergency Response Plans for the Pipeline and for the Edmonton, Sumas and Burnaby Terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least&nbsp; 6 months prior to commencing operations</strong>, updated Emergency Response Plans which must include:<br />a) the following relevant emergency preparedness and response documents:<br />i) an Emergency Response Plan to include the pipeline expansion;<br />ii) updated Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals; and<br />iii) all related and accompanying site-specific plans and documents, such as control point mapping, Geographic Response Plans, tactical response plans, volunteer management plans, and fire safety plans;<br />b) an emergency response and preparedness table for the pipeline (including facilities) indicating which plans and documents referenced in a) will be referred to in an emergency response for each 10-kilometre-long pipeline segment. For each pipeline segment, the table must also identify, at a minimum:<br />i) high consequence areas, including environmentally sensitive areas (e.g. wetlands), heritage sites and water supply wells (Condition 93);<br />ii) potentially affected persons or groups;<br />iii) available access to the right-of-way and high consequence areas;<br />iv) nearest control point(s);<br />v) nearest available equipment cache(s);<br />vi) response times for deployment of equipment and Trans Mountain personnel, mutual aid personnel, and third party contractors;<br />vii) the available equipment and trained personnel, whether employed by Trans Mountain, contracted, or available through mutual aid (including contact information); and<br />viii) geological, meteorological, and geographical hazards (e.g., snow avalanche, mud slides, rock slides, and steep slopes); and<br />c) maps depicting the information identified in b).(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 128 | <strong>Offset Measures Plan for residual effects on caribou habitat</strong><br />Trans Mountain must file with the NEB for approval, in accordance with the timelines below, an Offset Measures Plan for each affected caribou range, the goal of which is to offset all unavoidable and residual direct and indirect Project-related effects on caribou habitat, after taking into account the implementation of the measures identified in the relevant Environmental Protection Plan(s) for the Project and the Caribou Habitat Restoration Plan (see Condition&nbsp;37) measures. The Offset Measures Plan must include:<br />a) A preliminary version, to be filed <strong>at least 3 months prior to applying for leave to open</strong>, with the plan&rsquo;s criteria and measurable goals and that includes:<br />i) an initial quantification of the area of caribou habitat directly and indirectly disturbed by the Project;<br />ii) a list of the potential on-the-ground offset measures available;<br />iii) each potential offset measure&rsquo;s appropriate offset ratio, based on consultation with expert federal and provincial authorities and on a review of the scientific literature on conservation offsets;<br />iv) each potential offset measure&rsquo;s expected effectiveness including a discussion of uncertainty and how measures align with criteria specified in the scientific literature specific to conservation offsets;<br />v) each potential offset measure&rsquo;s relative qualitative and quantitative value toward achieving the offset; and<br />vi) a conceptual decision-making tree(s) or decision framework(s) that will be used to select which specific potential offset measures and accompanying offset ratios will be used under what circumstances.<br />b) A final version, to be filed <strong>on or before 31 January after the second complete growing season after completing final clean-up</strong>, including:<br />i) the contents of the preliminary Offset Measures Plan, with any updates identified in a revision log that includes the rationale for any changes;<br />ii) a tabular list of the potential offset measures and appropriate offset ratios to be implemented or already underway, including site-specific details and maps showing the locations, and an explanation of how they meet criteria in the scientific literature for offsets;<br />iii) a description of factors considered when determining the location of offset measures, including consideration of how the measures could maximize benefits to landscape variables;<br />iv) a schedule indicating when potential offset measures will be initiated and their estimated completion dates;<br />v)either an assessment of the predicted offset measures&rsquo; effectiveness including a discussion of uncertainty and a quantitative compilation showing how the measures would offset the previously determined residual effects, or a plan for completing an assessment of the potential offset measures&rsquo; effectiveness and value; and<br />vi) an update on the restoration success to support offset measure decisions.<br />Both the preliminary and final versions of the plan must also include the following:<ol><li>a summary of its consultations with Appropriate Government Authorities and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Offset Measures Plan;</li><li>a description of how Trans Mountain has taken any available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and</li><li>evidence of Trans Mountain&rsquo;s consideration of any updates to the applicable Recovery Strategy, as well as to range boundaries and identified critical habitat made prior and up to the date on which leave to open is granted.</li></ol>(a)) a)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(b)) b)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)<br />&nbsp;(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 130 | <strong>Groundwater Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing operations</strong>, a Groundwater Monitoring Program that pertains to all terminals and pump stations, and for any vulnerable aquifers along the pipeline route. The&nbsp; program must include, at a minimum:<br />a) locations of groundwater monitoring wells, their depths, the rationales for well locations (including how groundwater flow direction was considered), groundwater flow velocity, parameters to be monitored and frequency of monitoring;<br />b) a description of any program changes required to meet this condition for facilities with an existing Groundwater Monitoring Program;<br />c) methods, criteria and rationale for identifying vulnerable aquifers along the pipeline route;<br />d) applicable regulatory criteria for comparing monitoring results, and a process outlining what steps will be followed should monitoring results indicate a negative change in groundwater quality;and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the program.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;<br />&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 140 | <strong>Post-construction greenhouse gas (GHG) assessment report</strong><br />Trans Mountain must file with the NEB for approval, <strong>within</strong> <strong>2 months after commencing operations</strong>, an updated GHG assessment report specific to the Project. The report must include:<br />a) the methodology used for the assessment, including the sources of GHG emissions, assumptions, and methods of estimation;<br />b) the total direct GHG emissions generated from Project construction, including land-clearing;<br />c) a breakdown of direct GHG emissions generated by the construction of individual Project components (pipeline, pump stations, tank terminals and Westridge Marine Terminal) and by land-clearing activities; and<br />d) a comparison and discussion of the direct GHG emissions calculated in b) with the predicted emissions in Trans Mountain&rsquo;s application and subsequent submissions.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 142 | <strong>GHG Emissions Offset Plan &ndash; Project construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>within 4 months after commencing operations</strong>, a plan for providing offsets for all direct GHG emissions generated from Project construction, as determined in Condition 140. The plan must include:<br />a) a list and discussion of all possible offset options considered;<br />b) the criteria against which each option was assessed for viability;<br />c) a description of the offset option(s) selected for direct GHG emissions generated from Project construction, and the rationale for selecting the option(s);<br />d) confirmation that the selected offset option is registered under the approved quantification protocols and has been verified by an accredited &ldquo;verification body&rdquo; ;<br />e) a schedule indicating when the selected offset options(s) will be initiated; and<br />f) an accounting of offsets confirming no net GHG emissions from Project construction.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 146 | <strong>Reports on engagement with Indigenous groups &ndash; operations</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations,</strong> a report on the engagement activities it has undertaken with Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;<br />b)&nbsp; the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 147 | <strong>Natural hazard assessment</strong><br />Trans Mountain must file with the NEB, <strong>within 1 year after commencing operations</strong>:<br />a) the results of the baseline natural hazard assessment for the Project; and<br />b) confirmation that the natural hazard assessment will be:<br />i) updated at intervals not exceeding 5 years; and<br />ii) integrated into the existing Natural Hazard Management Program for the Trans Mountain Pipeline system.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<p style=margin: 2pt 0in; tab-stops: right 232.2pt;">&nbsp;</p><font color="#000000" face="Times New Roman" size="3"> </font>(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)" | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 149 | <strong>Caribou Habitat Restoration and Offset Measures Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the first complete growing season after commencing operations</strong>, a program for monitoring and verifying the effectiveness of caribou habitat restoration and offset measures implemented as part of the final Caribou Habitat Restoration Plan (Condition 37) and the final Offset Measures Plan (Condition 128). This program must include:<br />a) the scientific methods or protocols for short- and long-term monitoring of the restoration and offset measures, and effectiveness of the measures;<br />b) monitoring frequency, timing, and locations, and the rationale for each;<br />c) protocols for how restoration and offset measures will be adapted, as required, based on the monitoring results from the program&rsquo;s implementation;<br />d) a summary of Trans Mountain&rsquo;s consultation with Appropriate Government Authorities and any species experts on the design of the monitoring program; and<br />e) a proposed schedule for filing reports on monitoring results and adaptive management measures to the NEB, Environment and Climate Change Canada, and appropriate provincial authorities to be contained in the Caribou Habitat Restoration and Offset Measures Monitoring Program as well as at the beginning of each report filed.(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 150 | <strong>Caribou habitat restoration and offset measures monitoring report(s)</strong><br />Trans Mountain must file with the NEB, <strong>based on the approved schedule for the Caribou Habitat Restoration and Offset Measures Monitoring Program </strong>(required by Condition 149), a report(s) outlining the monitoring program&rsquo;s results, including the observed effectiveness of habitat restoration and offset measures for each affected caribou range, and how those measures will be adapted, as required, based on monitoring results. Any proposed changes to the NEB-approved reporting schedule must be included within the relevant report prior to any reporting on a revised schedule.(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up, </strong>a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants.<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />i) an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />ii) a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />iii) an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 155 | <strong>Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the <em>Species at Risk Act</em>, that includes:<br />a) an evaluation of avoidance and mitigation success with reference to the measurable goals outlined in the Rare Ecological Community and Rare Plant Population Management Plan required by Condition 40;<br />b) identification of communities, species, and critical habitats that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />c) identification of any ongoing effects to ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, or on any early draft, candidate, proposed, or final critical habitat under the <em>Species at Risk Act</em>;<br />d) for the ongoing effects identified in c), a Final Rare Ecological Community and Rare Plant Population Offset Plan that updates the Preliminary Rare Ecological Community and Rare Plant Population Offset Plan required by Condition 40, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 156 | <strong>Wetland Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Wetland Reclamation Evaluation Report and Offset Plan that includes:<br />a) the extent (in hectares), by wetland type, that was impacted by Project construction and associated activities;<br />b) for each wetland impacted, an evaluation of mitigation and reclamation success with reference to the measurable goals outlined in the Wetland Survey and Mitigation Plan required by Condition 41;<br />c) identification of any wetlands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, an evaluation of any temporary or ongoing loss of any individual functional condition (e.g., habitat, hydrology and biogeochemistry);<br />e) for any wetland that has not achieved reclamation success in terms of overall wetland function, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition, a Final Wetland Offset Plan that updates the Preliminary Wetland Offset Plan required by Condition 41, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 157 | <strong>Grasslands Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the tenth complete growing season after completing final clean-up</strong>, a Grasslands Reclamation Evaluation Report and Offset Plan that applies to native grasslands in the British Columbia interior and that includes:<br />a) the extent (in hectares) of grasslands that were impacted by Project construction and associated activities;<br />b) an evaluation of reclamation success with reference to the measurable goals outlined in the Grasslands Survey and Mitigation Plan required by Condition 42;<br />c) an identification of any grasslands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for those grasslands that have not yet achieved reclamation success, a Final Grasslands Offset Plan that updates the preliminary plan required by Condition 42, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | ?<strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station) ) For filings associated with Phase 14 (Blue River Pump Station)&nbsp;(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 30 | <strong>Power system protection for pump stations and terminals</strong><br />Trans Mountain must file with the NEB the following details of its electrical power system design for each pump station and each of the following: Westridge Marine Terminal, Burnaby Terminal, Edmonton Terminal, and Sumas Terminal:(a)) Descriptions of the overcurrent and ground fault protection schemes including:(i)) a summary of coordination studies between the upstream and downstream protective devices, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(ii)) relay settings and time-current curves, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(iii)) the specification of neutral grounding resistors, <strong>at least 6 months prior to commencing construction</strong>;(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(iv)) specifications of contactors, fuses, and circuit breakers, <strong>at least 6 months prior to commencing construction</strong>; and(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(v)) a description of other electrical protections, relay settings, and trip characteristics, <strong>at least 3 months prior to commencing dry commissioning</strong>.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(b)) Consistent with the NEB&rsquo;s Safety Advisory SA-2015-03, dated 4 May 2015, <strong>at least 6 months prior to commencing construction</strong>, information confirming that Trans Mountain has performed the ground fault and arcing fault protection designs for each pump station and terminal, including:<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />i) a means to clear ground faults without intentional time delay if the fault currents exceed the design limit set by the neutral grounding resistance; and<br />ii) a means to block the stored energy from other running motors from feeding an electrical fault in another motor running from the same bus.<br />&nbsp;<br />This filing must include a description of the ground fault and arcing fault protection designs including the above measures.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)<br />&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)<br />&nbsp;(c)) <strong>At least 6 months prior to commencing construction</strong>, either:&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;&nbsp;<br />i) a written confirmation that Trans Mountain determined during detailed design that electrical faults will not exceed their design limits and migrate to an arcing fault; or<br />ii) for a station or a terminal for which Trans Mountain determined during detailed design that an electrical fault could exceed its design limit and migrate to an arcing fault, the electrical configuration of that station or terminal and the additional equipment and devices that will be used to mitigate the adverse effects of such arcing faults.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)<br />&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)<br />&nbsp;(d)) Single-line diagrams of the electrical power systems<strong>, at least 6 months prior to commencing construction.</strong>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)<br />&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)<br />&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 36 | <strong>Pre-construction caribou habitat assessment</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range</strong>, a detailed caribou habitat assessment of the Project right-of-way through each caribou range traversed by the Project, including a 500 metre buffer on either side. The framework of the habitat assessment must use the updated critical habitat polygons delineated by the Southern Mountain Caribou Recovery Team and components of critical habitat outlined in the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014). The habitat assessment must include:<br />a) map(s) indicating the location of the habitat;<br />b) a description of the amount of habitat and the existing habitat alteration, in hectares;<br />c) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge into consideration into the assessment including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />d) a description of how Trans Mountain has incorporated input from Appropriate Government Authorities and species experts into the assessment methodology; and<br />e) a description of the type of habitat characterized by the biophysical attributes of critical habitat, as defined in the applicable Recovery Strategy.(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 37 | Trans Mountain must file with the NEB for approval, in accordance with the timelines below, preliminary and final versions of a CHRP for each caribou range potentially affected by the Project.(a)) <strong>Preliminary CHRP </strong>&ndash; to be filed <strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range. </strong>This version of the CHRP must include the following:<br />i) the CHRP&rsquo;s goals and measureable targets for each caribou range, including the goal of avoidance of critical habitat destruction;<br />ii) a detailed description of measures that will be used to avoid or lessen Project activities that impact critical habitat, and the rationale for selecting the measures;<br />iii) a list of criteria used to identify potential caribou habitat restoration sites;<br />iv) conceptual decision-making tree(s) or decision framework(s) that will be used to identify and prioritize potential caribou habitat restoration sites, and mitigative actions to be used at different types of sites, including consideration of typical site factors that may constrain implementation;<br />v) a literature review upon which the decision-making tree(s) or decision framework(s) are based, including:<br />1) an identification of applicable temporal and spatial caribou habitat restoration methodologies;<br />2) an assessment of the relative effectiveness of the identified methodologies; and<br />3) a detailed methodology of how the literature review was conducted.<br />vi) the quantifiable targets and performance measures that will be used to evaluate the extent of predicted residual effects, CHRP effectiveness, the extent to which the goals and measurable targets have been met, and the need for further measures to offset unavoidable and residual effects on caribou habitat;<br />vii) a schedule indicating when mitigation measures will be initiated and their estimated completion dates;<br />viii) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge studies into consideration in identifying potential caribou habitat restoration sites including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />ix) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the preliminary CHRP.(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(b)) <strong>Final CHRP </strong>&ndash; to be filed <strong>on or before 1 November after the first complete growing season after completing final clean-up.</strong> This version of the CHRP must include the following:<br />i) the preliminary CHRP, with any updates identified in a revision log that includes the rationale for any changes to decision-making criteria;<br />ii) a complete tabular list of caribou habitat restoration sites, including locations, spatial areas, habitat quality descriptions, site-specific restoration activities, and challenges;<br />iii) a description of how selected restoration measures are consistent with the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014);<br />iv) maps or updated Environmental Alignment Sheets showing the site locations;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />v) specification drawings for the implementation of each restoration method;<br />vi) a qualitative and quantitative and assessment of the total area of direct and indirect disturbance to caribou habitat that will be restored, the duration of spatial disturbance, and the area-based extent of the resulting unavoidable and residual effects to be offset, including indirect disturbance; and<br />vii) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the final CHRP.<br />&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 38 | <strong>Sowaqua Spotted Owl Mitigation Plan </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction of any Project component within the Sowaqua spotted owl wildlife habitat area</strong>, a Sowaqua Spotted Owl Mitigation Plan that includes:<br />a) a summary of results from supplemental surveys conducted in the Sowaqua spotted owl wildlife habitat area;<br />b) the area of habitat potentially directly and indirectly affected by the Project;<br />c) a description of how an avoidance, mitigation, and offset hierarchy was considered in the plan;<br />d) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable goals for evaluating mitigation success;<br />e) an evaluation of offset options within or outside of the Sowaqua spotted owl wildlife habitat area, an indication of the selected option, and the rationale for the selected option;<br />f) details on post-construction monitoring of mitigation measures and offset measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, any adjustments to the offset measures, and a proposed reporting schedule;<br />g) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />h) details on how the mitigation and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the mitigation plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the mitigation plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the mitigation plan.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 39 | <strong>Hydrogeological study at Coldwater Indian Reserve (IR) No. 1</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction between Veale Road and Kingsvale Pump Station</strong>, a hydrogeological report relating to the aquifer at Coldwater IR No. 1 in British Columbia. The report must:<br />a) describe the methodology and information sources used, including any field investigations;<br />b) delineate the extent of the aquifer in the area of Coldwater IR No. 1;<br />c) characterize the aquifer recharge sources and aquifer confinement;<br />d) characterize the direction and speed of groundwater movement to wells on Coldwater IR No. 1;<br />e) quantify the risks posed to groundwater supplies on Coldwater IR No. 1 in the event of leaks, accidents or malfunctions from the Project;<br />f) based on the assessment of risks, describe proposed measures to address identified risks, including but not limited to considerations related to routing, Project design, operational measures, or monitoring;<br />g) provide justification for the measures proposed to address identified potential risks to groundwater supplies on Coldwater IR No. 1; and<br />h) include a summary of consultations undertaken with the Coldwater First Nation and Appropriate Government Authorities, as well as copies of all written comments that may be provided to Trans Mountain by the Coldwater First Nation or Appropriate Government Authorities. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from the Coldwater First Nation or Appropriate Government Authorities, into the assessment.(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 40 | <strong>Rare Ecological Community and Rare Plant Population Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, an updated Rare Ecological Community and Rare Plant Population Management Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the Species at Risk Act, that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results, and a demonstration of the overall adequacy of the rare ecological community and rare plant surveys, including the adequacy for the identification of biophysical attributes for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act;<br />b) avoidance and mitigation measures to be implemented during construction and operations, including all relevant measures committed to throughout the OH-001-2014 proceeding and any new measures resulting from supplementary surveys, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />c) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />d) details on post-construction monitoring, including survey methods, the appropriate number of years of monitoring to determine the success of each type of avoidance and mitigation measure, corrective actions that might be necessary, and the circumstances under which each such action would be taken;<br />e) a Preliminary Rare Ecological Community and Rare Plant Population Offset Plan for any ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, and for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act, and that, after five years of operations, have ongoing effects. This preliminary plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a rationale for why the community, species, or critical habitat cannot be avoided by a sufficient distance to avoid both direct and indirect residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the expected residual effects on that community, species, or critical habitat, including a discussion of the potential for time lags &nbsp;between when Project effects occur and when mitigation measures would become fully functional, and taking into account the success on past projects of the proposed mitigation and corrective measures in b) and d) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the appropriateness of offsets for the community, species or critical habitat, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of how the avoidance, mitigation, monitoring, corrective and offset measures are consistent with any applicable recovery, action or management strategies or plans for the community, species or critical habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Rare Ecological Community and Rare Plant Population Management Plan, including confirmation that the avoidance, mitigation, monitoring, corrective, and offset measures in the Rare Ecological Community and Rare Plant Population Management Plan will be implemented to the extent feasible in the case of discovery via their inclusion in the Rare Ecological Communities or Rare Plant Species Discovery Contingency Plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 41 | <strong>Wetland Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Wetland Survey and Mitigation Plan for wetlands potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results and a demonstration of the overall adequacy of the wetland surveys;<br />b) a description of any wetlands for which ground-based surveys were not possible, an explanation as to why not, attempts made to obtain access, and what further information on each wetland will be collected immediately prior to or during construction;<br />c) a description of the functional condition of each wetland for comparison during post-construction monitoring, including individual functional conditions (e.g., habitat, hydrology and biogeochemistry, including the presence and abundance of migratory birds and species at risk), and a description of the methods used to determine the type and amount of each individual wetland function and the overall functional condition;<br />d) a description of the crossing methods, mitigation measures and reclamation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each such method and measure will be applied;<br />e) measurable goals against which the success of wetland mitigation and reclamation will be evaluated, including a description of how such goals incorporate the aim of returning wetlands to their original functionality while allowing for reasonable natural variation, and including measurable goals for each of the first-, third- and fifth-year post-construction monitoring reporting stages for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies;<br />f) a description of how the<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss of wetland function, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />g) details of the post-construction monitoring plan for wetlands for the first five years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Wetland Offset Plan for any wetland that has not achieved reclamation success in terms of overall wetland function after five years of operations, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition &ndash; this plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the expected residual effects on the wetland, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in d) and g) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the wetland, taking its specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios and indicator species, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, details with rationales on the offset measures that will be implemented before or during the first five years of operations to compensate for expected temporary or ongoing losses to individual functional conditions, including the amount and type of offsets required, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wetland Survey and Mitigation Plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 42 | <strong>Grasslands Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 5 months prior to commencing construction</strong>, a pre-construction Grasslands Survey and Mitigation Plan for native grasslands in the B.C. interior that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of survey results for such grasslands, including but not limited to native plant species diversity, species at risk, the density and distribution of existing invasive plant species, and the presence of cryptogamic crust, together with a demonstration of the adequacy of such surveys and a summary of existing and ongoing land management impacts;<br />b) a description (including quantification) of overlap of the Project with grasslands and of expected residual effects;<br />c) a description of the mitigation and reclamation measures to be implemented for grasslands during construction and operations, including the extent to which native seed will be used, with rationales and unambiguous criteria explaining under what circumstances each such measure will be applied;<br />d) measurable goals against which the success of grassland mitigation and reclamation will be evaluated, including goals related to cryptogamic crust recovery, invasive species control, and access control, and how existing and ongoing land management impacts and land-use changes by landowners outside the control of Trans Mountain will be taken into account;<br />e) a description of how the:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy, and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss for grasslands, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />f) details of the post-construction monitoring plan for grasslands for the first ten years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />g) a Preliminary Grasslands Offset Plan for those grasslands that, after ten years of operations, have not achieved reclamation success. This plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) expected residual effects on the grasslands, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in c) and f) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the grasslands, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offsets measures will be monitored, assessed, and reported on, and problems corrected;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />i) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />j) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grasslands Survey and Mitigation Plan.(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 44 | <strong>Wildlife Species at Risk Mitigation and Habitat Restoration Plans&nbsp; </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction,</strong> Wildlife Species at Risk Mitigation and Habitat Restoration Plans for each species whose draft, candidate, proposed, or final critical habitat is directly or indirectly affected by the Project. Each plan must include:<br />a) a summary of supplementary pre-construction survey results, including surveys for biophysical attributes of critical habitat;<br />b) the location and type of critical habitat, for those wildlife species with early draft and candidate critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />c) the location, types and total spatial area for each type of critical habitat for those wildlife species with proposed or final critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />d) a detailed description of measures that will be used to avoid the destruction of critical habitat;<br />e) a detailed description of mitigation and habitat restoration measures to be implemented to reduce direct and indirect Project effects on critical habitat, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation and critical habitat restoration success;<br />f) identification and review of alternative mitigation and habitat restoration measures to avoid or lessen direct and indirect Project effects on critical habitat, and the rationale for the selected measure(s);<br />g) detailed description of how selected mitigation and critical habitat restoration measures address the potential for time lags between when the Project impacts occur and when mitigation and critical habitat restoration measures are implemented and are fully functional;<br />h) details on post-construction monitoring of mitigation measures and critical habitat restoration measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />i) details on how the mitigation, critical habitat restoration measures, and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />j) a commitment to include the results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />k) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plans including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />l) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowner/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />m) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wildlife Species at Risk Mitigation and Habitat Restoration Plans.(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)<br />&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)<br />&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)<br />&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)<br />&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 47 | <strong>Access Management Plan(s)</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, an Access Management Plan(s) to be included within the updated Environmental Protection Plans required by Conditions 72 and 78. Each plan must address issues related to soil, vegetation, fish and fish habitat, and wildlife and wildlife habitat. Each plan must also describe access control measures proposed to control both human and predator access during construction and operations, and include:<br />a) objectives of the plan;<br />b) measurable goals for evaluating the plan&rsquo;s success in achieving its objectives;<br />c) a summary of any related baseline information that has been or will be collected to aid in evaluating the plan&rsquo;s success, and justification of the adequacy of this baseline information, or a rationale if no baseline information has or will be collected;<br />d) a list of sites where access control measures will be implemented for construction and those that will remain in place throughout operations, the control measure(s) proposed at those sites, and the rationale for selecting those sites and measures;<br />e) the methods for monitoring the effectiveness of access control measures implemented during construction and operations, and justification of the adequacy of such monitoring;<br />f) a description of available adaptive management measures and of the criteria Trans Mountain will use to determine if and when adaptive management measures are warranted based on monitoring results;<br />g) a commitment to report, as part of Trans Mountain&rsquo;s post-construction environmental monitoring reports (required by Condition 151), on the control measures implemented, monitoring undertaken, and the success of control measures in meeting Access Management Plan goals and objectives, as well as a schedule, with rationale, for reporting throughout operations;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />i) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Plan/Report.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)&nbsp; &nbsp; &nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 48 | <strong>Navigation and navigation safety plan</strong><br />Trans Mountain must file with the NEB, <strong>for approval</strong>, <strong>at least 4 months prior to commencing construction</strong>, a Navigation and Navigation Safety Plan that includes:<br />a) an updated list of navigable waterways to be crossed by or affected by the Project (including power lines, marine terminal, temporary or permanent bridge crossings, or other ancillary works that are physically or operationally connected to the Project);<br />b) an updated listing of effects of the Project on navigation and navigation safety for each of the identified waterways identified in a);<br />c) proposed mitigation measures to address Project effects on navigation and navigation safety for each of the identified waterways, including adherence to codes and standards (such as the CSA); and<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and waterway users, regarding their navigational use of each of the identified waterways. In its summary, Trans Mountain must:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) describe the Appropriate Government Authorities, potentially affected Indigenous groups, and commercial and recreational waterway users consulted;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) describe how Trans Mountain identified those consulted; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan. | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)&nbsp;&nbsp;(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 55 | <strong>Fugitive Emissions Management Plan for pump stations</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction at any pump stations</strong>, a Fugitive Emissions Management Plan for the pump stations associated with the Project that includes:<br />a) a description of the procedures implemented for leak detection and the criteria used in selecting target leaking components;<br />b) quantification methods considered and the rationale for the selected method(s);<br />c) monitoring frequency for each target leaking component and the parameters that will be measured;<br />d) a decision framework that will be implemented to repair or replace leaking components;<br />e) a description of record-keeping procedures; and<br />f) a discussion of additional mitigation measures that will be employed to minimize fugitive emissions.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 56 | <strong>Grizzly Bear Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction in each vulnerable grizzly bear population unit / grizzly bear management area</strong>, a Grizzly Bear Mitigation Plan for each of these areas. Trans Mountain must provide a rationale for why any vulnerable grizzly bear population units / grizzly bear management units potentially affected by the Project are not addressed in the plan. The Grizzly Bear Mitigation Plan(s) must include:<br />a) a summary of results from any supplemental surveys conducted;<br />b) potential direct and indirect effects of Project activities on vulnerable grizzly bear population units and grizzly bear management units;<br />c) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation success;<br />d) details on post-construction monitoring of mitigation measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />e) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan(s); and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grizzly Bear Mitigation Plan, including confirmation that the mitigation, monitoring, and corrective measures in this plan will be implemented in the case of discovery via their inclusion in Trans Mountain&rsquo;s Wildlife Species of Concern Discovery Contingency Plan.(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 59 | <strong>Worker accommodation strategy</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a worker accommodation strategy, developed in consultation with appropriate municipal or provincial authorities. The strategy must include:<br />a) a final summary of all proposed accommodations, including the location of any temporary camp(s);<br />b) the number of workers that will be housed; and<br />c) a description of how the strategy addresses any concerns or requests raised in consultation with municipal or provincial authorities.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the event that temporary camp(s) are to be used, the strategy must also include:<br />i) a description of how the potential environmental and socio-economic impacts have been assessed, and a description of all associated mitigation measures;<br />ii) copies of, or reference to, any mitigation or operational plans that will be required or implemented for the camp(s), including a description of how Trans Mountain has incorporated any additional mitigation measures into relevant Environmental Protection Plan(s);<br />iii) copies of any necessary municipal or provincial permits for any camp(s) that have been received 3 months prior to construction. &nbsp;If camp permits are not yet in place 3 months prior to commencing construction, provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a list of the outstanding camp permits and a schedule for when these camp permits will be in place; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) copies of any outstanding camp permits prior to commencing construction;<br />iv) copies or excerpts of all policies relating to the rules of conduct for workers housed at the camp(s);<br />v) confirmation that all policies relating to the camp(s) will be provided to workers;<br />vi) confirmation that all policies relating to the camp(s) were made available to all local communities and other relevant service providers in proximity to any camp(s) that will be used for the Project; and<br />vii) a summary of its consultations with affected landowners/tenants where any camp(s) will be located. Trans Mountain must provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a description of the information provided to landowners/tenants; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Strategy.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table and must:(a)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(ii)) <div><strong>at least 30 days prior to commencing construction;</strong></div>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(b) and c)) b) post on its company website the same information required by a),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />c) maintain at each of its construction offices:<ul><li>i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;</li><li>ii) copies of any permits, authorizations, and approvals referenced in i); and</li><li>iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).</li></ul> | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 76 | <strong>Old Growth Management Areas Mitigation and Replacement Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction within old growth management areas</strong>, an Old Growth Management Areas Mitigation and Replacement Plan for these areas that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) avoidance and mitigation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />b) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />c) details on post-construction monitoring, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />d) the expected residual effects (including quantification) on old growth management areas, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional;<br />e) replacement or other offset measures that will be implemented to compensate for residual effects with the aim of no-net-loss to old growth forests within old growth management areas overall, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) discussion of the appropriateness of compensation for the old growth management area, taking its specific features into account, and of any potential limitations of the effectiveness of such replacement or offset measures;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an explanation with rationales on the amount and type of replacements or other offsets required;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a timeline for their implementation;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv)&nbsp; the selection of compensation sites;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) identification of the parties involved in planning and implementation and their respective roles and responsibilities, and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a description of the methods and schedule for monitoring and reporting to demonstrate compensation success;<br />f) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />g) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Old Growth Management Areas Mitigation and Replacement Plan.(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 8 | <strong>Design temperatures &ndash; terminals and pump stations</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 3 months prior to ordering pipe for terminals and pump stations</strong>, confirmation, with rationale, that:<br />a) the selected maximum and minimum design temperatures are in accordance with CSA Z662-15, Clause 5.2.1;<br />b) the selected design temperatures are based on historical, location-specific extreme daily maximum and minimum temperatures, as opposed to average temperatures; and<br />c) the extent of the historical weather data used is commensurate with the expected operational life of the Project.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 80 | <strong>Noise Management Plan for construction at terminals and pump stations</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 3 months prior to commencing construction at each terminal and pump station</strong>, a Noise Management Plan for construction, where residences are within 300 metres of the proposed construction activities. The plan must include:<br />a) proposed hours of daytime and nighttime work;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />c) a noise monitoring program, including locations, methodology, and schedule;<br />d) a description of the public and Indigenous communication and noise complaint response process; and<br />e) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents.<div>&nbsp;</div><div>&nbsp;</div>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 9 | <strong>Quality Management Plan</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 4 months prior to manufacturing any pipe and major components for the Project</strong>, a Project-specific Quality Management Plan that includes:<br />a) material/vendor qualification requirements;<br />b) quality control and assurance of pipe, fittings, and components that ensure all materials meet Trans Mountain&rsquo;s specifications (i.e., processes, procedures, specifications, random testing, inspection, and test reports);<br />c) mandatory documentation of process conditions during manufacture and verification of the conformance of manufacturer material test reports with Trans Mountain&rsquo;s requirements;<br />d) mandatory inspection requirements, inspector competency training, and qualifications;<br />e) non-conformance reporting and correction procedures;<br />f) change management process;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />g) commissioning requirements; and<br />h) material handling requirements during transportation.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 90 | <strong>Consultation on improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a consultation plan for its review of its Emergency Response Plans and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing A3S4V5). This plan must include:<br />a) the consultation plan&rsquo;s scope;<br />b) the consultation plan&rsquo;s objectives;<br />c) a preliminary list of Appropriate Government Authorities, first responders, potentially affected Indigenous groups and affected landowners/tenants with whom Trans Mountain will consult;<br />d) a preliminary list of consultation locations and timing; and<br />e) the methods that will be used to track commitments made during consultations and to incorporate them into Trans Mountain&rsquo;s Emergency Management Program, including its Emergency Response Plans.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 92 | <strong>Updates under the <em>Species at Risk Act</em></strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a summary of any relevant updates under the <em>Species at Risk Act</em>, including new Schedule 1 listings and new or amended Recovery Strategies, Action Plans, and Management Plans for species that have the potential to be affected by the Project. For each species-specific update, the summary must include:<br />a) a discussion of the Project activities&rsquo; potential effects on the listed species or its critical habitat, including an explanation as to whether additional surveys are required to locate such critical habitat;&nbsp;<br />b) identification of all reasonable alternatives to the Project activities referred to in a), including avoidance measures, and a discussion on the potential effects of the alternatives, the chosen approach, and the rationale for selecting the chosen approach;<br />c) any additional site-specific mitigation;<br />d) any monitoring to be undertaken and a commitment to include monitoring results as part of the post-construction environmental monitoring reports filed under Condition 151;<br />e) an explanation as to how the responses to b), c) and d) above are consistent with applicable Recovery Strategies and Actions Plans; and<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the summary of updates, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 94 | <strong>Consultation reports &ndash; protection of municipal water sources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, <strong>and on or before 31 January of each year during construction and of the first 5 years after commencing operations,</strong> a report on Trans Mountain&rsquo;s consultations with municipalities and regional districts, communities, and Indigenous groups related to the protection of municipal and community water sources, including those sources currently relied upon and sources identified for potential future use. Each report must include:<br />a) the name of the municipality, regional district, community, or Indigenous group consulted;<br />b) the methods, dates, and locations of all meetings or consultations;<br />c) a summary of all issues or concerns raised; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />d) a summary of any steps or measures that have been or will be undertaken, including groundwater modelling or monitoring, as a result of consultations with municipalities, regional districts, communities, or Indigenous groups. This summary must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) any updates or amendments to maintenance policies, systems, programs, procedures, practices, and activities aimed at preventing pipeline releases;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the criteria used to identify and select modelling or monitoring locations and parameters;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) results of any modelling or monitoring;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) any measures that have been taken to address modelling or monitoring results; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) any measures to share or to make accessible to municipalities, regional districts, communities, or Indigenous groups data or issues that arise regarding drinking water (aquifers, groundwater, and well water supplies); or<br />in the alternative to i)-v) above, an explanation why no further action is required to address or respond to issues or concerns raised.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-009-2016 | Line 2 Pump Stations Authorization to construct and operate: • Edmonton Pump Station • Gainford Pump Station • Wolf Pump Station • Edson Pump Station • Hinton Pump Station • Blue River Pump Station • McMurphy Pump Station • Blackpool Pump Station • Black Pines Pump Station • Kamloops Pump Station • Kingsvale Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />c) the scope, methodology, and justification for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />d) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to the participating Indigenous group.<br />Trans Mountain must provide a copy of the report to each potentially affected group identified in b) above at the same time that it is filed with the NEB.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp;&nbsp;&nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 100 | <strong>Heritage resources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction of individual Project components as described in Condition 10(a)</strong>:<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b); and<br />d) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c).(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 101 | <strong>Uninterruptible Power Supply (UPS) and battery systems</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction at each terminal and pump station</strong>, confirmation that the UPS system design and planned operation related to that facility, is in compliance with the requirements of CSA 22.1 &ndash; 15 or other applicable standard(s) that exceeds the requirements of CSA 22.1 &ndash; 15. If another standard is used, this filing must include the name of the standard and an explanation of why the standard was used and how it meets or exceeds the requirements of CSA 22.1 1 &ndash; 15.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 105 | <strong>Quality assurance verification</strong><br />Trans Mountain must file <strong>monthly summary reports, </strong><strong>from commencing </strong><strong>construction until after commencing operations, </strong>outlining non-conformances with its design, materials, and construction specifications and the disposition of these non-conformances.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump&nbsp;Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 111 | <strong>Joining Programs</strong><br />Trans Mountain must develop Joining Programs and file them with the NEB <strong>at least 45 days prior to commencing welding of, respectively</strong>:<br />a) field circumferential production, tie-in, and repair pipeline welds, including the tie-in welds between existing segments and Line 1 or Line 2; and<br />b) terminals and pump stations.<br />The Joining Programs must include:<br />i) welder qualification requirements;<br />ii) requirements for welding inspector qualifications and duties;<br />iii) welding procedure specifications;<br />iv) non-destructive examination () specifications;<br />v) procedure qualification records for welding procedure specifications and NDE specifications;<br />vi) a quality assurance program for field welds and welding procedures; and<br />vii) any additional information that supports the Joining Program.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 112 | <strong>Pressure testing</strong><br />a) Trans Mountain must pressure test the new and reactivated pipeline segments, terminals, and pump stations with a liquid medium.<br />b) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing</strong>, a Pressure Testing Program that demonstrates compliance with applicable codes, standards, and regulatory requirements.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 113 | <strong>Hydrostatic Testing Plan</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing of any Project component</strong>, a Hydrostatic Testing Plan for the Project that includes:<br />a) the locations of all water withdrawal and discharge sites;<br />b) a discussion of any clearing activities or any other associated works, if required, that will allow for the transportation of the hydrostatic test water;<br />c) water withdrawal rates;<br />d) water withdrawal volumes;<br />e) the flow rate/volume of water at the withdrawal sites; and<br />f) site-specific mitigation measures to be implemented at the water withdrawal and discharge sites or at any other locations required to allow for the transportation of hydrostatic test water, including a description of the water quality monitoring methods to be used on hydrostatic testing water prior to discharge; and<br />g) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 114 | <strong>NDE of final tie-in welds</strong><br />Trans Mountain must delay NDE of final tie-in welds (i.e.: welds which will not be subjected to hydrostatic testing) and any repairs to them <strong>for at least 48 hours following weld completion</strong>. Trans Mountain must include this requirement in the NDE specification of its Joining Program required by Condition 111.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 121 | <strong>Financial Assurances Plan &ndash; operations phase</strong><br />a) Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to applying for leave to open Line 2,</strong> a Financial Assurances Plan that includes details of the financial resources and secured sources of funds that will be necessary to pay, without limitation, all actual loss or damage, costs and expenses, including cleanup and remediation, and loss of non-use value relating to non-use of a public resource associated with an unintended or uncontrolled release from the Project during the operations phase.<a href=http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn1">[1]</a> These costs may arise from, among other things, potential accidents, malfunctions, and failures during the Project operations phase, including all spills originating from the pipeline and the terminals.<br />The Financial Assurances Plan must be signed by an officer of the company, verifying that it is accurate, complete, and, at a minimum, meets the criteria and coverage levels described below:<br />i) Criteria for financial assurance instruments and plan:<ol><li>Any letter of credit that forms part of the Financial Assurances Plan must be unconditional and irrevocable, segregated from Trans Mountain&#39;s day-to-day business activities, and be dedicated to providing funds to cover the costs described in sub a) above, without limitation.</li><li>Third party liability insurance must be current, and broad, respecting the scope of environmental damages covered by the policy; the policy will be consistent with provisions available in the insurance market(i.e., only exceptional/non-standard perils, taking into account the Project&#39;s nature and scope, would be excluded from coverage). Such insurance must be structured on a multi-year basis, recognizing potential loss of income by persons sustaining damage caused by Trans Mountain, over a reasonable number of years after the event.</li><li>A portion of cash reserves or a portion of future cash flows of the Project may be included as instruments in the Financial Assurances Plan, provided they are secured by a commitment letter from an officer of the company confirming that the funds will be dedicated to the Financial Assurances Plan without restrictions for the period specified by the officer.</li><li>Parental and other third party guarantors must be registered within a Canadian jurisdiction and must have financial strength that is demonstrated in balance sheet values and ratios and credit ratings. For example, total assets less total liabilities of the guarantor should be several multiples of the liability assumed in the Trans Mountain guarantee.</li></ol>ii) Financial assurance components and coverage levels:<br />Trans Mountain&#39;s Financial Assurances Plan must provide a total coverage, for the Project as a whole, of $1.1 billion<a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn2">[2]</a> for the costs described in sub a) above, without limitation. The plan should include the following components and minimum coverage levels:<ol><li>Ready cash: Trans Mountain must have unfettered access to at least $100 million to cover costs, including compensation to third parties for losses and damages in the near term, while insurance claims are being processed. Once used, this source of cash must be replenished immediately to cover the costs of a potential future spill. This can be in the form of a letter of credit, surety bond or other form acceptable to the NEB.</li><li>Core coverage: Trans Mountain must put in effect and maintain current at all times a core financial coverage of at least $1 billion that includes third party liability insurance and other financial assurance instruments that comply with the criteria. Core coverage must be a portfolio approach with multiple financial instruments used and may not be composed of a single financial instrument (e.g., only third party liability insurance). At least one component of core coverage must be funds that are readily accessible to Trans Mountain (e.g., cash reserves held by the general partner and not distributed to the limited partners).<br />Trans Mountain may use a number of financial and insurance instruments in its Financial Assurances Plan. However, sales of Project assets used for transporting hydrocarbon commodities will not be eligible candidates.&nbsp; Below are some illustrative financial and insurance instruments that could be potential candidates for the Financial Assurances Plan:</li></ol><ul><li>Irrevocable, unfettered letter of credit.</li><li>Secured line of credit.</li><li>Cash reserves held by the general partner and not distributed to the limited partners (and verifiable on Trans Mountain Pipelines Limited Partnership&#39;s balance sheet).</li><li>Internal cash flow, committed by Trans Mountain to financial assurances.</li><li>Industry pooled fund.</li><li>Third party liability insurance with exclusions for only exceptional/non-standard perils.</li><li>No fault third party liability insurance.</li><li>Parental and other third party guarantees provided by parties demonstrating financial strength through balance sheets and credit ratings.</li><li>Other instruments developed by Trans Mountain and the insurance and financial markets.</li></ul>b) Trans Mountain must file the following with the NEB:<br />i) <strong>At least 6 months prior to applying for leave to open Line 2</strong>, a report from an independent third party that has assessed the Financial Assurances Plan and its key components against the criteria and actual experiences of industry damage claims. The report must summarize the key features of each financial and insurance instrument proposed for inclusion in the Financial Assurances Plan.<br />ii) <strong>At least 3 months prior to applying for leave to open Line 2</strong>, a supplement to the report described in b)i) that provides verification of any third party liability insurance coverage, a copy of the insurance certificate, and a summary of the insurance policy&#39;s key features. This summary must include: limits on insurance coverage, deductible amounts, the risks and perils and properties covered by the insurance policy, the exclusions from coverage, Trans Mountain&#39;s obligations, effective dates, and names of insurers and reinsurers.<br />iii) <strong>With its first leave to open application for Line 2</strong>, a report describing the steps it took to eliminate any deficiencies in its Financial Assurances Plan that were identified in the independent third party report referenced in b)i) and the NEB&#39;s subsequent review.<br />iv) <strong>On or before 31 January of each year after commencing operations</strong>, a letter signed by an officer of the company verifying that all components of the Financial Assurances Plan remain as the NEB approved and sufficient to meet the financial assurance coverage levels described in ii).<br />v) <strong>At least 2 months prior to any intended change(s) to the Financial Assurances Plan during the Projects operations phase</strong>, a letter, for approval, detailing the intended change(s) and how the change(s) provides the same or greater level of protection.<br />vi) <strong>Within 30 days after accessing any component of the Financial Assurances Plan</strong>, a report detailing the component accessed, the reason for accessing it, and Trans Mountain&rsquo;s plan to ensure that it continues to meet the requirements of its NEB-approved Financial Assurances Plan.<br />&nbsp;<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref1">[1]</a> &nbsp;&nbsp;&nbsp; In the context of this condition, &ldquo;operations phase&rdquo; refers to the period after the Project receives leave to open approval and prior to it being fully abandoned.<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref2">[2]</a> &nbsp;&nbsp;&nbsp; The NEB&rsquo;s basis for any final coverage level is described in its report to Governor in Council." | In Progress | During Construction Phase | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 125 | <strong>Emergency Response Plans for the Pipeline and for the Edmonton, Sumas and Burnaby Terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least&nbsp; 6 months prior to commencing operations</strong>, updated Emergency Response Plans which must include:<br />a) the following relevant emergency preparedness and response documents:<br />i) an Emergency Response Plan to include the pipeline expansion;<br />ii) updated Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals; and<br />iii) all related and accompanying site-specific plans and documents, such as control point mapping, Geographic Response Plans, tactical response plans, volunteer management plans, and fire safety plans;<br />b) an emergency response and preparedness table for the pipeline (including facilities) indicating which plans and documents referenced in a) will be referred to in an emergency response for each 10-kilometre-long pipeline segment. For each pipeline segment, the table must also identify, at a minimum:<br />i) high consequence areas, including environmentally sensitive areas (e.g. wetlands), heritage sites and water supply wells (Condition 93);<br />ii) potentially affected persons or groups;<br />iii) available access to the right-of-way and high consequence areas;<br />iv) nearest control point(s);<br />v) nearest available equipment cache(s);<br />vi) response times for deployment of equipment and Trans Mountain personnel, mutual aid personnel, and third party contractors;<br />vii) the available equipment and trained personnel, whether employed by Trans Mountain, contracted, or available through mutual aid (including contact information); and<br />viii) geological, meteorological, and geographical hazards (e.g., snow avalanche, mud slides, rock slides, and steep slopes); and<br />c) maps depicting the information identified in b).(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 128 | <strong>Offset Measures Plan for residual effects on caribou habitat</strong><br />Trans Mountain must file with the NEB for approval, in accordance with the timelines below, an Offset Measures Plan for each affected caribou range, the goal of which is to offset all unavoidable and residual direct and indirect Project-related effects on caribou habitat, after taking into account the implementation of the measures identified in the relevant Environmental Protection Plan(s) for the Project and the Caribou Habitat Restoration Plan (see Condition&nbsp;37) measures. The Offset Measures Plan must include:<br />a) A preliminary version, to be filed <strong>at least 3 months prior to applying for leave to open</strong>, with the plan&rsquo;s criteria and measurable goals and that includes:<br />i) an initial quantification of the area of caribou habitat directly and indirectly disturbed by the Project;<br />ii) a list of the potential on-the-ground offset measures available;<br />iii) each potential offset measure&rsquo;s appropriate offset ratio, based on consultation with expert federal and provincial authorities and on a review of the scientific literature on conservation offsets;<br />iv) each potential offset measure&rsquo;s expected effectiveness including a discussion of uncertainty and how measures align with criteria specified in the scientific literature specific to conservation offsets;<br />v) each potential offset measure&rsquo;s relative qualitative and quantitative value toward achieving the offset; and<br />vi) a conceptual decision-making tree(s) or decision framework(s) that will be used to select which specific potential offset measures and accompanying offset ratios will be used under what circumstances.<br />b) A final version, to be filed <strong>on or before 31 January after the second complete growing season after completing final clean-up</strong>, including:<br />i) the contents of the preliminary Offset Measures Plan, with any updates identified in a revision log that includes the rationale for any changes;<br />ii) a tabular list of the potential offset measures and appropriate offset ratios to be implemented or already underway, including site-specific details and maps showing the locations, and an explanation of how they meet criteria in the scientific literature for offsets;<br />iii) a description of factors considered when determining the location of offset measures, including consideration of how the measures could maximize benefits to landscape variables;<br />iv) a schedule indicating when potential offset measures will be initiated and their estimated completion dates;<br />v)either an assessment of the predicted offset measures&rsquo; effectiveness including a discussion of uncertainty and a quantitative compilation showing how the measures would offset the previously determined residual effects, or a plan for completing an assessment of the potential offset measures&rsquo; effectiveness and value; and<br />vi) an update on the restoration success to support offset measure decisions.<br />Both the preliminary and final versions of the plan must also include the following:<ol><li>a summary of its consultations with Appropriate Government Authorities and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Offset Measures Plan;</li><li>a description of how Trans Mountain has taken any available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and</li><li>evidence of Trans Mountain&rsquo;s consideration of any updates to the applicable Recovery Strategy, as well as to range boundaries and identified critical habitat made prior and up to the date on which leave to open is granted.</li></ol> | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 130 | <strong>Groundwater Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing operations</strong>, a Groundwater Monitoring Program that pertains to all terminals and pump stations, and for any vulnerable aquifers along the pipeline route. The&nbsp; program must include, at a minimum:<br />a) locations of groundwater monitoring wells, their depths, the rationales for well locations (including how groundwater flow direction was considered), groundwater flow velocity, parameters to be monitored and frequency of monitoring;<br />b) a description of any program changes required to meet this condition for facilities with an existing Groundwater Monitoring Program;<br />c) methods, criteria and rationale for identifying vulnerable aquifers along the pipeline route;<br />d) applicable regulatory criteria for comparing monitoring results, and a process outlining what steps will be followed should monitoring results indicate a negative change in groundwater quality;and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the program.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 140 | <strong>Post-construction greenhouse gas (GHG) assessment report</strong><br />Trans Mountain must file with the NEB for approval, <strong>within</strong> <strong>2 months after commencing operations</strong>, an updated GHG assessment report specific to the Project. The report must include:<br />a) the methodology used for the assessment, including the sources of GHG emissions, assumptions, and methods of estimation;<br />b) the total direct GHG emissions generated from Project construction, including land-clearing;<br />c) a breakdown of direct GHG emissions generated by the construction of individual Project components (pipeline, pump stations, tank terminals and Westridge Marine Terminal) and by land-clearing activities; and<br />d) a comparison and discussion of the direct GHG emissions calculated in b) with the predicted emissions in Trans Mountain&rsquo;s application and subsequent submissions.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 142 | <strong>GHG Emissions Offset Plan &ndash; Project construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>within 4 months after commencing operations</strong>, a plan for providing offsets for all direct GHG emissions generated from Project construction, as determined in Condition 140. The plan must include:<br />a) a list and discussion of all possible offset options considered;<br />b) the criteria against which each option was assessed for viability;<br />c) a description of the offset option(s) selected for direct GHG emissions generated from Project construction, and the rationale for selecting the option(s);<br />d) confirmation that the selected offset option is registered under the approved quantification protocols and has been verified by an accredited &ldquo;verification body&rdquo; ;<br />e) a schedule indicating when the selected offset options(s) will be initiated; and<br />f) an accounting of offsets confirming no net GHG emissions from Project construction.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Post Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 146 | <strong>Reports on engagement with Indigenous groups &ndash; operations</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations,</strong> a report on the engagement activities it has undertaken with Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;<br />b)&nbsp; the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 147 | <strong>Natural hazard assessment</strong><br />Trans Mountain must file with the NEB, <strong>within 1 year after commencing operations</strong>:<br />a) the results of the baseline natural hazard assessment for the Project; and<br />b) confirmation that the natural hazard assessment will be:<br />i) updated at intervals not exceeding 5 years; and<br />ii) integrated into the existing Natural Hazard Management Program for the Trans Mountain Pipeline system.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 149 | <strong>Caribou Habitat Restoration and Offset Measures Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the first complete growing season after commencing operations</strong>, a program for monitoring and verifying the effectiveness of caribou habitat restoration and offset measures implemented as part of the final Caribou Habitat Restoration Plan (Condition 37) and the final Offset Measures Plan (Condition 128). This program must include:<br />a) the scientific methods or protocols for short- and long-term monitoring of the restoration and offset measures, and effectiveness of the measures;<br />b) monitoring frequency, timing, and locations, and the rationale for each;<br />c) protocols for how restoration and offset measures will be adapted, as required, based on the monitoring results from the program&rsquo;s implementation;<br />d) a summary of Trans Mountain&rsquo;s consultation with Appropriate Government Authorities and any species experts on the design of the monitoring program; and<br />e) a proposed schedule for filing reports on monitoring results and adaptive management measures to the NEB, Environment and Climate Change Canada, and appropriate provincial authorities to be contained in the Caribou Habitat Restoration and Offset Measures Monitoring Program as well as at the beginning of each report filed. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 150 | <strong>Caribou habitat restoration and offset measures monitoring report(s)</strong><br />Trans Mountain must file with the NEB, <strong>based on the approved schedule for the Caribou Habitat Restoration and Offset Measures Monitoring Program </strong>(required by Condition 149), a report(s) outlining the monitoring program&rsquo;s results, including the observed effectiveness of habitat restoration and offset measures for each affected caribou range, and how those measures will be adapted, as required, based on monitoring results. Any proposed changes to the NEB-approved reporting schedule must be included within the relevant report prior to any reporting on a revised schedule. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up, </strong>a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants.<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />i) an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />ii) a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />iii) an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 155 | <strong>Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the <em>Species at Risk Act</em>, that includes:<br />a) an evaluation of avoidance and mitigation success with reference to the measurable goals outlined in the Rare Ecological Community and Rare Plant Population Management Plan required by Condition 40;<br />b) identification of communities, species, and critical habitats that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />c) identification of any ongoing effects to ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, or on any early draft, candidate, proposed, or final critical habitat under the <em>Species at Risk Act</em>;<br />d) for the ongoing effects identified in c), a Final Rare Ecological Community and Rare Plant Population Offset Plan that updates the Preliminary Rare Ecological Community and Rare Plant Population Offset Plan required by Condition 40, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 156 | <strong>Wetland Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Wetland Reclamation Evaluation Report and Offset Plan that includes:<br />a) the extent (in hectares), by wetland type, that was impacted by Project construction and associated activities;<br />b) for each wetland impacted, an evaluation of mitigation and reclamation success with reference to the measurable goals outlined in the Wetland Survey and Mitigation Plan required by Condition 41;<br />c) identification of any wetlands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, an evaluation of any temporary or ongoing loss of any individual functional condition (e.g., habitat, hydrology and biogeochemistry);<br />e) for any wetland that has not achieved reclamation success in terms of overall wetland function, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition, a Final Wetland Offset Plan that updates the Preliminary Wetland Offset Plan required by Condition 41, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 157 | <strong>Grasslands Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the tenth complete growing season after completing final clean-up</strong>, a Grasslands Reclamation Evaluation Report and Offset Plan that applies to native grasslands in the British Columbia interior and that includes:<br />a) the extent (in hectares) of grasslands that were impacted by Project construction and associated activities;<br />b) an evaluation of reclamation success with reference to the measurable goals outlined in the Grasslands Survey and Mitigation Plan required by Condition 42;<br />c) an identification of any grasslands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for those grasslands that have not yet achieved reclamation success, a Final Grasslands Offset Plan that updates the preliminary plan required by Condition 42, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | ?<strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp; &nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp; &nbsp; &nbsp; | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 30 | <strong>Power system protection for pump stations and terminals</strong><br />Trans Mountain must file with the NEB the following details of its electrical power system design for each pump station and each of the following: Westridge Marine Terminal, Burnaby Terminal, Edmonton Terminal, and Sumas Terminal:(a)) Descriptions of the overcurrent and ground fault protection schemes including:(i)) a summary of coordination studies between the upstream and downstream protective devices, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)<br />&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)<br />&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)<br />&nbsp;(ii)) relay settings and time-current curves, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)<br />&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)<br />&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)<br />&nbsp;(iii)) the specification of neutral grounding resistors, <strong>at least 6 months prior to commencing construction</strong>;(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)<br />&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)<br />&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)<br />&nbsp;(iv)) specifications of contactors, fuses, and circuit breakers, <strong>at least 6 months prior to commencing construction</strong>; and(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)<br />&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)<br />&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)<br />&nbsp;(v)) a description of other electrical protections, relay settings, and trip characteristics, <strong>at least 3 months prior to commencing dry commissioning.</strong>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)<br />&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)<br />&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)<br />&nbsp;(b)) Consistent with the NEB&rsquo;s Safety Advisory SA-2015-03, dated 4 May 2015, <strong>at least 6 months prior to commencing construction</strong>, information confirming that Trans Mountain has performed the ground fault and arcing fault protection designs for each pump station and terminal, including:<br /><br />i) a means to clear ground faults without intentional time delay if the fault currents exceed the design limit set by the neutral grounding resistance; and<br />ii) a means to block the stored energy from other running motors from feeding an electrical fault in another motor running from the same bus.<br /><br />This filing must include a description of the ground fault and arcing fault protection designs including the above measures.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(c)) <strong>At least 6 months prior to commencing construction</strong>, either:<br /><br />i) a written confirmation that Trans Mountain determined during detailed design that electrical faults will not exceed their design limits and migrate to an arcing fault; <strong>or</strong><br />ii) for a station or a terminal for which Trans Mountain determined during detailed design that an electrical fault could exceed its design limit and migrate to an arcing fault, the electrical configuration of that station or terminal and the additional equipment and devices that will be used to mitigate the adverse effects of such arcing faults.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(d)) Single-line diagrams of the electrical power systems<strong>, at least 6 months prior to commencing construction.</strong>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 36 | <strong>Pre-construction caribou habitat assessment</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range</strong>, a detailed caribou habitat assessment of the Project right-of-way through each caribou range traversed by the Project, including a 500 metre buffer on either side. The framework of the habitat assessment must use the updated critical habitat polygons delineated by the Southern Mountain Caribou Recovery Team and components of critical habitat outlined in the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014). The habitat assessment must include:<br />a) map(s) indicating the location of the habitat;<br />b) a description of the amount of habitat and the existing habitat alteration, in hectares;<br />c) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge into consideration into the assessment including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />d) a description of how Trans Mountain has incorporated input from Appropriate Government Authorities and species experts into the assessment methodology; and<br />e) a description of the type of habitat characterized by the biophysical attributes of critical habitat, as defined in the applicable Recovery Strategy.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 37 | Trans Mountain must file with the NEB for approval, in accordance with the timelines below, preliminary and final versions of a CHRP for each caribou range potentially affected by the Project.(a)) <strong>Preliminary CHRP </strong>&ndash; to be filed <strong>at least 6 months prior to commencing construction of any Project component potentially affecting each caribou range. </strong>This version of the CHRP must include the following:<br />i) the CHRP&rsquo;s goals and measureable targets for each caribou range, including the goal of avoidance of critical habitat destruction;<br />ii) a detailed description of measures that will be used to avoid or lessen Project activities that impact critical habitat, and the rationale for selecting the measures;<br />iii) a list of criteria used to identify potential caribou habitat restoration sites;<br />iv) conceptual decision-making tree(s) or decision framework(s) that will be used to identify and prioritize potential caribou habitat restoration sites, and mitigative actions to be used at different types of sites, including consideration of typical site factors that may constrain implementation;<br />v) a literature review upon which the decision-making tree(s) or decision framework(s) are based, including:<br />1) an identification of applicable temporal and spatial caribou habitat restoration methodologies;<br />2) an assessment of the relative effectiveness of the identified methodologies; and<br />3) a detailed methodology of how the literature review was conducted.<br />vi) the quantifiable targets and performance measures that will be used to evaluate the extent of predicted residual effects, CHRP effectiveness, the extent to which the goals and measurable targets have been met, and the need for further measures to offset unavoidable and residual effects on caribou habitat;<br />vii) a schedule indicating when mitigation measures will be initiated and their estimated completion dates;<br />viii) a description of how Trans Mountain has taken available and applicable Indigenous traditional ecological knowledge studies into consideration in identifying potential caribou habitat restoration sites including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />ix) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the preliminary CHRP.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(b)) <strong>Final CHRP </strong>&ndash; to be filed <strong>on or before 1 November after the first complete growing season after completing final clean-up.</strong> This version of the CHRP must include the following:<br />i) the preliminary CHRP, with any updates identified in a revision log that includes the rationale for any changes to decision-making criteria;<br />ii) a complete tabular list of caribou habitat restoration sites, including locations, spatial areas, habitat quality descriptions, site-specific restoration activities, and challenges;<br />iii) a description of how selected restoration measures are consistent with the Recovery Strategy for the Woodland Caribou, Southern Mountain Population in Canada (2014);<br />iv) maps or updated Environmental Alignment Sheets showing the site locations;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />v) specification drawings for the implementation of each restoration method;<br />vi) a qualitative and quantitative and assessment of the total area of direct and indirect disturbance to caribou habitat that will be restored, the duration of spatial disturbance, and the area-based extent of the resulting unavoidable and residual effects to be offset, including indirect disturbance; and<br />vii) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the final CHRP.(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 38 | <strong>Sowaqua Spotted Owl Mitigation Plan </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction of any Project component within the Sowaqua spotted owl wildlife habitat area</strong>, a Sowaqua Spotted Owl Mitigation Plan that includes:<br />a) a summary of results from supplemental surveys conducted in the Sowaqua spotted owl wildlife habitat area;<br />b) the area of habitat potentially directly and indirectly affected by the Project;<br />c) a description of how an avoidance, mitigation, and offset hierarchy was considered in the plan;<br />d) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable goals for evaluating mitigation success;<br />e) an evaluation of offset options within or outside of the Sowaqua spotted owl wildlife habitat area, an indication of the selected option, and the rationale for the selected option;<br />f) details on post-construction monitoring of mitigation measures and offset measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, any adjustments to the offset measures, and a proposed reporting schedule;<br />g) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />h) details on how the mitigation and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the mitigation plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the mitigation plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the mitigation plan.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 40 | <strong>Rare Ecological Community and Rare Plant Population Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, an updated Rare Ecological Community and Rare Plant Population Management Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the Species at Risk Act, that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results, and a demonstration of the overall adequacy of the rare ecological community and rare plant surveys, including the adequacy for the identification of biophysical attributes for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act;<br />b) avoidance and mitigation measures to be implemented during construction and operations, including all relevant measures committed to throughout the OH-001-2014 proceeding and any new measures resulting from supplementary surveys, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />c) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />d) details on post-construction monitoring, including survey methods, the appropriate number of years of monitoring to determine the success of each type of avoidance and mitigation measure, corrective actions that might be necessary, and the circumstances under which each such action would be taken;<br />e) a Preliminary Rare Ecological Community and Rare Plant Population Offset Plan for any ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, and for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act, and that, after five years of operations, have ongoing effects. This preliminary plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a rationale for why the community, species, or critical habitat cannot be avoided by a sufficient distance to avoid both direct and indirect residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the expected residual effects on that community, species, or critical habitat, including a discussion of the potential for time lags &nbsp;between when Project effects occur and when mitigation measures would become fully functional, and taking into account the success on past projects of the proposed mitigation and corrective measures in b) and d) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the appropriateness of offsets for the community, species or critical habitat, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of how the avoidance, mitigation, monitoring, corrective and offset measures are consistent with any applicable recovery, action or management strategies or plans for the community, species or critical habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Rare Ecological Community and Rare Plant Population Management Plan, including confirmation that the avoidance, mitigation, monitoring, corrective, and offset measures in the Rare Ecological Community and Rare Plant Population Management Plan will be implemented to the extent feasible in the case of discovery via their inclusion in the Rare Ecological Communities or Rare Plant Species Discovery Contingency Plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 41 | <strong>Wetland Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Wetland Survey and Mitigation Plan for wetlands potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results and a demonstration of the overall adequacy of the wetland surveys;<br />b) a description of any wetlands for which ground-based surveys were not possible, an explanation as to why not, attempts made to obtain access, and what further information on each wetland will be collected immediately prior to or during construction;<br />c) a description of the functional condition of each wetland for comparison during post-construction monitoring, including individual functional conditions (e.g., habitat, hydrology and biogeochemistry, including the presence and abundance of migratory birds and species at risk), and a description of the methods used to determine the type and amount of each individual wetland function and the overall functional condition;<br />d) a description of the crossing methods, mitigation measures and reclamation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each such method and measure will be applied;<br />e) measurable goals against which the success of wetland mitigation and reclamation will be evaluated, including a description of how such goals incorporate the aim of returning wetlands to their original functionality while allowing for reasonable natural variation, and including measurable goals for each of the first-, third- and fifth-year post-construction monitoring reporting stages for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies;<br />f) a description of how the<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss of wetland function, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />g) details of the post-construction monitoring plan for wetlands for the first five years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Wetland Offset Plan for any wetland that has not achieved reclamation success in terms of overall wetland function after five years of operations, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition &ndash; this plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the expected residual effects on the wetland, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in d) and g) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the wetland, taking its specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios and indicator species, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, details with rationales on the offset measures that will be implemented before or during the first five years of operations to compensate for expected temporary or ongoing losses to individual functional conditions, including the amount and type of offsets required, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wetland Survey and Mitigation Plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 42 | <strong>Grasslands Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Grasslands Survey and Mitigation Plan for native grasslands in the B.C. interior that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of survey results for such grasslands, including but not limited to native plant species diversity, species at risk, the density and distribution of existing invasive plant species, and the presence of cryptogamic crust, together with a demonstration of the adequacy of such surveys and a summary of existing and ongoing land management impacts;<br />b) a description (including quantification) of overlap of the Project with grasslands and of expected residual effects;<br />c) a description of the mitigation and reclamation measures to be implemented for grasslands during construction and operations, including the extent to which native seed will be used, with rationales and unambiguous criteria explaining under what circumstances each such measure will be applied;<br />d) measurable goals against which the success of grassland mitigation and reclamation will be evaluated, including goals related to cryptogamic crust recovery, invasive species control, and access control, and how existing and ongoing land management impacts and land-use changes by landowners outside the control of Trans Mountain will be taken into account;<br />e) a description of how the:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy, and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss for grasslands, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />f) details of the post-construction monitoring plan for grasslands for the first ten years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />g) a Preliminary Grasslands Offset Plan for those grasslands that, after ten years of operations, have not achieved reclamation success. This plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) expected residual effects on the grasslands, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in c) and f) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the grasslands, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offsets measures will be monitored, assessed, and reported on, and problems corrected;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />i) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />j) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grasslands Survey and Mitigation Plan.(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 44 | <strong>Wildlife Species at Risk Mitigation and Habitat Restoration Plans&nbsp; </strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction,</strong> Wildlife Species at Risk Mitigation and Habitat Restoration Plans for each species whose draft, candidate, proposed, or final critical habitat is directly or indirectly affected by the Project. Each plan must include:<br />a) a summary of supplementary pre-construction survey results, including surveys for biophysical attributes of critical habitat;<br />b) the location and type of critical habitat, for those wildlife species with early draft and candidate critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />c) the location, types and total spatial area for each type of critical habitat for those wildlife species with proposed or final critical habitat, including a description of the biophysical attributes, potentially directly and indirectly affected by the Project;<br />d) a detailed description of measures that will be used to avoid the destruction of critical habitat;<br />e) a detailed description of mitigation and habitat restoration measures to be implemented to reduce direct and indirect Project effects on critical habitat, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation and critical habitat restoration success;<br />f) identification and review of alternative mitigation and habitat restoration measures to avoid or lessen direct and indirect Project effects on critical habitat, and the rationale for the selected measure(s);<br />g) detailed description of how selected mitigation and critical habitat restoration measures address the potential for time lags between when the Project impacts occur and when mitigation and critical habitat restoration measures are implemented and are fully functional;<br />h) details on post-construction monitoring of mitigation measures and critical habitat restoration measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />i) details on how the mitigation, critical habitat restoration measures, and monitoring measures are consistent with applicable Recovery Strategies and Action Plans;<br />j) a commitment to include the results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />k) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plans including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />l) a summary of its consultations with Appropriate Government Authorities, any species experts, potentially affected Indigenous groups and affected landowner/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />m) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wildlife Species at Risk Mitigation and Habitat Restoration Plans. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 47 | <strong>Access Management Plan(s)</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, an Access Management Plan(s) to be included within the updated Environmental Protection Plans required by Conditions 72 and 78. Each plan must address issues related to soil, vegetation, fish and fish habitat, and wildlife and wildlife habitat. Each plan must also describe access control measures proposed to control both human and predator access during construction and operations, and include:<br />a) objectives of the plan;<br />b) measurable goals for evaluating the plan&rsquo;s success in achieving its objectives;<br />c) a summary of any related baseline information that has been or will be collected to aid in evaluating the plan&rsquo;s success, and justification of the adequacy of this baseline information, or a rationale if no baseline information has or will be collected;<br />d) a list of sites where access control measures will be implemented for construction and those that will remain in place throughout operations, the control measure(s) proposed at those sites, and the rationale for selecting those sites and measures;<br />e) the methods for monitoring the effectiveness of access control measures implemented during construction and operations, and justification of the adequacy of such monitoring;<br />f) a description of available adaptive management measures and of the criteria Trans Mountain will use to determine if and when adaptive management measures are warranted based on monitoring results;<br />g) a commitment to report, as part of Trans Mountain&rsquo;s post-construction environmental monitoring reports (required by Condition 151), on the control measures implemented, monitoring undertaken, and the success of control measures in meeting Access Management Plan goals and objectives, as well as a schedule, with rationale, for reporting throughout operations;<br />h) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge studies into consideration including demonstration that those Indigenous persons and groups that provided Indigenous traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />i) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Plan/Report.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 48 | <strong>Navigation and navigation safety plan</strong><br />Trans Mountain must file with the NEB, <strong>for approval</strong>, <strong>at least 4 months prior to commencing construction</strong>, a Navigation and Navigation Safety Plan that includes:<br />a) an updated list of navigable waterways to be crossed by or affected by the Project (including power lines, marine terminal, temporary or permanent bridge crossings, or other ancillary works that are physically or operationally connected to the Project);<br />b) an updated listing of effects of the Project on navigation and navigation safety for each of the identified waterways identified in a);<br />c) proposed mitigation measures to address Project effects on navigation and navigation safety for each of the identified waterways, including adherence to codes and standards (such as the CSA); and<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and waterway users, regarding their navigational use of each of the identified waterways. In its summary, Trans Mountain must:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) describe the Appropriate Government Authorities, potentially affected Indigenous groups, and commercial and recreational waterway users consulted;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) describe how Trans Mountain identified those consulted; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan. | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 55 | <strong>Fugitive Emissions Management Plan for pump stations</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction at any pump stations</strong>, a Fugitive Emissions Management Plan for the pump stations associated with the Project that includes:<br />a) a description of the procedures implemented for leak detection and the criteria used in selecting target leaking components;<br />b) quantification methods considered and the rationale for the selected method(s);<br />c) monitoring frequency for each target leaking component and the parameters that will be measured;<br />d) a decision framework that will be implemented to repair or replace leaking components;<br />e) a description of record-keeping procedures; and<br />f) a discussion of additional mitigation measures that will be employed to minimize fugitive emissions.<div>&nbsp;</div><div>&nbsp;</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 56 | <strong>Grizzly Bear Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction in each vulnerable grizzly bear population unit / grizzly bear management area</strong>, a Grizzly Bear Mitigation Plan for each of these areas. Trans Mountain must provide a rationale for why any vulnerable grizzly bear population units / grizzly bear management units potentially affected by the Project are not addressed in the plan. The Grizzly Bear Mitigation Plan(s) must include:<br />a) a summary of results from any supplemental surveys conducted;<br />b) potential direct and indirect effects of Project activities on vulnerable grizzly bear population units and grizzly bear management units;<br />c) mitigation measures to be implemented, including all relevant measures committed to throughout the OH-001-2014 proceeding, any new mitigation measures resulting from supplementary surveys, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and measurable targets for evaluating mitigation success;<br />d) details on post-construction monitoring of mitigation measures, including survey methods, corrective measures, detailed criteria using clear and unambiguous language that describes the circumstances under which each measure will be applied, and a proposed reporting schedule;<br />e) a commitment to include results of the monitoring in the post-construction environmental monitoring reports filed under Condition 151;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan(s); and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Grizzly Bear Mitigation Plan, including confirmation that the mitigation, monitoring, and corrective measures in this plan will be implemented in the case of discovery via their inclusion in Trans Mountain&rsquo;s Wildlife Species of Concern Discovery Contingency Plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 59 | <strong>Worker accommodation strategy</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a worker accommodation strategy, developed in consultation with appropriate municipal or provincial authorities. The strategy must include:<br />a) a final summary of all proposed accommodations, including the location of any temporary camp(s);<br />b) the number of workers that will be housed; and<br />c) a description of how the strategy addresses any concerns or requests raised in consultation with municipal or provincial authorities.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the event that temporary camp(s) are to be used, the strategy must also include:<br />i) a description of how the potential environmental and socio-economic impacts have been assessed, and a description of all associated mitigation measures;<br />ii) copies of, or reference to, any mitigation or operational plans that will be required or implemented for the camp(s), including a description of how Trans Mountain has incorporated any additional mitigation measures into relevant Environmental Protection Plan(s);<br />iii) copies of any necessary municipal or provincial permits for any camp(s) that have been received 3 months prior to construction. &nbsp;If camp permits are not yet in place 3 months prior to commencing construction, provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a list of the outstanding camp permits and a schedule for when these camp permits will be in place; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) copies of any outstanding camp permits prior to commencing construction;<br />iv) copies or excerpts of all policies relating to the rules of conduct for workers housed at the camp(s);<br />v) confirmation that all policies relating to the camp(s) will be provided to workers;<br />vi) confirmation that all policies relating to the camp(s) were made available to all local communities and other relevant service providers in proximity to any camp(s) that will be used for the Project; and<br />vii) a summary of its consultations with affected landowners/tenants where any camp(s) will be located. Trans Mountain must provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a description of the information provided to landowners/tenants; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Strategy.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table and must:(a)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(ii)) <div><strong>at least 30 days prior to commencing construction</strong>;</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(b) and c)) b) post on its company website the same information required by a),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />c) maintain at each of its construction offices:<ul><li>i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;</li><li>ii) copies of any permits, authorizations, and approvals referenced in i); and</li><li>iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).</li></ul> | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 7 | <strong>Environmental and socio-economic assessment - route re-alignments</strong><br />As applicable, Trans Mountain must file with the NEB for approval,&nbsp;<strong>concurrent with its filing of the Plan, Profile and Book of Reference pursuant to section 33 of the&nbsp;<em>National Energy Board Act</em></strong>, an environmental and socio-economic assessment for each proposed detailed route re-alignment that extends beyond the applied-for corridor width of Trans Mountain&rsquo;s preferred route in proximity to:<br />&bull; Ohamil Indian Reserve 1;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&bull; Tzeachten Indian Reserve 13; and<br />&bull; Surrey Bend Regional Park.<br />Any assessment must include:<br />a) environmental alignment sheets at an appropriate scale, clearly depicting the proposed route re-alignments;<br />b) results of any pre-construction surveys within the areas that were not previously subject to such surveys, and an indication of potential residual effects;<br />c) all associated mitigation measures that are beyond those identified during the OH-001-2014 proceeding;<br />d) analysis supporting the use of the measures in c), including any supplementary reports;<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information based on any supplemental surveys completed; and<br />f) a summary of consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants, as well as copies of all written comments that may be provided to Trans Mountain by those consulted. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the assessment.<div>&nbsp;</div><div>&nbsp;</div>(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 76 | <strong>Old Growth Management Areas Mitigation and Replacement Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction within old growth management areas</strong>, an Old Growth Management Areas Mitigation and Replacement Plan for these areas that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) avoidance and mitigation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />b) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />c) details on post-construction monitoring, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />d) the expected residual effects (including quantification) on old growth management areas, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional;<br />e) replacement or other offset measures that will be implemented to compensate for residual effects with the aim of no-net-loss to old growth forests within old growth management areas overall, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) discussion of the appropriateness of compensation for the old growth management area, taking its specific features into account, and of any potential limitations of the effectiveness of such replacement or offset measures;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an explanation with rationales on the amount and type of replacements or other offsets required;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a timeline for their implementation;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv)&nbsp; the selection of compensation sites;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) identification of the parties involved in planning and implementation and their respective roles and responsibilities, and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a description of the methods and schedule for monitoring and reporting to demonstrate compensation success;<br />f) a summary of its consultations with Appropriate Government Authorities and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />g) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Old Growth Management Areas Mitigation and Replacement Plan.(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 8 | <strong>Design temperatures &ndash; terminals and pump stations</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to ordering pipe for terminals and pump stations</strong>, confirmation, with rationale, that:<br />a) the selected maximum and minimum design temperatures are in accordance with CSA Z662-15, Clause 5.2.1;<br />b) the selected design temperatures are based on historical, location-specific extreme daily maximum and minimum temperatures, as opposed to average temperatures; and<br />c) the extent of the historical weather data used is commensurate with the expected operational life of the Project.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 80 | <strong>Noise Management Plan for construction at terminals and pump stations</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 3 months prior to commencing construction at each terminal and pump station</strong>, a Noise Management Plan for construction, where residences are within 300 metres of the proposed construction activities. The plan must include:<br />a) proposed hours of daytime and nighttime work;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />c) a noise monitoring program, including locations, methodology, and schedule;<br />d) a description of the public and Indigenous communication and noise complaint response process; and<br />e) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents.<div>&nbsp;</div><div>&nbsp;</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 9 | <strong>Quality Management Plan</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 4 months prior to manufacturing any pipe and major components for the Project</strong>, a Project-specific Quality Management Plan that includes:<br />a) material/vendor qualification requirements;<br />b) quality control and assurance of pipe, fittings, and components that ensure all materials meet Trans Mountain&rsquo;s specifications (i.e., processes, procedures, specifications, random testing, inspection, and test reports);<br />c) mandatory documentation of process conditions during manufacture and verification of the conformance of manufacturer material test reports with Trans Mountain&rsquo;s requirements;<br />d) mandatory inspection requirements, inspector competency training, and qualifications;<br />e) non-conformance reporting and correction procedures;<br />f) change management process;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />g) commissioning requirements; and<br />h) material handling requirements during transportation.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 92 | <strong>Updates under the <em>Species at Risk Act</em></strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a summary of any relevant updates under the <em>Species at Risk Act</em>, including new Schedule 1 listings and new or amended Recovery Strategies, Action Plans, and Management Plans for species that have the potential to be affected by the Project. For each species-specific update, the summary must include:<br />a) a discussion of the Project activities&rsquo; potential effects on the listed species or its critical habitat, including an explanation as to whether additional surveys are required to locate such critical habitat;&nbsp;<br />b) identification of all reasonable alternatives to the Project activities referred to in a), including avoidance measures, and a discussion on the potential effects of the alternatives, the chosen approach, and the rationale for selecting the chosen approach;<br />c) any additional site-specific mitigation;<br />d) any monitoring to be undertaken and a commitment to include monitoring results as part of the post-construction environmental monitoring reports filed under Condition 151;<br />e) an explanation as to how the responses to b), c) and d) above are consistent with applicable Recovery Strategies and Actions Plans; and<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the summary of updates, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 94 | <strong>Consultation reports &ndash; protection of municipal water sources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, <strong>and on or before 31 January of each year during construction and of the first 5 years after commencing operations,</strong> a report on Trans Mountain&rsquo;s consultations with municipalities and regional districts, communities, and Indigenous groups related to the protection of municipal and community water sources, including those sources currently relied upon and sources identified for potential future use. Each report must include:<br />a) the name of the municipality, regional district, community, or Indigenous group consulted;<br />b) the methods, dates, and locations of all meetings or consultations;<br />c) a summary of all issues or concerns raised; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />d) a summary of any steps or measures that have been or will be undertaken, including groundwater modelling or monitoring, as a result of consultations with municipalities, regional districts, communities, or Indigenous groups. This summary must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) any updates or amendments to maintenance policies, systems, programs, procedures, practices, and activities aimed at preventing pipeline releases;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the criteria used to identify and select modelling or monitoring locations and parameters;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) results of any modelling or monitoring;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) any measures that have been taken to address modelling or monitoring results; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) any measures to share or to make accessible to municipalities, regional districts, communities, or Indigenous groups data or issues that arise regarding drinking water (aquifers, groundwater, and well water supplies); or<br />in the alternative to i)-v) above, an explanation why no further action is required to address or respond to issues or concerns raised.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-008-2016 | Line 1 Pump Stations Authorization to construct and operate: • Black Pines Pump Station on Line 1 Authorization to: • drag reducing agent (DRA) injection at Jasper Pump Station • add one pump unit to Kamloops Pump Station • add one pump unit to Sumas Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />c) the scope, methodology, and justification for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />d) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to the participating Indigenous group.<br />Trans Mountain must provide a copy of the report to each potentially affected group identified in b) above at the same time that it is filed with the NEB.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.<div>&nbsp;</div>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 100 | <strong>Heritage resources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction of individual Project components as described in Condition 10(a)</strong>:<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b); and<br />d) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c).(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 101 | <strong>Uninterruptible Power Supply (UPS) and battery systems</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction at each terminal and pump station</strong>, confirmation that the UPS system design and planned operation related to that facility, is in compliance with the requirements of CSA 22.1 &ndash; 15 or other applicable standard(s) that exceeds the requirements of CSA 22.1 &ndash; 15. If another standard is used, this filing must include the name of the standard and an explanation of why the standard was used and how it meets or exceeds the requirements of CSA 22.1 1 &ndash; 15.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 105 | <strong>Quality assurance verification</strong><br />Trans Mountain must file <strong>monthly summary reports, </strong><strong>from commencing </strong><strong>construction until after commencing operations, </strong>outlining non-conformances with its design, materials, and construction specifications and the disposition of these non-conformances.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 111 | <strong>Joining Programs</strong><br />Trans Mountain must develop Joining Programs and file them with the NEB <strong>at least 45 days prior to commencing welding of, respectively</strong>:<br />a) field circumferential production, tie-in, and repair pipeline welds, including the tie-in welds between existing segments and Line 1 or Line 2; and<br />b) terminals and pump stations.<br />The Joining Programs must include:<br />i) welder qualification requirements;<br />ii) requirements for welding inspector qualifications and duties;<br />iii) welding procedure specifications;<br />iv) non-destructive examination () specifications;<br />v) procedure qualification records for welding procedure specifications and NDE specifications;<br />vi) a quality assurance program for field welds and welding procedures; and<br />vii) any additional information that supports the Joining Program.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 112 | <strong>Pressure testing</strong><br />a) Trans Mountain must pressure test the new and reactivated pipeline segments, terminals, and pump stations with a liquid medium.<br />b) Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing</strong>, a Pressure Testing Program that demonstrates compliance with applicable codes, standards, and regulatory requirements.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 113 | <strong>Hydrostatic Testing Plan</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing pressure testing of any Project component</strong>, a Hydrostatic Testing Plan for the Project that includes:<br />a) the locations of all water withdrawal and discharge sites;<br />b) a discussion of any clearing activities or any other associated works, if required, that will allow for the transportation of the hydrostatic test water;<br />c) water withdrawal rates;<br />d) water withdrawal volumes;<br />e) the flow rate/volume of water at the withdrawal sites; and<br />f) site-specific mitigation measures to be implemented at the water withdrawal and discharge sites or at any other locations required to allow for the transportation of hydrostatic test water, including a description of the water quality monitoring methods to be used on hydrostatic testing water prior to discharge; and<br />g) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 114 | <strong>NDE of final tie-in welds</strong><br />Trans Mountain must delay NDE of final tie-in welds (i.e.: welds which will not be subjected to hydrostatic testing) and any repairs to them <strong>for at least 48 hours following weld completion</strong>. Trans Mountain must include this requirement in the NDE specification of its Joining Program required by Condition 111.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 117 | <strong>Reporting on improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least</strong> <strong>2 years and 1 year prior to commencing operations</strong>, detailed updates for the company&rsquo;s review of its Emergency Management Program (toward meeting the requirements of Condition 124). This filing must include:<br />a) a summary of work undertaken to-date;<br />b) the approximate timing for completing remaining work; and<br />c) a summary of parties that were consulted (Condition 90) and how their comments and feedback were considered in improving the program.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 118 | <strong>Firefighting capacity at terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least 1 year prior to commencing operations at the terminals:</strong><br />a) the following information regarding developing appropriate firefighting capacity for a safe, timely, and effective response to a credible worst-case fire at the Westridge Marine Terminal and at the Edmonton, Sumas, and Burnaby Terminals:<br />i) an assessment of necessary resources and equipment, including an explanation of how the assessment was informed by Trans Mountain&rsquo;s terminal risk assessments;<br />ii) a summary of Trans Mountain&rsquo;s consultation with appropriate municipal authorities and first responders, that includes any issues or concerns raised regarding each municipality&rsquo;s respective firefighting capacity and how Trans Mountain has addressed or responded to them;<br />iii) a Firefighting Capacity Framework, informed by the assessment in i) and consultation in ii), and that includes a list of and timeline for completing key activities and milestones leading to the establishment of appropriate firefighting capacity; and<br />b) a plan for responding to a fire exceeding a credible worst case scenario.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 119 | <strong>Emergency Preparedness and Response Exercise and Training Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 1 year prior to commencing operations</strong>, an Emergency Preparedness and Response Exercise and Training Program for the pipeline; the Edmonton, Sumas, and Burnaby Terminals; and the Westridge Marine Terminal. The program&rsquo;s objective is to demonstrate the continual improvement of responder competencies (including control centre personnel) at all levels of the company to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type, including tank fires and earthquakes. The program must include the following:<br />a) a defined scope, other objectives in addition to those noted above, and program targets that address responder turn-over and ensure responders&rsquo; ongoing training and practice;<br />b) a list of mandatory courses for responders;<br />c) a discussion of how Trans Mountain will train its personnel to respond to all hydrocarbon spill scenarios in various seasons, including releases of hydrocarbons in mountain regions during winter conditions, into ice covered watercourses, into watercourses under varying flow conditions and into waterbodies (aquifers or streams)that are used as municipal water supply sources;<br />d) a description of, and schedule for, all emergency response exercises (full-scale, tabletop, drills, functional) that Trans Mountain will conduct prior to operations to test a variety of scenarios;<br />e) a plan, including rationales, for determining the schedule and frequency of all emergency response exercises (full-scale, tabletop, drills, functional) to test a variety of scenarios during the Project&rsquo;s operational life;<br />f) a discussion of how emergency response exercises will meet the objectives of testing Trans Mountain&rsquo;s:<br />i) emergency response procedures;<br />ii) company personnel training;<br />iii) communications systems;<br />iv) response equipment;<br />v) safety procedures; and<br />vi) the effectiveness of its liaison and continuing education programs;<br />g) a learnings implementation plan for exercises that considers how Trans Mountain will update and amend its Emergency Response Plans and related documents following exercises. The learnings implementation plan must consider three main purposes:<br />i) to validate plans;<br />ii) to develop Trans Mountain responder competencies (including control centre personnel) and provide them with the opportunity to carry out and understand their roles in emergency response; and<br />iii) to test Project-specific emergency response procedures;<br />h) a plan for addressing the training requirements contained within the <em>National Energy Board Onshore Pipeline Regulations</em>; and<br />i) confirmation that an independent third party has reviewed and assessed the Emergency Preparedness and Response Exercise and Training Program and that Trans Mountain has considered and incorporated the comments generated by that review and assessment into the program.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 120 | <strong>Notification and reporting on emergency response exercises</strong><br />For any tabletop, functional, and full-scale emergency response exercises undertaken as part of its Emergency Preparedness and Response Exercise and Training Program required by Condition 119:<br />a) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>at least 45 days prior to the date of each exercise</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />b) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after</strong> <strong>completing each</strong> <strong>full-scale exercise</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement; and<br />iii) steps to be taken to correct deficiencies.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 121 | <strong>Financial Assurances Plan &ndash; operations phase</strong><br />a) Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to applying for leave to open Line 2,</strong> a Financial Assurances Plan that includes details of the financial resources and secured sources of funds that will be necessary to pay, without limitation, all actual loss or damage, costs and expenses, including cleanup and remediation, and loss of non-use value relating to non-use of a public resource associated with an unintended or uncontrolled release from the Project during the operations phase.<a href=http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn1">[1]</a> These costs may arise from, among other things, potential accidents, malfunctions, and failures during the Project operations phase, including all spills originating from the pipeline and the terminals.<br />The Financial Assurances Plan must be signed by an officer of the company, verifying that it is accurate, complete, and, at a minimum, meets the criteria and coverage levels described below:<br />i) Criteria for financial assurance instruments and plan:<ol><li>Any letter of credit that forms part of the Financial Assurances Plan must be unconditional and irrevocable, segregated from Trans Mountain&#39;s day-to-day business activities, and be dedicated to providing funds to cover the costs described in sub a) above, without limitation.</li><li>Third party liability insurance must be current, and broad, respecting the scope of environmental damages covered by the policy; the policy will be consistent with provisions available in the insurance market(i.e., only exceptional/non-standard perils, taking into account the Project&#39;s nature and scope, would be excluded from coverage). Such insurance must be structured on a multi-year basis, recognizing potential loss of income by persons sustaining damage caused by Trans Mountain, over a reasonable number of years after the event.</li><li>A portion of cash reserves or a portion of future cash flows of the Project may be included as instruments in the Financial Assurances Plan, provided they are secured by a commitment letter from an officer of the company confirming that the funds will be dedicated to the Financial Assurances Plan without restrictions for the period specified by the officer.</li><li>Parental and other third party guarantors must be registered within a Canadian jurisdiction and must have financial strength that is demonstrated in balance sheet values and ratios and credit ratings. For example, total assets less total liabilities of the guarantor should be several multiples of the liability assumed in the Trans Mountain guarantee.</li></ol>ii) Financial assurance components and coverage levels:<br />Trans Mountain&#39;s Financial Assurances Plan must provide a total coverage, for the Project as a whole, of $1.1 billion<a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftn2">[2]</a> for the costs described in sub a) above, without limitation. The plan should include the following components and minimum coverage levels:<ol><li>Ready cash: Trans Mountain must have unfettered access to at least $100 million to cover costs, including compensation to third parties for losses and damages in the near term, while insurance claims are being processed. Once used, this source of cash must be replenished immediately to cover the costs of a potential future spill. This can be in the form of a letter of credit, surety bond or other form acceptable to the NEB.</li><li>Core coverage: Trans Mountain must put in effect and maintain current at all times a core financial coverage of at least $1 billion that includes third party liability insurance and other financial assurance instruments that comply with the criteria. Core coverage must be a portfolio approach with multiple financial instruments used and may not be composed of a single financial instrument (e.g., only third party liability insurance). At least one component of core coverage must be funds that are readily accessible to Trans Mountain (e.g., cash reserves held by the general partner and not distributed to the limited partners).<br />Trans Mountain may use a number of financial and insurance instruments in its Financial Assurances Plan. However, sales of Project assets used for transporting hydrocarbon commodities will not be eligible candidates.&nbsp; Below are some illustrative financial and insurance instruments that could be potential candidates for the Financial Assurances Plan:</li></ol><ul><li>Irrevocable, unfettered letter of credit.</li><li>Secured line of credit.</li><li>Cash reserves held by the general partner and not distributed to the limited partners (and verifiable on Trans Mountain Pipelines Limited Partnership&#39;s balance sheet).</li><li>Internal cash flow, committed by Trans Mountain to financial assurances.</li><li>Industry pooled fund.</li><li>Third party liability insurance with exclusions for only exceptional/non-standard perils.</li><li>No fault third party liability insurance.</li><li>Parental and other third party guarantees provided by parties demonstrating financial strength through balance sheets and credit ratings.</li><li>Other instruments developed by Trans Mountain and the insurance and financial markets.</li></ul>b) Trans Mountain must file the following with the NEB:<br />i) <strong>At least 6 months prior to applying for leave to open Line 2</strong>, a report from an independent third party that has assessed the Financial Assurances Plan and its key components against the criteria and actual experiences of industry damage claims. The report must summarize the key features of each financial and insurance instrument proposed for inclusion in the Financial Assurances Plan.<br />ii) <strong>At least 3 months prior to applying for leave to open Line 2</strong>, a supplement to the report described in b)i) that provides verification of any third party liability insurance coverage, a copy of the insurance certificate, and a summary of the insurance policy&#39;s key features. This summary must include: limits on insurance coverage, deductible amounts, the risks and perils and properties covered by the insurance policy, the exclusions from coverage, Trans Mountain&#39;s obligations, effective dates, and names of insurers and reinsurers.<br />iii) <strong>With its first leave to open application for Line 2</strong>, a report describing the steps it took to eliminate any deficiencies in its Financial Assurances Plan that were identified in the independent third party report referenced in b)i) and the NEB&#39;s subsequent review.<br />iv) <strong>On or before 31 January of each year after commencing operations</strong>, a letter signed by an officer of the company verifying that all components of the Financial Assurances Plan remain as the NEB approved and sufficient to meet the financial assurance coverage levels described in ii).<br />v) <strong>At least 2 months prior to any intended change(s) to the Financial Assurances Plan during the Projects operations phase</strong>, a letter, for approval, detailing the intended change(s) and how the change(s) provides the same or greater level of protection.<br />vi) <strong>Within 30 days after accessing any component of the Financial Assurances Plan</strong>, a report detailing the component accessed, the reason for accessing it, and Trans Mountain&rsquo;s plan to ensure that it continues to meet the requirements of its NEB-approved Financial Assurances Plan.<br />&nbsp;<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref1">[1]</a> &nbsp;&nbsp;&nbsp; In the context of this condition, &ldquo;operations phase&rdquo; refers to the period after the Project receives leave to open approval and prior to it being fully abandoned.<br /><a href="http://iapps/ERS/Internal/CMConditionHeader/Create?instrumentId=86753cbc-a8e3-4871-8c14-d55b382cf72f#_ftnref2">[2]</a> &nbsp;&nbsp;&nbsp; The NEB&rsquo;s basis for any final coverage level is described in its report to Governor in Council." | In Progress | During Construction Phase | Standard | Filing Not Required | Financial
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 123 | <strong>Evacuation Plans</strong><br />a) Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing operations at the terminals</strong>, an Evacuation Plan for people present in areas potentially affected by an incident at each of Trans Mountain&rsquo;s Edmonton, Sumas, and Burnaby Terminals as well as at the Westridge Marine Terminal. Each Evacuation Plan must, at a minimum:<br />i) describe how areas for evacuation were determined;<br />ii) describe the circumstances under which evacuation may be required, as well as the respective methods and procedures for public notification;<br />iii) describe specific evacuation routes, methods, and destinations;<br />iv) be prepared in consultation with Appropriate Government Authorities, first responders and potentially affected Indigenous groups with the authority to issue evacuation or shelter in place orders during an emergency;<br />v) state how input from Appropriate Government Authorities, first responders and potentially affected Indigenous groups, with the authority to issue evacuation or shelter in place orders during an emergency, was considered in preparing the plan;<br />vi) define the roles, responsibilities, and jurisdictional authority of all parties involved in implementing an evacuation; and<br />vii) confirm that an independent third party has reviewed and assessed the plan and that Trans Mountain has considered and incorporated comments generated by the review and assessment into the plan.<br />b) Trans Mountain must include with its Evacuation Plan for the Burnaby Terminal, a plan specific to Simon Fraser University that includes the requirements in a) i) to vii), above.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 124 | <strong>Implementing improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing operations</strong>, a detailed summary of its review of its Emergency Response Plans (as noted in Conditions 125 and 126) and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing <a href=https://docs.neb-one.gc.ca/ll-eng/llisapi.dll/fetch/2000/90464/90552/548311/956726/2392873/2451003/2393783/B18-1_-_V7_1.0_TO_5.2.8.3_RISK_ASSESS_MGMT_SPILLS_-_A3S4V5.pdf?nodeid=2393784&amp;vernum=-2">A3S4V5</a>). This filing must include a description of changes made to Trans Mountain&rsquo;s Emergency Management Program, as required under the <em>National Energy Board Onshore Pipeline Regulations</em>, including changes to:<br />a) the Pipeline Emergency Response Plan;<br />b) Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals, as well as the Westridge Marine Terminal; and<br />c) site-specific plans and documents related to a) and b), such as Geographic Response Plans, Geographical Response Strategies, control point mapping, tactical plans for submerged and sunken oil and tactical plans for high consequence areas.<br />The summary must demonstrate Trans Mountain&rsquo;s ability to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type and in any geographic region or season and must include the following:<br />i) a discussion of how the updated plans conform to the requirements contained within the <em>National Energy Board Onshore Pipeline Regulations</em>;<br />ii) a discussion of how the plans consider, and would allow coordination with relevant federal, provincial, municipal and Indigenous community emergency response plans;<br />iii) a discussion of how the results of research initiatives, such as the Scientific Advisory Committee work noted in Trans Mountain&rsquo;s response to NEB Information Request No. 1.63 (Filing <a href="https://docs.neb-one.gc.ca/ll-eng/llisapi.dll/fetch/2000/90464/90552/548311/956726/2392873/2451003/2454322/B32-2_-_Trans_Mountain_Response_to_NEB_IR_No._1_1_of_2_-_A3W9H8.pdf?nodeid=2456419&amp;vernum=-2">A3W9H8</a>) and other research noted during the OH-001-2014 proceeding, have been considered and incorporated into Trans Mountain&rsquo;s emergency response planning;<br />iv) a description of the models used in response planning, including oil trajectory, fate and behavior, and air dispersion models; and<br />v) confirmation that an independent third party has reviewed and assessed the Emergency Response Plans and that Trans Mountain has considered and incorporated the comments generated by the review and assessment into the plans.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)" | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 125 | <strong>Emergency Response Plans for the Pipeline and for the Edmonton, Sumas and Burnaby Terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least&nbsp; 6 months prior to commencing operations</strong>, updated Emergency Response Plans which must include:<br />a) the following relevant emergency preparedness and response documents:<br />i) an Emergency Response Plan to include the pipeline expansion;<br />ii) updated Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals; and<br />iii) all related and accompanying site-specific plans and documents, such as control point mapping, Geographic Response Plans, tactical response plans, volunteer management plans, and fire safety plans;<br />b) an emergency response and preparedness table for the pipeline (including facilities) indicating which plans and documents referenced in a) will be referred to in an emergency response for each 10-kilometre-long pipeline segment. For each pipeline segment, the table must also identify, at a minimum:<br />i) high consequence areas, including environmentally sensitive areas (e.g. wetlands), heritage sites and water supply wells (Condition 93);<br />ii) potentially affected persons or groups;<br />iii) available access to the right-of-way and high consequence areas;<br />iv) nearest control point(s);<br />v) nearest available equipment cache(s);<br />vi) response times for deployment of equipment and Trans Mountain personnel, mutual aid personnel, and third party contractors;<br />vii) the available equipment and trained personnel, whether employed by Trans Mountain, contracted, or available through mutual aid (including contact information); and<br />viii) geological, meteorological, and geographical hazards (e.g., snow avalanche, mud slides, rock slides, and steep slopes); and<br />c) maps depicting the information identified in b).(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 127 | <strong>Terminal fire protection and firefighting systems</strong><br />a) Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to applying for leave to open of any Project component at each respective terminal</strong>, an independent third party report confirming the adequacy of the proposed fire protection and firefighting systems implemented or planned to be implemented at the Edmonton Terminal West Tank Area, the Burnaby Terminal, the Sumas Terminal, and the Westridge Marine Terminal. The report must demonstrate that the resources and firefighting systems are capable of suppressing fires associated with all scenarios identified in the above-mentioned terminals&rsquo; final risk assessments (required by Condition 129).<br />b) Trans Mountain must file with the NEB for approval, <strong>at least 2 months prior to beginning the assessment leading to the report in a),</strong> the name and qualifications of the proposed independent third party that will prepare the report in a). | Closed | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 129 | <strong>Final terminal risk assessments</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to applying for leave to open for each terminal</strong>, final risk assessments for the Edmonton Terminal West Tank Area, the Sumas Terminal, the Burnaby Terminal, and the Westridge Marine Terminal, respectively, including all implemented mitigation measures. Trans Mountain must demonstrate in each risk assessment that mitigation measures will reduce the risks to levels that are ALARP while complying with the MIACC criteria for risk acceptability. The Edmonton Terminal West Tank Area, Sumas Terminal, and Burnaby Terminal must include the elements listed in Condition 22.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 130 | <strong>Groundwater Monitoring Program</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing operations</strong>, a Groundwater Monitoring Program that pertains to all terminals and pump stations, and for any vulnerable aquifers along the pipeline route. The&nbsp; program must include, at a minimum:<br />a) locations of groundwater monitoring wells, their depths, the rationales for well locations (including how groundwater flow direction was considered), groundwater flow velocity, parameters to be monitored and frequency of monitoring;<br />b) a description of any program changes required to meet this condition for facilities with an existing Groundwater Monitoring Program;<br />c) methods, criteria and rationale for identifying vulnerable aquifers along the pipeline route;<br />d) applicable regulatory criteria for comparing monitoring results, and a process outlining what steps will be followed should monitoring results indicate a negative change in groundwater quality;and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the program.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 136 | <strong>Pre-operations full-scale emergency response exercises</strong><br />a) <strong>Prior to commencing operations</strong>, Trans Mountain must complete a full-scale exercise for each of the following scenarios:<br />i) a 160-cubic-metre diluted bitumen release into Burrard Inlet as a result of a release from the Westridge Marine Terminal. The exercise must also consider emergency preparedness and response planning for a release that exceeds a credible worst case scenario spill event; and<br />ii) a credible worst-case release volume at the Burnaby Terminal.<br />b) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders, and potentially affected Indigenous groups,<strong> at least 45 days prior to the date of each exercise in a)</strong>, of:<br />i) the exercise&rsquo;s date(s) and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />c) Trans Mountain must file with the NEB and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after completing each exercise in a)</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement;<br />iii) steps to be taken to correct deficiencies; and<br />iv) confirmation that an independent third party has evaluated and assessed the emergency response exercises and that Trans Mountain will consider the comments generated for future exercises.(a)) a)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(b)) b)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(c)) c)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 137 | <strong>Tank roof design for tanks at the Edmonton Terminal</strong><br />Trans Mountain must install steel pontoon internal floating roofs and fixed roofs with odour control systems on all of its five proposed tanks at the Edmonton Terminal. Trans Mountain must file with the NEB, <strong>at least</strong> <strong>30 days prior to applying for leave to open the five proposed tanks, </strong>a letter signed by an officer of the company that confirms that these roofs were installed.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 138 | <strong>Confirmation of firefighting capacity at terminals</strong><br />Trans Mountain must file with the NEB, <strong>at least 30 days prior to commencing operations at the terminal</strong>, confirmation that appropriate firefighting capacity, in accordance with Condition 118, is in place.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 140 | <strong>Post-construction greenhouse gas (GHG) assessment report</strong><br />Trans Mountain must file with the NEB for approval, <strong>within</strong> <strong>2 months after commencing operations</strong>, an updated GHG assessment report specific to the Project. The report must include:<br />a) the methodology used for the assessment, including the sources of GHG emissions, assumptions, and methods of estimation;<br />b) the total direct GHG emissions generated from Project construction, including land-clearing;<br />c) a breakdown of direct GHG emissions generated by the construction of individual Project components (pipeline, pump stations, tank terminals and Westridge Marine Terminal) and by land-clearing activities; and<br />d) a comparison and discussion of the direct GHG emissions calculated in b) with the predicted emissions in Trans Mountain&rsquo;s application and subsequent submissions.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 141 | <strong>Post-construction noise surveys</strong><br />Trans Mountain must file with the NEB, <strong>within 3 months after commencing operations, </strong>the results of post-construction noise surveys conducted at the Sumas and Burnaby Terminals and at the Westridge Marine Terminal, demonstrating compliance with the British Columbia Oil and Gas Commission&rsquo;s <em>British Columbia Noise Control Best Practices Guideline (2009)</em>, and any further mitigation that Trans Mountain will undertake to achieve compliance.(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 142 | <strong>GHG Emissions Offset Plan &ndash; Project construction</strong><br />Trans Mountain must file with the NEB for approval, <strong>within 4 months after commencing operations</strong>, a plan for providing offsets for all direct GHG emissions generated from Project construction, as determined in Condition 140. The plan must include:<br />a) a list and discussion of all possible offset options considered;<br />b) the criteria against which each option was assessed for viability;<br />c) a description of the offset option(s) selected for direct GHG emissions generated from Project construction, and the rationale for selecting the option(s);<br />d) confirmation that the selected offset option is registered under the approved quantification protocols and has been verified by an accredited &ldquo;verification body&rdquo; ;<br />e) a schedule indicating when the selected offset options(s) will be initiated; and<br />f) an accounting of offsets confirming no net GHG emissions from Project construction.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 146 | <strong>Reports on engagement with Indigenous groups &ndash; operations</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January of each of the first 5 years after commencing operations,</strong> a report on the engagement activities it has undertaken with Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;<br />b)&nbsp; the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 147 | <strong>Natural hazard assessment</strong><br />Trans Mountain must file with the NEB, <strong>within 1 year after commencing operations</strong>:<br />a) the results of the baseline natural hazard assessment for the Project; and<br />b) confirmation that the natural hazard assessment will be:<br />i) updated at intervals not exceeding 5 years; and<br />ii) integrated into the existing Natural Hazard Management Program for the Trans Mountain Pipeline system.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up, </strong>a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants.<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />i) an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />ii) a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />iii) an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 153 | <strong>Full-scale emergency response exercises during operations</strong><br /><strong>a) Within 5 years after commencing operations</strong>, Trans Mountain must complete full-scale exercises to test each of the following five scenarios:<br />i) a full-bore rupture under ice and snow conditions in the Coquihalla Mountain Range;<br />ii) a full-bore rupture into the Athabasca River during high spring flow conditions;<br />iii) a full-bore rupture into Fraser River at the Port Mann Bridge, under peak flow conditions;<br />iv) a full-bore rupture into the North Thompson River during high spring flow conditions; and<br />v) a tank fire at the Burnaby Terminal.<br />b) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups <strong>at least 45 days prior to the date of each exercise in a)</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.<br />c) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after completing each exercise in a)</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement;<br />iii) steps to be taken to correct deficiencies; and<br />iv) confirmation that an independent third party has evaluated and assessed the emergency response exercises and that Trans Mountain will consider the comments generated for future exercises.(a)) <strong>Within 5 years after commencing operations</strong>, Trans Mountain must complete full-scale exercises to test each of the following five scenarios:<br />i) a full-bore rupture under ice and snow conditions in the Coquihalla Mountain Range;<br />ii) a full-bore rupture into the Athabasca River during high spring flow conditions;<br />iii) a full-bore rupture into Fraser River at the Port Mann Bridge, under peak flow conditions;<br />iv) a full-bore rupture into the North Thompson River during high spring flow conditions; and<br />v) a tank fire at the Burnaby Terminal.(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(b)) Trans Mountain must notify the NEB and all potential exercise participants and observers, including Appropriate Government Authorities, first responders and potentially affected Indigenous groups <strong>at least 45 days prior to the date of each exercise in a)</strong>, of:<br />i) the exercise&rsquo;s date and location(s);<br />ii) the exercise&rsquo;s objectives;<br />iii) the participants in the exercise; and<br />iv) the scenario for the exercise.(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(c)) Trans Mountain must file with the NEB, and provide to Appropriate Government Authorities, first responders and potentially affected Indigenous groups, <strong>within 3 months after completing each exercise in a)</strong>, a report on the exercise that includes:<br />i) the results of the completed exercise;<br />ii) areas for improvement;<br />iii) steps to be taken to correct deficiencies; and<br />iv) confirmation that an independent third party has evaluated and assessed the emergency response exercises and that Trans Mountain will consider the comments generated for future exercises.(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Emergency Management, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 155 | <strong>Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Rare Ecological Community and Rare Plant Population Mitigation Evaluation Report and Offset Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the <em>Species at Risk Act</em>, that includes:<br />a) an evaluation of avoidance and mitigation success with reference to the measurable goals outlined in the Rare Ecological Community and Rare Plant Population Management Plan required by Condition 40;<br />b) identification of communities, species, and critical habitats that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />c) identification of any ongoing effects to ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, or on any early draft, candidate, proposed, or final critical habitat under the <em>Species at Risk Act</em>;<br />d) for the ongoing effects identified in c), a Final Rare Ecological Community and Rare Plant Population Offset Plan that updates the Preliminary Rare Ecological Community and Rare Plant Population Offset Plan required by Condition 40, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />e) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />f) a summary of its consultations with Appropriate Government Authorities, any species experts and potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 156 | <strong>Wetland Reclamation Evaluation Report and Offset Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>on or before 31 January after the fifth complete growing season after completing final clean-up</strong>, a Wetland Reclamation Evaluation Report and Offset Plan that includes:<br />a) the extent (in hectares), by wetland type, that was impacted by Project construction and associated activities;<br />b) for each wetland impacted, an evaluation of mitigation and reclamation success with reference to the measurable goals outlined in the Wetland Survey and Mitigation Plan required by Condition 41;<br />c) identification of any wetlands that have not yet achieved the intended degree of reclamation success, and an evaluation of the need for ongoing monitoring, reporting and corrective actions;<br />d) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, an evaluation of any temporary or ongoing loss of any individual functional condition (e.g., habitat, hydrology and biogeochemistry);<br />e) for any wetland that has not achieved reclamation success in terms of overall wetland function, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition, a Final Wetland Offset Plan that updates the Preliminary Wetland Offset Plan required by Condition 41, and that also includes details with rationales on the amount and type of offsets required, the offset measures to be implemented, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the report/plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 2 | ?<strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 22 | <strong>Updated terminal risk assessments</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, <strong>and at the same time as Trans Mountain&rsquo;s filings for Conditions 23, 24 and 25</strong>, updated risk assessments for the Edmonton Terminal West Tank Area, the Sumas Terminal, and the Burnaby Terminal. The updated risk assessments must quantify and/or include the following:<br />a) the effect of any revised spill burn rates;<br />b) the potential consequences of a boil-over;<br />c) the potential consequences of flash fires and vapour cloud explosions;<br />d) the cumulative risk based on the total number of tanks in the terminal, considering all potential events (pool fire, boil-over, flash fire, vapour cloud explosion);<br />e) the domino (knock-on) effect caused by a release of the contents of one tank on other tanks within the terminal&rsquo;s common impoundment area(s), or other tanks in adjacent impoundment areas; and<br />f) risk mitigation measures, including ignition source control methods.<br />&nbsp;<br />For those risks that cannot be eliminated, Trans Mountain must demonstrate in each risk assessment that mitigation measures will reduce the risks to levels that are ALARP while complying with the Major Industrial Accidents Council of Canada (MIACC) criteria for risk acceptability.<br />The quantitative risk analysis must be based on recognized methodology, models, and software. Product release frequencies and event probabilities must be based on recent, documented data sources. The effect of mitigation measures on the risk results must be justified and documented(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 23 | <strong>Secondary containment &ndash; Edmonton Terminal</strong><br />Trans Mountain must file with the NEB <strong>for approval</strong>, <strong>at least 6 months prior to commencing construction</strong>, the final design of the Edmonton Terminal West Tank Area, including a report demonstrating the following:<br />a) the drainage system&rsquo;s capability to rapidly and safely channel a significant release from any tank in the West Tank Area Common Impoundment to the Remote Impoundment Annex and Remote Impoundment at the same time that a design precipitation event is occurring, without overtopping the diked areas;<br />b) the adequacy of the design in mitigating the following consequences of an accidental release and/or ignition of hydrocarbons, both within and beyond the Edmonton Terminal property boundary:<br />&nbsp; &nbsp; &nbsp;i) harm to personnel and the public;<br />&nbsp; &nbsp; &nbsp;ii) environmental damage; and<br />&nbsp; &nbsp; &nbsp;iii) damage to facilities; and<br />c) the ability of the Common Impoundment, Remote Impoundment Annex, and Remote Impoundment to contain a release of hydrocarbons from a rupture of the largest tank within the West Tank Area concurrent with a 1-in-100 year, 24-hour storm event. The scenario must include an allowance for water generated from potential firefighting activities and the maximum potential amount of standing water in all areas of the secondary containment system.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 24 | <strong>Secondary containment &ndash; Burnaby Terminal</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction, </strong>the final design of the Burnaby Terminal, including a report demonstrating the following:<br />a)&nbsp;the drainage system&rsquo;s capability to rapidly and safely channel a significant release from either Tank&nbsp;96, 97, or 98 to the Partial Remote Impoundment at the same time that a design precipitation event is occurring, without overtopping the diked areas;<br />b)&nbsp;the adequacy of the proposed design in mitigating the following consequences of an accidental release and/or ignition of hydrocarbons, both within and beyond the Burnaby Terminal property boundary:<br />&nbsp; &nbsp; &nbsp;i)&nbsp;harm to personnel and the public;<br />&nbsp; &nbsp; &nbsp;ii) environmental damage; and<br />&nbsp; &nbsp; &nbsp;iii)&nbsp;damage to facilities; and<br />c) the ability of the individual secondary containment areas, Common Impoundment areas, Intermediate Stormwater Retention, Partial Remote Impoundment, and Tertiary Containment to contain a release of hydrocarbons from a multiple-tank rupture scenario concurrent with a 1-in-100 year, 24-hour storm event. The scenario must include an allowance for water generated from potential firefighting activities and the maximum potential amount of standing water in all areas of the secondary containment system. The assessment may include a calculation of the probability of exceedance of on-site containment considering all possible tank rupture combinations, excluding those tanks with sufficient individual secondary containment. The calculation may be based on a tank utilization histogram most representative of the expanded terminal operations, similar to that provided in Attachment 1 of Trans Mountain&rsquo;s response to NEB Information Request No. 4.24a) (Filing <a href=https://docs.neb-one.gc.ca/ll-eng/llisapi.dll/fetch/2000/90464/90552/548311/956726/2392873/2451003/2759257/B371-12_-_Trans_Mountain_Response_to_NEB_IR_No._4.24a-Attachment_1_-_A4K4X3.pdf?nodeid=2759477&amp;vernum=-2">A4K4X3</a>).(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)" | Closed | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 25 | <strong>Secondary containment &ndash; Sumas Terminal</strong><br />Trans Mountain must file with the NEB <strong>for approval</strong>, <strong>at least 6 months prior to commencing construction</strong>, the final design of the Sumas Terminal, including a report demonstrating the following:<br />a) the adequacy of the proposed design in preventing the following consequences of an accidental release and/or ignition of hydrocarbons, both within and beyond the Sumas Terminal property boundary:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) harm to personnel and the public;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) environmental damage; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) damage to facilities; and<br />b) the ability of the secondary containment system to contain a release of hydrocarbons from a multiple-tank rupture scenario concurrent with a 1-in-100 year, 24-hour storm event. The scenario must include an allowance for water generated from potential firefighting activities and the maximum potential amount of standing water in all areas of the secondary containment system. The assessment may include a calculation of the probability of exceedance of on-site containment considering all possible tank rupture combinations, excluding those tanks with sufficient individual secondary containment. The calculation may be based on a tank utilization histogram most representative of the expanded terminal operations, similar to that provided in Attachment 1 of Trans Mountain&rsquo;s response to NEB Information Request No. 4.24b) (Filing A4K4X4).(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 30 | <strong>Power system protection for pump stations and terminals</strong><br />Trans Mountain must file with the NEB the following details of its electrical power system design for each pump station and each of the following: Westridge Marine Terminal, Burnaby Terminal, Edmonton Terminal, and Sumas Terminal:(a)) Descriptions of the overcurrent and ground fault protection schemes including:(i)) a summary of coordination studies between the upstream and downstream protective devices, <strong>at least 3 months prior to commencing dry commissioning</strong>;(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)<br />&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(ii)) relay settings and time-current curves, <strong>at least 3 months prior to commencing dry commissioning;</strong>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)<br />&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(iii)) the specification of neutral grounding resistors, <strong>at least 6 months prior to commencing construction</strong>;(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)<br />&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(iv)) specifications of contactors, fuses, and circuit breakers, <strong>at least 6 months prior to commencing construction</strong>; and(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)<br />&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(v)) a description of other electrical protections, relay settings, and trip characteristics, <strong>at least 3 months prior to commencing dry commissioning.</strong>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)<br />&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(b)) Consistent with the NEB&rsquo;s Safety Advisory SA-2015-03, dated 4 May 2015,&nbsp;<strong>at least 6 months prior to commencing construction</strong>, information confirming that Trans Mountain has performed the ground fault and arcing fault protection designs for each pump station and terminal, including:<br /><br />i) a means to clear ground faults without intentional time delay if the fault currents exceed the design limit set by the neutral grounding resistance; and<br />ii) a means to block the stored energy from other running motors from feeding an electrical fault in another motor running from the same bus.<br /><br />This filing must include a description of the ground fault and arcing fault protection designs including the above measures.&nbsp; &nbsp; &nbsp; &nbsp;(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(c)) <strong>At least 6 months prior to commencing construction</strong>, either:&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br /><br />i) a written confirmation that Trans Mountain determined during detailed design that electrical faults will not exceed their design limits and migrate to an arcing fault; or<br />ii) for a station or a terminal for which Trans Mountain determined during detailed design that an electrical fault could exceed its design limit and migrate to an arcing fault, the electrical configuration of that station or terminal and the additional equipment and devices that will be used to mitigate the adverse effects of such arcing faults.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(d)) Single-line diagrams of the electrical power systems<strong>, at least 6 months prior to commencing construction</strong>.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 32 | <strong>Sumas Terminal Geotechnical Report</strong><br />Trans Mountain must file with the NEB, <strong>at least 6 months prior to commencing construction at the Sumas Terminal</strong>, a geotechnical report that provides feasibility-level geotechnical design recommendations for the proposed expansion at the Sumas Terminal.(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 40 | <strong>Rare Ecological Community and Rare Plant Population Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, an updated Rare Ecological Community and Rare Plant Population Management Plan for ecological communities of concern, rare plants and lichens, and early draft, candidate, proposed, or final critical habitat for plant and lichen species under the Species at Risk Act, that are potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results, and a demonstration of the overall adequacy of the rare ecological community and rare plant surveys, including the adequacy for the identification of biophysical attributes for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act;<br />b) avoidance and mitigation measures to be implemented during construction and operations, including all relevant measures committed to throughout the OH-001-2014 proceeding and any new measures resulting from supplementary surveys, with rationales and unambiguous criteria explaining under what circumstances each measure will be applied, and measurable goals against which the success of each measure will be evaluated;<br />c) a description of how the avoidance, mitigation, and offset hierarchy was considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />d) details on post-construction monitoring, including survey methods, the appropriate number of years of monitoring to determine the success of each type of avoidance and mitigation measure, corrective actions that might be necessary, and the circumstances under which each such action would be taken;<br />e) a Preliminary Rare Ecological Community and Rare Plant Population Offset Plan for any ecological communities and rare plant and lichen species that have an at-risk status of S1, S1S2 or S2, or that are listed under federal or provincial legislation for protection, and for any early draft, candidate, proposed, or final critical habitat under the Species at Risk Act, and that, after five years of operations, have ongoing effects. This preliminary plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) a rationale for why the community, species, or critical habitat cannot be avoided by a sufficient distance to avoid both direct and indirect residual effects;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the expected residual effects on that community, species, or critical habitat, including a discussion of the potential for time lags &nbsp;between when Project effects occur and when mitigation measures would become fully functional, and taking into account the success on past projects of the proposed mitigation and corrective measures in b) and d) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an analysis of the appropriateness of offsets for the community, species or critical habitat, taking their specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of how the avoidance, mitigation, monitoring, corrective and offset measures are consistent with any applicable recovery, action or management strategies or plans for the community, species or critical habitat;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vii) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />g) a summary of its consultations with Appropriate Government Authorities, any species experts and any potentially affected Indigenous groups. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Rare Ecological Community and Rare Plant Population Management Plan, including confirmation that the avoidance, mitigation, monitoring, corrective, and offset measures in the Rare Ecological Community and Rare Plant Population Management Plan will be implemented to the extent feasible in the case of discovery via their inclusion in the Rare Ecological Communities or Rare Plant Species Discovery Contingency Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 41 | <strong>Wetland Survey and Mitigation Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 5 months prior to commencing construction</strong>, a pre-construction Wetland Survey and Mitigation Plan for wetlands potentially affected directly or indirectly by the Project during construction or operations, that includes:<br />a) a summary of supplementary survey results and a demonstration of the overall adequacy of the wetland surveys;<br />b) a description of any wetlands for which ground-based surveys were not possible, an explanation as to why not, attempts made to obtain access, and what further information on each wetland will be collected immediately prior to or during construction;<br />c) a description of the functional condition of each wetland for comparison during post-construction monitoring, including individual functional conditions (e.g., habitat, hydrology and biogeochemistry, including the presence and abundance of migratory birds and species at risk), and a description of the methods used to determine the type and amount of each individual wetland function and the overall functional condition;<br />d) a description of the crossing methods, mitigation measures and reclamation measures to be implemented during construction and operations, with rationales and unambiguous criteria explaining under what circumstances each such method and measure will be applied;<br />e) measurable goals against which the success of wetland mitigation and reclamation will be evaluated, including a description of how such goals incorporate the aim of returning wetlands to their original functionality while allowing for reasonable natural variation, and including measurable goals for each of the first-, third- and fifth-year post-construction monitoring reporting stages for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies;<br />f) a description of how the<br />&nbsp;&nbsp;&nbsp;&nbsp; i) avoidance, mitigation, and offset hierarchy; and<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the goal of no-net-loss of wetland function, were considered in developing the plan, with rationales for progressing from avoidance to mitigation to offsets;<br />g) details of the post-construction monitoring plan for wetlands for the first five years of operations, including corrective actions that might be necessary and the circumstances under which each such action would be taken;<br />h) a Preliminary Wetland Offset Plan for any wetland that has not achieved reclamation success in terms of overall wetland function after five years of operations, and for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies and that has had a temporary or ongoing loss in any individual functional condition &ndash; this plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the expected residual effects on the wetland, including a discussion of the potential for time lags between when Project effects occur and when mitigation measures would become fully functional, taking into account the success on past projects of the proposed mitigation, reclamation and corrective measures in d) and g) above;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) an analysis of the appropriateness of offsets for the wetland, taking its specific features into account, and of any potential limitations on offset effectiveness;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) an explanation with rationales of how the need for offset measures will be determined and how quantitative offset objectives will be developed, including the use and selection of offset ratios and indicator species, with the aim of achieving no-net-loss;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) the potential types of offset measures, the process for selecting which will be implemented, an estimation of the probability of their success, and how compensation sites will be selected;<br />&nbsp;&nbsp;&nbsp;&nbsp; v) a discussion of how the effectiveness of offset measures will be monitored, assessed, and reported on, and problems corrected; and<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) for any wetland to which no-net-loss under the Federal Policy on Wetland Conservation applies, details with rationales on the offset measures that will be implemented before or during the first five years of operations to compensate for expected temporary or ongoing losses to individual functional conditions, including the amount and type of offsets required, the selection of compensation sites, identification of the parties involved in planning and implementation and their respective roles and responsibilities, a timeline for implementation, and the methods and schedule for monitoring and reporting to demonstrate offset success;<br />i) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information;<br />j) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />k) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Wetland Survey and Mitigation Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval,&nbsp;<strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 54 | <strong>Fugitive Emissions Management Plan for Edmonton, Sumas and Burnaby Terminals</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction at each Terminal</strong>, a Fugitive Emissions Management Plan for the Edmonton, Sumas, and Burnaby Terminals. This plan must include:<br />a) a description of the fugitive emission sources within the terminals during construction and operations;<br />b) a description of the emission and odour controls that will be employed to reduce fugitive emissions from the tanks, and any other sources identified in a);<br />c) procedures for verifying the capture and destruction efficiency of tank vapour activation units or any other emission or odour control units at the terminals;<br />d) quantification of fugitive emissions during operations, including the methods used;<br />e) any additional mitigation measures that will be employed to further reduce the fugitive emissions;<br />f) a description of Trans Mountain&rsquo;s program for addressing complaints with respect to fugitive emissions, including a public and Indigenous communication and complaint response process; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 55 | <strong>Fugitive Emissions Management Plan for pump stations</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction at any pump stations</strong>, a Fugitive Emissions Management Plan for the pump stations associated with the Project that includes:<br />a) a description of the procedures implemented for leak detection and the criteria used in selecting target leaking components;<br />b) quantification methods considered and the rationale for the selected method(s);<br />c) monitoring frequency for each target leaking component and the parameters that will be measured;<br />d) a decision framework that will be implemented to repair or replace leaking components;<br />e) a description of record-keeping procedures; and<br />f) a discussion of additional mitigation measures that will be employed to minimize fugitive emissions. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 59 | <strong>Worker accommodation strategy</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a worker accommodation strategy, developed in consultation with appropriate municipal or provincial authorities. The strategy must include:<br />a) a final summary of all proposed accommodations, including the location of any temporary camp(s);<br />b) the number of workers that will be housed; and<br />c) a description of how the strategy addresses any concerns or requests raised in consultation with municipal or provincial authorities.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the event that temporary camp(s) are to be used, the strategy must also include:<br />i) a description of how the potential environmental and socio-economic impacts have been assessed, and a description of all associated mitigation measures;<br />ii) copies of, or reference to, any mitigation or operational plans that will be required or implemented for the camp(s), including a description of how Trans Mountain has incorporated any additional mitigation measures into relevant Environmental Protection Plan(s);<br />iii) copies of any necessary municipal or provincial permits for any camp(s) that have been received 3 months prior to construction. &nbsp;If camp permits are not yet in place 3 months prior to commencing construction, provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a list of the outstanding camp permits and a schedule for when these camp permits will be in place; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) copies of any outstanding camp permits prior to commencing construction;<br />iv) copies or excerpts of all policies relating to the rules of conduct for workers housed at the camp(s);<br />v) confirmation that all policies relating to the camp(s) will be provided to workers;<br />vi) confirmation that all policies relating to the camp(s) were made available to all local communities and other relevant service providers in proximity to any camp(s) that will be used for the Project; and<br />vii) a summary of its consultations with affected landowners/tenants where any camp(s) will be located. Trans Mountain must provide:<br />&nbsp;&nbsp;&nbsp;&nbsp; 1) a description of the information provided to landowners/tenants; and<br />&nbsp;&nbsp;&nbsp;&nbsp; 2) description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Strategy.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table and must:(a)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <div><strong>within 3 months after the [certificate/order] date</strong>;</div>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(ii)) <div><strong>at least 30 days prior to commencing construction;</strong></div>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(b) and c)) b) post on its company website the same information required by a),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />c) maintain at each of its construction offices:<ul><li>i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;</li><li>ii) copies of any permits, authorizations, and approvals referenced in i); and</li><li>iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).</li></ul> | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Phase 02 (terminal Edmonton)) For filings associated with Phase&nbsp;02 (terminal Edmonton)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 79 | <strong>Air Emissions Management Plan for the Edmonton, Sumas and Burnaby Terminals</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at each of the Edmonton, Sumas, and Burnaby Terminals</strong>, an Air Emissions Management Plan for each of those terminals that includes:<br />a) a description of the baseline, pre-construction conditions informed by relevant modelling results and recent existing monitoring data;<br />b) descriptions of the locations of air monitoring sites (on a map or diagram), including the rationale for the locations selected;<br />c)&nbsp; the timing for installing air monitoring stations;<br />d) the methods and schedule for monitoring ambient ground-level concentrations of potential concern (e.g., volatile organic compounds, ozone, hydrogen sulphide, mercaptans, criteria air contaminants, secondary ozone and particulate matter, and reduced visibility) and emissions source tracking;<br />e) procedures for monitoring station data recording, assessment, and reporting details, including a description of how the real time and non-continuous air quality monitoring data will be made available to the public;<br />f) a description of the public and Indigenous communication and complaint response process;<br />g)&nbsp; the criteria or thresholds that, if triggered or exceeded, will require implementing additional emissions reduction measures;<br />h) possible measures that will be implemented as a result of the monitoring data or ongoing concerns; and<br />i) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 8 | <strong>Design temperatures &ndash; terminals and pump stations</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 3 months prior to ordering pipe for terminals and pump stations</strong>, confirmation, with rationale, that:<br />a) the selected maximum and minimum design temperatures are in accordance with CSA Z662-15, Clause 5.2.1;<br />b) the selected design temperatures are based on historical, location-specific extreme daily maximum and minimum temperatures, as opposed to average temperatures; and<br />c) the extent of the historical weather data used is commensurate with the expected operational life of the Project.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 80 | <strong>Noise Management Plan for construction at terminals and pump stations</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at each terminal and pump station</strong>, a Noise Management Plan for construction, where residences are within 300 metres of the proposed construction activities. The plan must include:<br />a) proposed hours of daytime and nighttime work;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />c) a noise monitoring program, including locations, methodology, and schedule;<br />d) a description of the public and Indigenous communication and noise complaint response process; and<br />e) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 9 | <strong>Quality Management Plan</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 4 months prior to manufacturing any pipe and major components for the Project</strong>, a Project-specific Quality Management Plan that includes:<br />a) material/vendor qualification requirements;<br />b) quality control and assurance of pipe, fittings, and components that ensure all materials meet Trans Mountain&rsquo;s specifications (i.e., processes, procedures, specifications, random testing, inspection, and test reports);<br />c) mandatory documentation of process conditions during manufacture and verification of the conformance of manufacturer material test reports with Trans Mountain&rsquo;s requirements;<br />d) mandatory inspection requirements, inspector competency training, and qualifications;<br />e) non-conformance reporting and correction procedures;<br />f) change management process;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />g) commissioning requirements; and<br />h) material handling requirements during transportation.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 90 | <strong>Consultation on improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a consultation plan for its review of its Emergency Response Plans and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing A3S4V5). This plan must include:<br />a) the consultation plan&rsquo;s scope;<br />b) the consultation plan&rsquo;s objectives;<br />c) a preliminary list of Appropriate Government Authorities, first responders, potentially affected Indigenous groups and affected landowners/tenants with whom Trans Mountain will consult;<br />d) a preliminary list of consultation locations and timing; and<br />e) the methods that will be used to track commitments made during consultations and to incorporate them into Trans Mountain&rsquo;s Emergency Management Program, including its Emergency Response Plans.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 94 | <strong>Consultation reports &ndash; protection of municipal water sources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, <strong>and on or before 31 January of each year during construction and of the first 5 years after commencing operations,</strong> a report on Trans Mountain&rsquo;s consultations with municipalities and regional districts, communities, and Indigenous groups related to the protection of municipal and community water sources, including those sources currently relied upon and sources identified for potential future use. Each report must include:<br />a) the name of the municipality, regional district, community, or Indigenous group consulted;<br />b) the methods, dates, and locations of all meetings or consultations;<br />c) a summary of all issues or concerns raised; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />d) a summary of any steps or measures that have been or will be undertaken, including groundwater modelling or monitoring, as a result of consultations with municipalities, regional districts, communities, or Indigenous groups. This summary must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) any updates or amendments to maintenance policies, systems, programs, procedures, practices, and activities aimed at preventing pipeline releases;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) the criteria used to identify and select modelling or monitoring locations and parameters;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) results of any modelling or monitoring;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) any measures that have been taken to address modelling or monitoring results; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) any measures to share or to make accessible to municipalities, regional districts, communities, or Indigenous groups data or issues that arise regarding drinking water (aquifers, groundwater, and well water supplies); or<br />in the alternative to i)-v) above, an explanation why no further action is required to address or respond to issues or concerns raised.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal)(Initial filing ) Initial filing&nbsp;(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | XO-T260-010-2016 | New Tanks (Line 1 and Line 2) Authorization to construct and operate: • five new tanks at the Edmonton Terminal West Tank Area • one new tank at the Sumas Terminal • 14 new tanks at the Burnaby Terminal | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />c) the scope, methodology, and justification for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />d) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to the participating Indigenous group.<br />Trans Mountain must provide a copy of the report to each potentially affected group identified in b) above at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with &nbsp;Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 1 | <strong>Condition compliance</strong><br />Trans Mountain must comply with all of the [certificate/order] conditions, unless the NEB otherwise directs.<div>&nbsp;</div>(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 10 | <strong>Phased filings</strong><br />Due to the Project&rsquo;s large spatial extent, Trans Mountain may wish to commence Project construction activities at specific locations at different times (i.e., using a phased approach). This may entail doing so on the basis of pipeline spreads of defined lengths, or by regions, or work areas of Trans Mountain&rsquo;s choosing (such as terminals or pump stations). If Trans Mountain intends to use a phased approach for Project construction, it must undertake the following:<br />a) Trans Mountain must file with the NEB, <strong>at least 7 months prior to commencing construction</strong>, a complete list of construction spreads, regions, or work areas that, for the duration of Project construction, will serve as the basis by which Trans Mountain may submit condition filings in a phased approach. Each spread, region, or work area must be clearly delineated (e.g., by kilometre posts).<br />b) As part of its filing for a), to aid the NEB in anticipating future submissions, Trans Mountain must indicate the specific conditions and related spread(s), region(s) or work area(s) for which it expects to apply this phased approach. Trans Mountain must file updates to this list <strong>as they are available</strong>.<br />c) When submitting a filing for any condition using this phased approach, Trans Mountain must clearly indicate which spread(s), region(s), or work area(s) that filing applies to.<br />d) Construction of a particular spread, region, or work area <strong>must not</strong> proceed until all pre-construction conditions using this phased approach have been satisfied for that spread, region, or work area. Prior to commencing construction of the initial spread, region, or work area, all applicable conditions with more general pre-construction timing elements must also be satisfied.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 100 | <strong>Heritage resources</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction of individual Project components as described in Condition 10(a)</strong>:<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b); and<br />d) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c).(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 106 | <strong>Construction progress reports</strong><br />Trans Mountain must file with the NEB <strong>monthly construction progress reports from commencing construction until after commencing operations</strong>. The reports must include information on the progress of activities carried out during the reporting period, including:<br />a) safety, environmental and security issues or non-compliances that occurred during the reporting period;<br />b) measures undertaken to resolve safety and environmental issues or non-compliances identified in a);<br />c) confirmation that security issues identified in a) have been addressed;<br />d) a description and the location of any change made to geohazard mitigation measures pursuant to Condition&nbsp;51; and<br />e) the location of any pressure tests carried out during the reporting period and a description of any unsuccessful pressure tests, including the reasons for the lack of&nbsp; success of each.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | During Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 13 | <strong>Socio-Economic Effects Monitoring Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 6 months prior to commencing construction</strong>, a plan for monitoring potential adverse socio-economic effects of the Project during construction. The plan must include the following:<br />a) the factors or indicators to be monitored;<br />b) the methods and rationale for selecting the factors or indicators;<br />c) a description of the baseline, pre-construction socio-economic conditions;<br />d) the monitoring methods and schedule, including third party data source identification;<br />e) data recording, assessment, and reporting details;<br />f) a discussion of how measures will be implemented to address any identified adverse effects, including:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) the criteria or thresholds that will require measures to be implemented;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) how monitoring methods and measures implementation to address adverse effects, as necessary, are incorporated into Construction Execution Plans; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a description of the roles and responsibilities of construction prime contractors, sub-contractors, and community relations staff in monitoring socio-economic effects and implementing measures to address adverse effects;<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) plans for regular consultation and reporting on effects during construction with potentially affected communities, Indigenous groups, local and regional authorities, and service providers. | Closed | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 139 | <strong>Project completion</strong><br />Trans Mountain must file with the NEB, <strong>within 30 days after commencing operations</strong>, confirmation, signed by an officer of the company, that the Project was completed and constructed in compliance with all applicable [certificate/order] conditions. If compliance with any of the conditions cannot be confirmed, the officer of the company must include the reason(s) for this and the proposed course of action to achieve compliance.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB, <strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up, </strong>a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants.<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />i) an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />ii) a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />iii) an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 2 | ?<strong>Compliance with commitments</strong><br />Without limiting Conditions 3, 4 and 6, Trans Mountain must implement all of the commitments it made in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 3 | <strong>Environmental protection</strong><br />Trans Mountain must implement or cause to be implemented, at a minimum, all of the policies, practices, programs, mitigation measures, recommendations, and procedures for the protection of the environment included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 4 | <strong>Engineering and safety</strong><br />Trans Mountain must cause the Project to be designed, located, constructed, installed, and operated in accordance with, at a minimum, the specifications, standards, policies, mitigation measures, procedures, and other information included or referred to in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Integrity Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 45 | <strong>Weed and Vegetation Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, an updated Weed and Vegetation Management Plan for the Project that includes:<br />a) a summary of supplementary survey results, including pre-construction weed surveys, and a demonstration of the adequacy of such surveys;<br />b) measurable goals;<br />c) criteria describing when and where problem vegetation will be managed for each Project phase, including pre-construction, construction, post-construction, and operations;<br />d) a description of potential adverse effects related to treatment measures;<br />e) management procedures and a decision-making framework for selecting appropriate prevention and treatment measures, including a description of relevant specific habitats, land uses and land management plans and how each will be considered and kept up-to-date in selecting prevention and treatment measures;<br />f) the methods and schedule for short- and long-term vegetation monitoring;<br />g) a summary of its consultations with Appropriate Government Authorities, invasive plant councils or committees, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />h) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Weed and Vegetation Management Plan.(Blue River Deactivation) For filings associated with Blue River Deactivation | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 46 | <strong>Contamination Identification and Assessment Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 4 months prior to commencing construction</strong>, a Contamination Identification and Assessment Plan that includes:<br />a) a description of the procedures that have been implemented to-date, and that will be implemented prior to or during construction, to identify and assess pre-existing solid, liquid or gaseous contamination that could be disturbed by, or affect, the Project, including whether site investigations have been or will be undertaken;<br />b) a demonstration of the adequacy of the procedures in a) with reference to relevant standards, guidelines, and best practices, including how historical land use has been taken into account and a discussion of the potential for chemicals of concern to not be detectable by smell or by sight;<br />c) the information that has been or will be reported by Trans Mountain, including to whom and when, concerning pre-existing contamination;<br />d) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plan; and<br />e) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the Contamination Identification and Assessment Plan.(Blue River Deactivation) For filings associated with Blue River Deactivation | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 5 | <strong>Certificate expiration (sunset clause)</strong><br />Unless the NEB otherwise directs prior to 30 September 2021, this [certificate/order] will expire on 30 September 2021, unless construction of the Project has commenced by that date.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Sunset Clause
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table and must:(a)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <div><strong>within 3 months after the [certificate/order] date;</strong></div>(Blue River Deactivation) For filings associated with Blue River Deactivation(ii)) <div><strong>at least 30 days prior to commencing construction;</strong></div>(Blue River Deactivation) For filings associated with Blue River Deactivation(iii)) <div><strong>monthly, from the commencement of construction until the first month after commencing operations</strong>; and</div>(Blue River Deactivation) For filings associated with Blue River Deactivation(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Blue River Deactivation) For filings associated with Blue River Deactivation(b) and c)) b) post on its company website the same information required by a),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />c) maintain at each of its construction offices:<ul><li>i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;</li><li>ii) copies of any permits, authorizations, and approvals referenced in i); and</li><li>iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).</li></ul> | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 62 | <strong>Construction schedule</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction</strong>, a construction schedule identifying the major construction activities expected and, on a monthly basis, on the first working day of each calendar month from the commencement of construction until after commencing operations, updated detailed construction schedules.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 63 | <strong>Security Management Programs&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; </strong><br />Trans Mountain must file confirmation, signed by an officer of the company:<br />a) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and<br />b) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;<br />pursuant to the <em>National Energy Board Onshore Pipeline Regulations</em> and CSA Z246.1 (as amended from time to time).&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(a)) <strong>at least 3 months prior to commencing construction</strong>, that it has developed a Security Management Program for the construction phase of the Project; and(Blue River Deactivation) For filings associated with Blue River Deactivation(b)) <strong>at least 3 months prior to commencing operations</strong>, that it has amended its operations phase Security Management Program to include operation of the Project;(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Security
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 64 | <strong>Construction safety manuals</strong><br />Trans Mountain must file with the NEB:<br />a) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and<br />b) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.<br />These manuals must address routine construction activities, as well as blasting, tunneling, avalanche safety, safe work in proximity to operational pipelines and facilities, and special access procedures that may be required in areas subject to activities other than Project construction.(a)) <strong>at least 3 months prior to commencing construction</strong>, the Health and Safety Management Plan for the Project; and(Blue River Deactivation) For filings associated with Blue River Deactivation(b)) <strong>at least 2 months prior to commencing construction</strong>, Construction Safety Manuals (Project-Specific Safety Plans) for the applicable Project components. These must include separate Construction Safety Manuals for pipeline construction, terminal and pump station construction, Burnaby Mountain tunnel construction, and Westridge Marine Terminal construction.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Safety Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 73 | <strong>Traffic Control Plans for public roadways</strong><br />Trans Mountain must file with the NEB, <strong>at least 3 months prior to commencing construction of the pipeline and at least 2 months prior to commencing construction at each terminal and pump station</strong>, Traffic Control Plans for the use of public roadways for the Project. The plans must include:<br />a) information regarding the timing and location of key construction activities (including equipment mobilization and staging, pipe stockpiling, pipeline and pump station construction, and equipment demobilization);<br />b) current traffic volumes and anticipated traffic volumes during the construction period for both day and night times;<br />c) a description of the predicted traffic flows, including vehicle types and volumes, at key construction points, marshalling areas, access roads, and public roadways;<br />d) an assessment of the potential impacts associated with the increased volume of construction-related traffic (e.g., safety hazards, noise, light, dust, etc.) and associated mitigation measures; and<br />e) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the plans.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 78 | <strong>Facilities Environmental Protection Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction at the facilities (terminals, pump stations, temporary facilities, and associated infrastructure),</strong> an updated Project-specific Facilities Environmental Protection Plan for the construction at the facilities.&nbsp;&nbsp;<br />The updated Facilities Environmental Protection Plan must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Trans Mountain&rsquo;s Project application, its subsequent filings, or as otherwise committed to during the OH-001-2014 proceeding. The updated Facilities Environmental Protection Plan must describe the criteria for implementing all procedures and measures using clear and unambiguous language that confirms Trans Mountain&rsquo;s intention to implement all of its commitments.<br />The updated Facilities Environmental Protection Plan must include the following:<br />a) environmental procedures (including site-specific plans), criteria for implementing these procedures, mitigation measures, and monitoring applicable to all Project phases and activities;<br />b) policies and procedures for environmental training and the reporting structure for environmental management during construction, including the qualifications, roles, responsibilities, and decision-making authority for each job title identified in the updated Facilities Environmental Protection Plan;<br />c) any additional measures arising from supplemental pre-construction studies and surveys;<br />d) updated contingency plans and management plans;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />e) updated facility drawings including relevant site-specific resources and mitigations;<br />f) a description of how Trans Mountain has taken available and applicable Indigenous traditional land use and traditional ecological knowledge into consideration in developing the Environmental Protection Plan, including demonstration that those Indigenous persons and groups that provided Indigenous traditional land use information and traditional ecological knowledge, as reported during the OH-001-2014 proceeding and/or pursuant to Condition 97, had the opportunity to review and comment on the information; and<br />g) a summary of its consultations with Appropriate Government Authorities, potentially affected Indigenous groups and affected landowners/tenants. In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation, including any recommendations from those consulted, into the Facilities Environmental Protection Plan.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 89 | <strong>Emergency Response Plans for construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction</strong>, a Project-specific Emergency Response Plan, including the Trans Mountain Expansion Project Emergency Response Plan and site-specific Emergency Response Plans as referenced in Volume 4B, Section 5.4.2 of its Project application (Filing A3S1K6), that would be implemented during the construction phase. The plan(s) must include spill contingency measures that Trans Mountain will employ in response to accidental spills attributable to construction activities, 24-hour medical evacuation, fire response, and security.(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-015-2016 | Authorization to deactivate: • Blue River Pump Station | 2016-11-29 | 2016-06-06 | 2021-09-30 | In Progress | Thompson--Okanagan/British Columbia | 96 | <strong>Reports on engagement with Indigenous groups &ndash; construction</strong><br />Trans Mountain must file with the NEB, <strong>at least 2 months prior to commencing construction and every 6 months thereafter until after commencing operations</strong>, a report on the engagement activities it has undertaken with potentially affected Indigenous groups. Each report must include, at a minimum, for each Indigenous group engaged:<br />a) the name of the group;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />b) the method(s), date(s), and location(s) of engagement activities;<br />c) a summary of any issues or concerns raised; and<br />d) the measures taken, or that will be taken, to address or respond to issues or concerns, or an explanation why no further action is required to address or respond to issues or concerns.<br />Trans Mountain must provide a copy of each report to each group engaged (and identified in a) above) at the same time that it is filed with the NEB.(Blue River Deactivation) For filings associated with Blue River Deactivation(Initial filing) Initial filing(Subsequent filings ) Subsequent filings&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-010-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Lower Mainland--Southwest /British Columbia , Edmonton/Alberta | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB&nbsp;<strong>at least thirty days prior to commencing construction</strong>&nbsp;of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-010-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Lower Mainland--Southwest /British Columbia , Edmonton/Alberta | 124 | <strong>Implementing improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing operations</strong>, a detailed summary of its review of its Emergency Response Plans (as noted in Conditions 125 and 126) and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing A3S4V5). This filing must include a description of changes made to Trans Mountain&rsquo;s Emergency Management Program, as required under the National Energy Board Onshore Pipeline Regulations, including changes to:<br />a) the Pipeline Emergency Response Plan;<br />b) Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals, as well as the Westridge Marine Terminal; and<br />c) site-specific plans and documents related to a) and b), such as Geographic Response Plans, Geographical Response Strategies, control point mapping, tactical plans for submerged and sunken oil and tactical plans for high consequence areas.<br /><br />The summary must demonstrate Trans Mountain&rsquo;s ability to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type and in any geographic region or season and must include the following:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) &nbsp;a discussion of how the updated plans conform to the requirements contained within the National Energy Board Onshore Pipeline Regulations;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a discussion of how the plans consider, and would allow coordination with relevant federal, provincial, municipal and Indigenous community emergency response plans;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a discussion of how the results of research initiatives, such as the Scientific Advisory Committee work noted in Trans Mountain&rsquo;s response to NEB Information Request No. 1.63 (Filing A3W9H8) and other research noted during the OH-001-2014 proceeding, have been considered and incorporated into Trans Mountain&rsquo;s emergency response planning;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of the models used in response planning, including oil trajectory, fate and behavior, and air dispersion models; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) confirmation that an independent third party has reviewed and assessed the Emergency Response Plans and that Trans Mountain has considered and incorporated the comments generated by the review and assessment into the plans.<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a summary of its consultations with Appropriate Government Authorities, first responders, potentially affected Indigenous groups, and affected landowners/tenants (Condition 90 and Condition 117). In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation including any recommendations from those consulted into Trans Mountain&rsquo;s Emergency Management Program, including its Emergency Response Plans. | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-010-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Lower Mainland--Southwest /British Columbia , Edmonton/Alberta | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-010-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Lower Mainland--Southwest /British Columbia , Edmonton/Alberta | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;</strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 04 (Burnaby Terminal)) For filings associated with&nbsp;Phase 04 (Burnaby Terminal)(c) and d)) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).(b)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <strong>within 3 months after the [certificate/order] date;</strong>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with&nbsp;Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with&nbsp;Phase 04 (Burnaby Terminal)(iii)) <strong>monthly, from the commencement of construction until the first month after commencing operations; and</strong>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with&nbsp;Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with&nbsp;Phase 04 (Burnaby Terminal)(ii)) <strong>at least 30 days prior to commencing construction;</strong>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with&nbsp;Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with&nbsp;Phase 04 (Burnaby Terminal)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with&nbsp;Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with&nbsp;Phase 04 (Burnaby Terminal) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-010-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Lower Mainland--Southwest /British Columbia , Edmonton/Alberta | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a description and justification for how Trans Mountain has incorporated the results of its engagements, including any recommendations, into the plan;<br />c) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />d) the scope, methodology, and rationale for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />e) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and<br />f) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to potentially affected Indigenous groups, subject to appropriate protections for confidential information.<br />Trans Mountain must provide a copy of the report to all potentially affected groups at the same time that it is filed with the NEB.(Phase 02 (Edmonton Terminal)) For filings associated with Phase 02 (Edmonton Terminal)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(Phase 03 (Sumas Terminal)) For filings associated with Phase 03 (Sumas Terminal)(Phase 04 (Burnaby Terminal)) For filings associated with Phase 04 (Burnaby Terminal) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-XO-T260-007-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB&nbsp;<strong>at least thirty days prior to commencing construction</strong>&nbsp;of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)&nbsp;(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)&nbsp;(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)&nbsp;(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)&nbsp;(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)&nbsp;(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)&nbsp;(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)&nbsp;(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)&nbsp;(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-XO-T260-007-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-XO-T260-007-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;</strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge)(b)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <strong>within 3 months after the [certificate/order] date;</strong>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(ii)) <strong>at least 30 days prior to commencing construction;</strong>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(iii)) <strong>monthly, from the commencement of construction until the first month after commencing operations; and</strong>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge)) For filings associated with Temp. Inf. Sites (Westridge)(c) and d)) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i). | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-XO-T260-007-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta, Lower Mainland--Southwest /British Columbia | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a description and justification for how Trans Mountain has incorporated the results of its engagements, including any recommendations, into the plan;<br />c) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />d) the scope, methodology, and rationale for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />e) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and<br />f) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to potentially affected Indigenous groups, subject to appropriate protections for confidential information.<br />Trans Mountain must provide a copy of the report to all potentially affected groups at the same time that it is filed with the NEB.(Temp. Inf. Sites (Spread 1) ) For filings associated with Temp. Inf. Sites (Spread 1)(Temp. Inf. Sites (Spread 2) ) For filings associated with Temp. Inf. Sites (Spread 2)(Temp. Inf. Sites (Spread 3) ) For filings associated with Temp. Inf. Sites (Spread 3)(Temp. Inf. Sites (Spread 4) ) For filings associated with Temp. Inf. Sites (Spread 4)(Temp. Inf. Sites (Spread 5A) ) For filings associated with Temp. Inf. Sites (Spread 5A)(Temp. Inf. Sites (Spread 5B) ) For filings associated with Temp. Inf. Sites (Spread 5B)(Temp. Inf. Sites (Spread 6) ) For filings associated with Temp. Inf. Sites (Spread 6)(Temp. Inf. Sites (Spread 7) ) For filings associated with Temp. Inf. Sites (Spread 7)(Temp. Inf. Sites (Westridge) ) For filings associated with Temp. Inf. Sites (Westridge) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-008-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB&nbsp;<strong>at least thirty days prior to commencing construction</strong>&nbsp;of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-008-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Year 1 Report) Year 1 Report | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-008-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;</strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(n/a) n/a(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(c) and d)) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).(b)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <strong>within 3 months after the [certificate/order] date;</strong>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(ii)) <strong>at least 30 days prior to commencing construction;</strong>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(iii)) <strong>monthly, from the commencement of construction until the first month after commencing operations; and</strong>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-008-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a description and justification for how Trans Mountain has incorporated the results of its engagements, including any recommendations, into the plan;<br />c) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />d) the scope, methodology, and rationale for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />e) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and<br />f) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to potentially affected Indigenous groups, subject to appropriate protections for confidential information.<br />Trans Mountain must provide a copy of the report to all potentially affected groups at the same time that it is filed with the NEB.(Phase 05 (Jasper Pump Station)) For filings associated with Phase 05 (Jasper Pump Station)&nbsp;&nbsp;&nbsp;&nbsp;(Phase 06 (Black Pines Pump Station)) For filings associated with Phase 06 (Black Pines Pump Station)(Phase 07 (Kamloops Pump Station)) For filings associated with Phase 07 (Kamloops Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 08 (Sumas Pump Station)) For filings associated with Phase 08 (Sumas Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-009-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB&nbsp;<strong>at least thirty days prior to commencing construction</strong>&nbsp;of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)<br />&nbsp; &nbsp; &nbsp;(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-009-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 124 | <strong>Implementing improvements to Trans Mountain&rsquo;s Emergency Management Program</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 6 months prior to commencing operations</strong>, a detailed summary of its review of its Emergency Response Plans (as noted in Conditions 125 and 126) and equipment (including its availability), as referenced in Volume 7, Section 4.8.2 of its Project application (Filing A3S4V5). This filing must include a description of changes made to Trans Mountain&rsquo;s Emergency Management Program, as required under the National Energy Board Onshore Pipeline Regulations, including changes to:<br />a) the Pipeline Emergency Response Plan;<br />b) Emergency Response Plans for the Edmonton, Sumas, and Burnaby Terminals, as well as the Westridge Marine Terminal; and<br />c) site-specific plans and documents related to a) and b), such as Geographic Response Plans, Geographical Response Strategies, control point mapping, tactical plans for submerged and sunken oil and tactical plans for high consequence areas.<br /><br />The summary must demonstrate Trans Mountain&rsquo;s ability to prepare for, respond to, recover from, and mitigate the potential effects of emergencies of any type and in any geographic region or season and must include the following:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) &nbsp;a discussion of how the updated plans conform to the requirements contained within the National Energy Board Onshore Pipeline Regulations;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a discussion of how the plans consider, and would allow coordination with relevant federal, provincial, municipal and Indigenous community emergency response plans;<br />&nbsp;&nbsp;&nbsp;&nbsp; iii) a discussion of how the results of research initiatives, such as the Scientific Advisory Committee work noted in Trans Mountain&rsquo;s response to NEB Information Request No. 1.63 (Filing A3W9H8) and other research noted during the OH-001-2014 proceeding, have been considered and incorporated into Trans Mountain&rsquo;s emergency response planning;<br />&nbsp;&nbsp;&nbsp;&nbsp; iv) a description of the models used in response planning, including oil trajectory, fate and behavior, and air dispersion models; and<br />&nbsp;&nbsp;&nbsp;&nbsp; v) confirmation that an independent third party has reviewed and assessed the Emergency Response Plans and that Trans Mountain has considered and incorporated the comments generated by the review and assessment into the plans.<br />&nbsp;&nbsp;&nbsp;&nbsp; vi) a summary of its consultations with Appropriate Government Authorities, first responders, potentially affected Indigenous groups, and affected landowners/tenants (Condition 90 and Condition 117). In its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation including any recommendations from those consulted into Trans Mountain&rsquo;s Emergency Management Program, including its Emergency Response Plans. | In Progress | During Construction Phase | Standard | Filing Not Required | Emergency Management
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-009-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk.(Year 1 Report) For filing of Year 1 report | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-009-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;</strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with&nbsp;Phase 18 (Kamloops Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with&nbsp;Phase 19 (Kingsvale Pump Station)(c) and d)) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).(b)) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <strong>within 3 months after the [certificate/order] date;</strong>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(ii)) <strong>at least 30 days prior to commencing construction;</strong>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(iii)) <strong>monthly, from the commencement of construction until the first month after commencing operations; and</strong>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp;(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station) | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-002-XO-T260-009-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Banff--Jasper--Rocky Mountain House/Alberta, Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia | 98 | <strong>Plan for Indigenous group participation in construction monitoring</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>at least 2 months prior to commencing construction</strong>, a plan describing participation by Indigenous groups in monitoring activities during construction for the protection of traditional land and resource use for the pipelines, terminals and pump stations, and traditional marine resource use at the Westridge Marine Terminal. The plan must include:<br />a) a summary of engagement activities undertaken with Indigenous groups to determine opportunities for their participation in monitoring activities;<br />b) a description and justification for how Trans Mountain has incorporated the results of its engagements, including any recommendations, into the plan;<br />c) a list of potentially affected Indigenous groups, if any, that have reached agreement with Trans Mountain to participate in monitoring activities;<br />d) the scope, methodology, and rationale for monitoring activities to be undertaken by Trans Mountain and each participating Indigenous group identified in b), including those elements of construction and geographic locations that will involve Indigenous Monitors;<br />e) a description of how Trans Mountain will use the information gathered through the participation of Indigenous Monitors; and<br />f) a description of how Trans Mountain will provide the information gathered through the participation of Indigenous Monitors to potentially affected Indigenous groups, subject to appropriate protections for confidential information.<br />Trans Mountain must provide a copy of the report to all potentially affected groups at the same time that it is filed with the NEB.(Phase 09 (Edmonton Pump Station)) For filings associated with Phase 09 (Edmonton Pump Station)(Phase 11 (Wolf Pump Station)) For filings associated with Phase 11 (Wolf Pump Station)(Phase 12 (Edson Pump Station)) For filings associated with Phase 12 (Edson Pump Station)(Phase 13 (Hinton Pump Station)) For filings associated with Phase 13 (Hinton Pump Station)(Phase 10 (Gainford Pump Station)) For filings associated with Phase 10 (Gainford Pump Station)(Phase 14 (Blue River Pump Station)) For filings associated with Phase 14 (Blue River Pump Station)(Phase 15 (McMurphy Pump Station)) For filings associated with Phase 15 (McMurphy Pump Station)&nbsp; &nbsp; &nbsp; &nbsp;&nbsp;(Phase 16 (Blackpool Pump Station)) For filings associated with Phase 16 (Blackpool Pump Station)(Phase 17 (Black Pines Pump Station)) For filings associated with Phase 17 (Black Pines Pump Station)(Phase 18 (Kamloops Pump Station)) For filings associated with Phase 18 (Kamloops Pump Station)(Phase 19 (Kingsvale Pump Station)) For filings associated with Phase 19 (Kingsvale Pump Station)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-MO-015-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Thompson--Okanagan/British Columbia | 100 | <strong>Heritage Resources and Sacred and Cultural Sites</strong><br />Trans Mountain must file with the NEB&nbsp;<strong>at least thirty days prior to commencing construction</strong>&nbsp;of individual Project components as described in Condition 10(a):<br />a) confirmation, signed by an officer of the company, that it has obtained all of the required archaeological and heritage resource permits and clearances from the Alberta Department of Culture and the British Columbia Ministry of Forests, Lands and Natural Resource Operations;<br />b) confirmation that it has consulted with the British Columbia Ministry of Forests, Lands and Natural Resource Operations, and that the Ministry has reviewed and approved the mitigation measures for disturbance to impacted palaeontological sites within British Columbia;<br />c) a description of how Trans Mountain will meet any conditions and respond to any comments and recommendations contained in the permits and clearances referred to in a) or obtained through the consultation referred to in b);<br />d) a list of sacred and cultural sites identified in the OH-001-2014 proceeding, MH-05-2018 Reconsideration proceeding, or Phase III Crown consultations and not already captured under condition 97;<br />e) a summary of any mitigation measures that Trans Mountain will implement to reduce or eliminate, to the extent possible, Project effects on sites listed in d), or a rationale for why mitigation was not required;<br />f) confirmation that Trans Mountain will update the relevant Environmental Protection Plan(s) to include any relevant information from the conditions or recommendations referred to in c) or the mitigations referred to in e).(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Prior to the Construction Phase | Standard | Filing Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-MO-015-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Thompson--Okanagan/British Columbia | 151 | <strong>Post-construction environmental monitoring reports</strong><br />Trans Mountain must file with the NEB,&nbsp;<strong>on or before 31 January following the first, third, and fifth complete growing seasons after completing final clean-up</strong>, a post-construction environmental monitoring report for the Project that must include:<br />a) a description of the valued components or issues that were assessed or monitored;<br />b) measurable goals for each valued component or issue;<br />c) monitoring methods for each valued component or issue, results of the monitoring, and a comparison to the defined measurable goals;&nbsp;<br />d) corrective actions taken, their observed success, and their current status;<br />e) identification on a map or diagram of the locations where corrective actions were taken;<br />f) any further corrective actions planned and a schedule for monitoring and reporting; and<br />g) a summary of its consultations with appropriate government authorities and any potentially affected Indigenous groups and affected landowners/tenants;<br />h) in its summary, Trans Mountain must provide a description and justification for how Trans Mountain has incorporated the results of its consultation into the strategy.<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;<br />In the post-construction environmental monitoring report filed after the fifth full growing season after completing clean-up, Trans Mountain must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; i.&nbsp; an assessment of the effectiveness of mitigative and corrective actions and how learnings have been or will be applied to Trans Mountain&rsquo;s Environmental Protection Program;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii. a detailed description of all valued components or issues for which the measurable goals have not been achieved during the duration of the post-construction monitoring program; and<br />&nbsp;&nbsp;&nbsp;&nbsp; iii. an evaluation of the need for any further corrective actions, measurable goals, assessments, or monitoring of valued components or issues, including a schedule for those.<br />&nbsp;<br />All filed post-construction environmental monitoring reports must address issues related, but not limited, to: soils; weeds; watercourse crossings; riparian vegetation; wetlands; rare plants, lichens and ecological communities; municipal tree replacement; wildlife and wildlife habitat; fish and fish habitat; marine fish and fish habitat; marine mammals; marine birds; and species at risk. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-MO-015-2016 |  | 2019-07-19 | 2019-07-19 |  | In Progress | Thompson--Okanagan/British Columbia | 6 | <strong>Commitments tracking table&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;</strong><br />Without limiting Conditions 2, 3 and 4, Trans Mountain must implement the commitments contained within its commitments tracking table. The proponent shall periodically update the commitments tracking table as per b), by adding to the table all commitments made by the Proponent in respect of the Project subsequent to the close of the MH-052-2018 proceeding, and must:(a)) file with the NEB and post on its website, <strong>at least thirty (30) days prior to commencing construction</strong>, an updated commitments tracking table. The commitments tracking table must contain:<br />&nbsp;&nbsp;&nbsp;&nbsp; i) all commitments Trans Mountain made to Indigenous groups in its Project application or to which it otherwise committed on the record of the OH-001-2014 proceeding, as well as the MH-052-2018 proceeding, during phase III and IV consultations, and during ongoing consultations and engagements;<br />&nbsp;&nbsp;&nbsp;&nbsp; ii) a plan for addressing all commitments made to Indigenous groups, the plan must include:<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;1) a description of the approach for addressing each commitment made to Indigenous groups<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;2) the accountable lead for implementing each commitment; and,<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;3) the estimated timeline associated with the fulfillment of each commitment; and<br />&nbsp;&nbsp;&nbsp;&nbsp; &nbsp;&nbsp;&nbsp;&nbsp;&nbsp;4) the criteria used to determine when commitments have been fulfilled/satisfied.(Blue River Deactivation) For filings associated with Blue River Deactivation(c) and d) ) c) post on its company website the same information required by a) and b),<strong>&nbsp;using the same indicated timeframes</strong>; and<br />d) maintain at each of its construction offices:<br />&nbsp; &nbsp; &nbsp;i) the relevant environmental portion of the commitments tracking table listing all of Trans Mountain&rsquo;s regulatory commitments, including those from the Project application and subsequent filings, and environmental conditions or site-specific mitigation or monitoring measures from permits, authorizations, and approvals for the Project issued by federal, provincial, or other permitting authorities;<br />&nbsp; &nbsp; &nbsp;ii) copies of any permits, authorizations, and approvals referenced in i); and<br />&nbsp; &nbsp; &nbsp;iii) copies of any subsequent variances to permits, authorizations, and approvals referenced in i).(b) ) file with the NEB, at the following times, an updated commitments tracking table including the status of each commitment:(i)) <strong>within 3 months after the [certificate/order] date;</strong>(Blue River Deactivation) For filings associated with Blue River Deactivation(ii)) <strong>at least 30 days prior to commencing construction;</strong>(Blue River Deactivation) For filings associated with Blue River Deactivation(iii)) <strong>monthly, from the commencement of construction until the first month after commencing operations; and</strong>(Blue River Deactivation) For filings associated with Blue River Deactivation(iv)) <div><strong>quarterly thereafter until</strong>:</div><ol><li><strong>all commitments on the table are satisfied</strong>&nbsp;(superseded, complete or otherwise closed), at which time Trans Mountain must file confirmation, signed by an officer of the company, that the commitments on the table have been satisfied; or</li><li><strong>6 years after commencing operations</strong>, at which time Trans Mountain must file with the NEB a summary of any outstanding commitments and a plan and implementation timeline for addressing these commitments;</li></ol><div>whichever comes earlier;&nbsp; &nbsp; &nbsp;</div>(Blue River Deactivation) For filings associated with Blue River Deactivation | In Progress | Includes all Phases of Constr. | Standard | Filing Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | MO-042-2019 | Application made by Trans Mountain Pipeline ULC (Trans Mountain), dated 30 August 2019, pursuant to subsection 95(2) of the CER Act | 2019-09-13 | 2019-09-13 |  | In Progress |  | 1 | <strong>Within 7 days of completing the Watercourse Diversion,</strong> Trans Mountain must file, with the Commission, confirmation that the approved Watercourse Diversion was completed and constructed in compliance with all applicable conditions and commitments from the Trans Mountain Expansion Project. If compliance with any of these conditions or commitments cannot be confirmed, Trans Mountain must file with the Commission details as to why compliance cannot be confirmed | In Progress | Post Construction Phase | Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Commission otherwise directs.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 10 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearings or NEB Decisions for MH 007 2017 and MH 018 2017. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 11 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH 030 2017. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 12 | Trans Mountain shall file with the Commission, and provide to Erich Ploentzke, within 30 days of the issuance of this Order, a CT listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i) the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii)&nbsp;the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 13 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH 022 2017. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 14 | Trans Mountain shall file with the Commission, and provide to Dale and Lorna Plummer and Carly Morin, within 30 days of the issuance of this Order, a CT listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i)&nbsp;the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii)&nbsp;the estimated timelines associated with the fulfillment of each commitment. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 15 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH 023 2017. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 16 | Trans Mountain shall file with the Commission, and provide to Janet and Lyle Russell, within 30 days of the issuance of this Order, a CT listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i)&nbsp;the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii)&nbsp;the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 17 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH 025 2017. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 2 | Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 3 | Trans Mountain shall file with the Commission, and provide to Victoria Maitland and John Gordon McKay, Dianne Murray, Keelan Petterson , and Javier and Annemarie Sarango, within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i) the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii)&nbsp;the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 4 | Trans Mountain shall file with the Commission, within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearings or NEB Decisions for MH 017 2017 (Dianne Murray), MH 026 2017 (Javier and Annemarie Sarango), and MH 060 2017 (Victoria Maitland and John Gordon McKay).<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 5 | <strong>Residence and its Foundation </strong>(b)) <strong>After Construction and Final Clean-up</strong><br />b) The Commission directs Trans Mountain, 12 months after completing final clean-up on or adjacent to the landowner lands, to:<br />b.1)&nbsp;conduct a post-construction inspection of the items documented in the pre-construction inspection report;<br />b.2)&nbsp;provide a copy of the post-construction inspection report to the landowner; and<br />b.3)&nbsp;file with the Commission a confirmation that it has fulfilled this requirement.<br /><br />&nbsp;(a)) Prior to Construction<br />The Commission directs Trans Mountain, prior to construction on or adjacent to the landowner lands, to:<br />a.1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; conduct a pre-construction inspection of the landowner residence and its foundation;<br />a.2)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; prepare a pre-construction inspection report which will include, at a minimum, documentation including photographs of the pre-construction condition of the residence and foundation;<br />a.3)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; provide the landowner with a copy of the pre-construction inspection report; and<br />a.4)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; file with the Commission, at least 15 days prior to the commencement of construction on or adjacent to the landowner lands, confirmation that it has fulfilled this requirement.<br />.(c)) <strong>After Construction and Final Clean-up</strong><br />c) Trans Mountain must file with the Commission, 6 months following the completion of the post-construction inspection report:<br />c.1)&nbsp;confirmation that no new damage, other than that noted in the pre construction report, was identified in the post-construction inspection report; or<br />c.2)&nbsp;should any new damage be noted in the post-construction inspection report that was not present in the pre-construction report Trans Mountain is required to:<br />1)&nbsp;confirm that work to repair any new damage has been completed by qualified professionals and has restored the landowner&rsquo;s residence and/or foundation to its pre-construction condition; or<br />2)&nbsp;provide a timeline for when the repairs are planned to be completed; or<br />3)&nbsp;provide justification that Trans Mountain determined the damage was not caused by construction. | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 6 | Septic System<br />&nbsp;(a)) <strong>Prior to Construction</strong><br />a)&nbsp;The Commission directs Trans Mountain, prior to construction on or adjacent to the landowner lands, to:<br />a.1)&nbsp;have a professional installer conduct an inspection of the landowner&rsquo;s septic system to complete a pre-construction functional analysis and prepare a pre-construction septic system inspection report (pre-construction septic report) for the current system;<br />a.2)&nbsp;provide a copy of the pre-construction septic report to the landowner;<br />a.3)&nbsp;locate and mark the septic system including the tank and tile field; and<br />a.4)&nbsp;file with the Commission, at least 15 days prior to the commencement of construction on or adjacent to the landowner lands, confirmation that it has fulfilled these requirements.<br />&nbsp;(b)) <strong>After Construction and Final Clean-up</strong><br />b)&nbsp;The Commission directs Trans Mountain, within 60 days after completing final clean-up on or adjacent to the landowner lands, to:<br />b.1) re-inspect the septic system to complete a post-construction functional analysis and prepare a post-construction septic system inspection report (post-construction septic report);<br />b.2)&nbsp;provide a copy of post-construction septic report to the landowner; and<br />b.3)&nbsp;file confirmation with the Commission that:<br />&nbsp;&nbsp;&nbsp; 1)&nbsp;no new damage was identified in the post-construction septic report; or<br />&nbsp;&nbsp;&nbsp; 2)&nbsp;should any new damage be noted in the post-construction septic report that was not present in the pre-construction septic report, Trans Mountain is required to:<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; a)&nbsp;confirm that work to repair any new damage has been completed by qualified professionals and has restored the landowner&rsquo;s septic system to, at a minimum, its pre-construction condition; or<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; b)&nbsp;provide a timeline for when the repairs are planned to be completed; or<br />&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; c)&nbsp;provide justification that Trans Mountain determined the damage was not caused by construction.&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;(c)) <strong>After Construction and Final Clean-up</strong><br />The Commission further directs Trans Mountain 18 months after completing final clean-up to:<br />c.1)&nbsp;re-inspect the septic system to complete a post-construction functional analysis and prepare a final septic system inspection report (final septic report);<br />c.2)&nbsp;provide a copy of the final septic report to the landowner; and<br />c.3)&nbsp;file confirmation with the Commission that:<br />1)&nbsp;no new damage was identified in the final septic report; or<br />2)&nbsp;should any new damage be noted in the final septic report that was not present in the pre-construction or post-construction septic reports, Trans Mountain is required to:<br />a)&nbsp;confirm that work to repair any new damage has been completed by qualified professionals and has restored the landowner&rsquo;s septic system to, at a minimum, its pre-construction condition; or<br />b)&nbsp;provide a timeline for when the repairs are planned to be completed; or<br />c)&nbsp;provide justification that Trans Mountain determined the damage was not caused by construction. | In Progress | Includes all Phases of Constr. | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 7 | Trans Mountain shall file with the Commission, and provide to Cribb Construction Ltd., within 30 days of the issuance of this Order, a CT listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i) the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | Closed | Unspecified | Standard | Filing Not Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 8 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH 010 2017. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-001-OPL-002-2019 | Letter and Amending Order - conditions previously issued | 2019-11-08 | 2019-11-08 |  | In Progress |  | 9 | Trans Mountain shall file with the Commission, and provide to Shawn Berry, and Stuart Palk and Wendy Bailer-Palk, within 30 days of the issuance of this Order, a CT listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i)&nbsp;&nbsp;the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii)&nbsp;the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2019 | PPBoR for segment 7.7 tunnel | 2019-11-19 | 2019-11-19 |  | In Progress |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order, and &nbsp;&nbsp;all commitments made during the detailed route hearing for MH-055-2017, unless the Commission otherwise directs | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2019 | PPBoR for segment 7.7 tunnel | 2019-11-19 | 2019-11-19 |  | In Progress |  | 2 | Trans Mountain shall file with the Commission, and provide to David Huntley, within 30 days of the issuance of this Order, a Commitments Table listing all commitments made by Trans Mountain in its detailed route application related to Segment 7.7 (tunnel), and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<ol><li>the documentation in which the commitment appears (for example, the detailed route application for the Segment 7.7 (tunnel), hearing transcripts, evidence, or other source); and</li><li>the estimated timelines associated with the fulfillment of each commitment;</li></ol> | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2019 | PPBoR for segment 7.7 tunnel | 2019-11-19 | 2019-11-19 |  | In Progress |  | 3 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB decision for MH-055-2017; and | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2019 | PPBoR for segment 7.7 tunnel | 2019-11-19 | 2019-11-19 |  | In Progress |  | 4 | Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order. | In Progress | During Construction Phase | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2019 | PPBoR Approval No. 5 for segments 3 and 4. | 2019-11-28 | 2019-11-28 |  | In Progress |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the MH-078-2017 detailed route hearing, unless the Commission otherwise directs.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2019 | PPBoR Approval No. 5 for segments 3 and 4. | 2019-11-28 | 2019-11-28 |  | In Progress |  | 2 | Trans Mountain shall file with the Commission, and provide to John Richardson and Robert McMahon, within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i) the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment;<br />&nbsp; | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2019 | PPBoR Approval No. 5 for segments 3 and 4. | 2019-11-28 | 2019-11-28 |  | In Progress |  | 3 | Trans Mountain shall file with the Commission, within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH-078-2017; and<br />&nbsp; | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative, Environmental Protection, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2019 | PPBoR Approval No. 5 for segments 3 and 4. | 2019-11-28 | 2019-11-28 |  | In Progress |  | 4 | Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order<br />&nbsp; | In Progress | During Construction Phase | Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-001-2020 | PPBoR Approval No 7 - Segments 2 and 5.3 | 2020-01-21 | 2020-01-21 |  | In Progress |  | 1 | Trans Mountain shall comply with all of the conditions contained in this Order, including all commitments made during the MH-023-2017 detailed route hearing, unless the Commission otherwise directs. | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-001-2020 | PPBoR Approval No 7 - Segments 2 and 5.3 | 2020-01-21 | 2020-01-21 |  | In Progress |  | 2 | Trans Mountain shall file with the Commission, and provide to Dale and Lorna Plummer, and Carly Morin, within 30 days of the issuance of this Order, a Commitments Table (CT) listing all commitments made by Trans Mountain in its detailed route application, and as otherwise agreed to during questioning, argument or any related submissions, including reference to:<br />i) the documentation in which the commitment appears (for example, the detailed route application, hearing transcripts, evidence, or other&nbsp;source); and<br />ii) and the estimated timelines associated with the fulfillment of each commitment;<br />&nbsp; | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-001-2020 | PPBoR Approval No 7 - Segments 2 and 5.3 | 2020-01-21 | 2020-01-21 |  | In Progress |  | 3 | Trans Mountain shall file with the Commission within 30 days of issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from the detailed route hearing or NEB Decision for MH-023-2017; and | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative, Integrity Management, Environmental Protection
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-001-2020 | PPBoR Approval No 7 - Segments 2 and 5.3 | 2020-01-21 | 2020-01-21 |  | In Progress |  | 4 | Trans Mountain shall maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order. | In Progress | Not Construction Related | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2020 | PPBoRs approval no. 9 for lands in segments 3,4 and 5.3 approved by Panel | 2020-05-04 | 2020-05-04 |  | In Progress |  | 1 | Trans Mountain must comply with all of the conditions contained in this Order, including all commitments made during Detailed Route Hearings<br />MH-002-2020 and MH-003-2020 (which incorporate the MH-008-2018 and MH-009-2018 hearing records), unless the Commission otherwise<br />directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2020 | PPBoRs approval no. 9 for lands in segments 3,4 and 5.3 approved by Panel | 2020-05-04 | 2020-05-04 |  | In Progress |  | 2 | Trans Mountain must file with the Commission, and provide to KGHM Ajax Mining Inc. and Sugarloaf Ranches Ltd., within 30 days of the issuance of this Order, a Commitments Table listing all commitments made by Trans Mountain on the record of the MH-002-2020 and MH-003-2020 proceedings, including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcripts, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2020 | PPBoRs approval no. 9 for lands in segments 3,4 and 5.3 approved by Panel | 2020-05-04 | 2020-05-04 |  | In Progress |  | 3 | Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any applicable changes resulting from Detailed Route Hearings MH-002-2020 and MH-003-2020 or the Commission&rsquo;s decisions in those hearings.<br />&nbsp; | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-003-2020 | PPBoRs approval no. 9 for lands in segments 3,4 and 5.3 approved by Panel | 2020-05-04 | 2020-05-04 |  | In Progress |  | 4 | Trans Mountain must maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 7 | The Commission&rsquo;s approval of PPBoR Sheets M002-PM03025-003, M002-PM03026-001, M002-PM03027-001, and M002-PM03027-002 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, and provide to the City of Coquitlam, within 30 days of the issuance of this Order, a commitments table listing all commitments made by Trans Mountain on the record of the MH-034-2017 proceeding, including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcripts, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment. | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 1 | Trans Mountain must comply with all of the conditions contained in this Order, including all commitments made during the detailed route hearing, unless the Commission otherwise directs.<br />&nbsp; | In Progress | Prior to the Construction Phase | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 10 | The Commission&rsquo;s approval of PPBoR Sheets M002-PM03028-001, M002-PM03028-002, M002-PM03028-003, and M002-PM03028-004 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any applicable changes resulting from Detailed Route Hearings MH-046-2017, MH-049-2017, MH-050-2017, MH-051-2017, MH-052-2017, MH-057-2017, and MH-058-2017 or the NEB&rsquo;s decisions in those hearings. | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 11 | The Commission&rsquo;s approval of PPBoR Sheet M002-PM03028-005 (from KP&nbsp;0+000 to KP 0+200) is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, and provide to David Huntley, within 30 days of the issuance of this Order, a commitments table listing all commitments made by Trans Mountain on the record of the MH-055-2017 proceeding, including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcripts, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment. | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 12 | The Commission&rsquo;s approval of PPBoR Sheet M002-PM03028-005 (from KP&nbsp;0+000 to KP 0+200) is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any applicable changes resulting from Detailed Route Hearing MH-055-2017 or the NEB&rsquo;s decision in that hearing. | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 2 | Trans Mountain must maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 3 | The Commission&rsquo;s approval of PPBoR Sheet M002-PM03013-002 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, and provide to 1054408 BC Ltd., within 30 days of the issuance of this Order, a commitments table listing all commitments made by Trans Mountain on the record of the MH-001-2020 proceeding (which incorporates the MH-003-2018 hearing record), including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcripts, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 4 | The Commission&rsquo;s approval of PPBoR Sheet M002-PM03013-002 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any applicable changes resulting from Detailed Route Hearing MH-001-2020 or the Commission&rsquo;s decision in that hearing.<br />&nbsp; | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 5 | The Commission&rsquo;s approval of PPBoR Sheets M002-PM03023-002, M002-PM03024-001, and M002-PM03024-002 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, and provide to the Fraser Heights Community Association and Min Guo, within 30 days of the issuance of this Order, a commitments table(s) listing all commitments made by Trans Mountain on the applicable record(s) of the MH-036-2017 and MH-053-2017 proceedings, including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcripts, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 6 | The Commission&rsquo;s approval of PPBoR Sheets M002-PM03023-002, M002-PM03024-001, and M002-PM03024-002 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any applicable changes resulting from Detailed Route Hearings MH-036-2017 and MH-053-2017 or the NEB&rsquo;s decisions in those hearings. | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 8 | The Commission&rsquo;s approval of PPBoR Sheets M002-PM03025-003, M002-PM03026-001, M002-PM03027-001, and M002-PM03027-002 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any applicable changes resulting from Detailed Route Hearing MH-034-2017 or the NEB&rsquo;s decision in that hearing.<br />&nbsp; | Closed | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-004-2020 | Panel to approve letter and Orders related to PPBoR sheets for lands in segments 5,6,7. | 2020-06-04 | 2020-06-04 |  | In Progress |  | 9 | The Commission&rsquo;s approval of PPBoR Sheets M002-PM03028-001, M002-PM03028-002, M002-PM03028-003, and M002-PM03028-004 is subject to the following conditions:<br /><br />Trans Mountain must file with the Commission, and provide to Holly Chan, Steve Cook, Karim and Anar Dossa, Lily and Frank Fan, Claudia Leung, Michael Radano, and Underhill Lands Ltd., within 30 days of the issuance of this Order, a commitments table(s) listing all commitments made by Trans Mountain on the applicable record(s) of the MH-046-2017, MH-049-2017, MH-050-2017, MH-051-2017, MH-052-2017, MH-057-2017, and MH-058-2017 proceedings, including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcripts, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment.<br />&nbsp; | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-007-OC-065 | Chilliwack BC Hydro Route Road | 2019-08-21 | 2019-08-26 |  | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | <strong>Compliance with commitments</strong><br />Trans Mountain must implement all of the commitments it made in its Realignment application or to which it otherwise committed on the record of the OH-001-2017 proceeding, unless the Board otherwise directs.<br />&nbsp; | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | AO-007-OC-065 | Chilliwack BC Hydro Route Road | 2019-08-21 | 2019-08-26 |  | In Progress | Cariboo/British Columbia , Lower Mainland--Southwest /British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | <strong>Noise Management Plan</strong><br />Trans Mountain must file with the NEB for approval, <strong>at least 3 months prior to commencing construction</strong>, a site-specific Noise Management Plan for construction of the Chilliwack Realignment, for all directly affected landowners within 15 m of the proposed<br />construction activities. The plan must include, at minimum:<br />a) proposed hours of daytime and nighttime work;<br />b) noise mitigation measures, including all technologically and economically feasible mitigation measures;<br />c) a noise monitoring program, including locations, methodology, and schedule;<br />d) a description of the public and Indigenous communication and noise complaint response process; and<br />e) a contingency plan that contains proposed mitigation measures for addressing noise complaints, which may include the temporary relocation of specific residents at their request.<br />&nbsp; | In Progress | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic, Socio-Economic
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2020 | Lands in Segments 2,4,5 PPBoR approval No. 11 - TMX detailed route | 2020-08-07 | 2020-08-07 |  | In Progress |  | 1 | Trans Mountain must comply with all of the conditions contained in this Order, including all commitments made during Detailed Route Hearing MH-078-2017, unless the Commission otherwise directs. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2020 | Lands in Segments 2,4,5 PPBoR approval No. 11 - TMX detailed route | 2020-08-07 | 2020-08-07 |  | In Progress |  | 2 | Trans Mountain must file with the Commission, and provide to Mr. John Richardson and Mr. Robert McMahon, within 30 days of the issuance of this Order, a commitments table listing all commitments made by Trans Mountain on the record of Detailed Route Hearing MH-078-2017, including reference to:<br />i) the documentation in which the commitment appears (for example, evidence, hearing transcript, or other source); and<br />ii) the estimated timelines associated with the fulfillment of each commitment. | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2020 | Lands in Segments 2,4,5 PPBoR approval No. 11 - TMX detailed route | 2020-08-07 | 2020-08-07 |  | In Progress |  | 3 | Trans Mountain must file with the Commission, within 30 days of the issuance of this Order, updated environmental and construction alignment sheets applicable to this Order, to include the Order number and account for any changes resulting from Detailed Route Hearing MH-078-2017 or the NEB&rsquo;s decision in that hearing. | In Progress | Prior to the Construction Phase | Non Standard | Filing Not Required | Administrative
Trans Mountain Pipeline ULC | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | Trans Mountain Expansion Project - Reconsideration- MH-052-2018 | In Progress | OPL-005-2020 | Lands in Segments 2,4,5 PPBoR approval No. 11 - TMX detailed route | 2020-08-07 | 2020-08-07 |  | In Progress |  | 4 | Trans Mountain must maintain at its construction office(s), a copy of this Order and any filings made to the Commission under this Order. | In Progress | Includes all Phases of Constr. | Non Standard | Filing Required | Administrative
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 1 | St. Clair must cause the abandonment operations to be carried out in accordance with the specifications, standards and other information referred to in its application and as agreed to in its related submissions. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition, Integrity Management
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 2 | St. Clair must implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in its application or as otherwise agreed to in its related submissions. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition, Environmental Protection
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 3 | St. Clair must file with the Board for approval, within 120 days following the completion of abandonment activities:a) the results of the Phase II Environmental Screening Assessment (ESA) conducted at the station site;b) St. Clair's plans with respect to conducting any additional assessments, remediation activities and reporting to the Board (refer to the Board's Remediation Process Guide [2011]) as a result of the outcomes of the Phase II ESA;c) St. Clair's detailed plans, if any, with respect to implementing groundwater monitoring, including, but not limited to, details regarding the parameters to be monitored, applicable standards/levels to assess against, well locations, anticipated frequency and duration, and responsibilities for monitoring and well maintenance; andd) the outcomes of St. Clair's consultation with applicable and/or interested federal and provincial authorities regarding a), b) and c)."" | Closed | Abandonment | Standard | Filing Not Required | Environmental Protection
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 4 | St. Clair must file with the Board, within 120 days following the completion of abandonment activities, one of the following:a) confirmation that the Station site has been fully transferred to TCPL, including details regarding the satisfaction of the conditions of sale, if any; orb) if the transfer of the Station site to TCPL is still pending, the reasoning for this pending status; orc) if the transfer of the Station site to TCPL has been terminated with no possibility of being completed in the future, a modified abandonment plan for the Station site which describes in detail how the site will be fully reclaimed, for approval by the Board."" | Closed | Abandonment | Standard | Filing Not Required | Administrative, Financial
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 5 | St. Clair must file with the Board for approval, within 120 days following the completion of abandonment activities, information demonstrating that there is adequate coverage for future financial liabilities. | Closed | Abandonment | Standard | Filing Not Required | Administrative, Financial
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 6 | St. Clair must file with the Board, within 120 days of the date of completion of the abandonment activities, confirmation, by an officer of the company, that the Project was completed and all activities were conducted in compliance with all conditions of this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. Thefiling required by this condition must include a statement confirming that the signatory to the filing is an officer of the company."" | Closed | Abandonment | Non Standard | Filing Not Required | Standard Condition
St. Clair Pipelines Management Inc. | Abandonment of Empire Odourant Station | Abandon Empire Odourant Station | Completed | MO-029-2011 | For Leave to Abandon the Empire Odourant Station located on Iroquiois Street in the Regional Municipality of Niagara Falls (Formerly Township of Willoughby) | 2011-12-20 | 2012-01-05 | 2012-12-31 | All Conditions Met | Hamilton--Niagara Peninsula/Ontario | 7 | Unless the Board otherwise directs prior to 31 December 2012, this Order shall expire on 31 December 2012, unless the abandonment activities have been completed by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | SCPLMI shall comply with all the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | SCPLMI shall cause the approved Project to be designed, located, constructed, installed, operated and decommissioned in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | SCPLMI shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | SCPLMl shall file with the Board, at least 30 days prior to construction, an updated project specific Environmental Protection Plan (EPP) which SCPLMI shall implement. This EPP shall describe all environmental protection procedures, and mitigation and monitoring commitments, as set out in SCPLMI's application for the Project, subsequent filings, or as otherwise agreed to in its related submissions. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 5 | SCPLMI shall notify the Board within 15 days of the successful completion of the intended HDD crossing of the St. Clair River. If the HDD crossing is not feasible, SCPLMI shall apply to the Board for approval of an alternate crossing technique and include an environmental assessment of the proposed alternative with its application prior to the commencement of construction. | Closed | During Construction Phase | Standard | Filing Not Required | Environmental Protection
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 6 | In the event of HDD bore equipment being set up in Canada, at least 14 days prior to the start of the HDD activity, SCPLMI shall file with the Board a noise management plan containing information on day-time and potential night-time HDD operations. The plan shall include but not be limited to:a) a final summary of proposed HDD noise mitigation measures for day-time and potential night-time operations;b) confirmation that residents potentially affected by HDD noise will receive notice from SCPLMI at least 14 days prior to starting the HDD activities;c) confirmation that residents potentially affected by HDD noise will receive contact information for SCPLMI at least 14 days prior to starting the HDD activities in the event they have concerns about the HDD noise; and d) a description of how SCPLMI plans to address any complaints received regarding HDD noise."" | Closed | During Construction Phase | Standard | Filing Not Required | Environmental Protection
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 7 | SCPLMI shall file with the Board, at least 14 days prior to the commencement of any groundbreaking activities:a) A copy of correspondence received from the Ontario Ministry of Tourism, Culture and Sport indicating the acceptability of the Project's archaeological assessment; andb) A statement on how SCPLMI intends to implement any recommendations contained in a) above."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 8 | Within 30 days of the date that the approved Project is placed in service, SCPLMI shall file with the Board a confinnation that the approved Proiect was completed and constructed in compliance with all applicable-conditions in this Order. If compliance with any of these conditions cannot be confirmed, SCPLMI shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of SCPLMI. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
St. Clair Pipelines Management Inc. | Bluewater River Crossing Replacement | Replace Bluewater River Crossing | Completed | XG-S402-011-2012 | Application pursuant to section 58 of the National Energy Board Act (NEB Act) and subsection 45.1(1) of the Onshore Pipeline Regulations, 1999 (OPR-99) for approval of the Bluewater River Crossing Replacement Project (the Project) | 2012-06-12 | 2012-06-13 |  | All Conditions Met | Windsor--Sarnia/Ontario | 9 | Unless the Board otherwise directs prior to 12 June 2013 this Order shall expire on 12 June 2013, unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
St. Clair Pipelines Management Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 1 | Algonquin shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 2 | Algonquin shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its Application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 3 | Algonquin shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its Application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 4 | Algonquin shall not commence physical work on the Project prior to Governor in Council approval of the Amending Orders for CPCN EC-III-2 and CPCN EC-III-3. | Closed | Prior to the Construction Phase | Standard | Filing Required | Administrative
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 5 | Within 30 days of the date that the approved Project is placed in service, Algonquin shall file with the Board a set of final engineering documents including: a. a legible copy of the single line diagram;b. drawings for the new IPL 6901 and 6904 structures;c. a list of the new structures with their respective numbers; andd. the specification of the ACSR conductor. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 6 | Within 30 days of the date that the approved Project is placed in service, Algonquin shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Algonquin shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Algonquin. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Algonquin Tinker Gen Co. | Algonquin Tinker Gen Co. s. 21 application to amend EC-III-2 and EC-III-3 | Variance EC-III-2 and EC-III-3 | Completed | MO-039-2016 | Algonquin Tinker Gen Co. (Algonquin) Application to perform work on International Power Lines 6901 and 6904 pursuant to sections 45 and 58.27 of the National Energy Board Act (NEB Act), and to vary Certificates of Public Convenience and Necessity EC-III-2 and EC-III-3 pursuant to section 21(2) of the NEB Act (Application) | 2016-08-26 | 2016-08-26 | 2017-09-30 | All Conditions Met |  | 7 | Unless the Board otherwise directs prior to 30 September 2017, this Order shall expire on 30 September 2017 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
TAQA NORTH by its managing partner TAQA NORTH Ltd. | TAQA North amendment application for deactivation of the subject pipeline (Burnt Cabin Creek (Chinchaga) Loop) | Deactivate Burnt Cabin Creek Loop | Completed | MO-007-2016 | TAQA North Ltd. (TAQA) – Application to Deactivate the Burnt Cabin Creek (Chinchaga) Pipeline Loop (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-04-08 | 2016-04-08 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
TAQA NORTH by its managing partner TAQA NORTH Ltd. | TAQA North amendment application for deactivation of the subject pipeline (Burnt Cabin Creek (Chinchaga) Loop) | Deactivate Burnt Cabin Creek Loop | Completed | MO-007-2016 | TAQA North Ltd. (TAQA) – Application to Deactivate the Burnt Cabin Creek (Chinchaga) Pipeline Loop (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-04-08 | 2016-04-08 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA shall maintain the Burnt Cabin Creek (Chinchaga) Pipeline Loop in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
TAQA NORTH by its managing partner TAQA NORTH Ltd. | TAQA North amendment application for deactivation of the subject pipeline (Burnt Cabin Creek (Chinchaga) Loop) | Deactivate Burnt Cabin Creek Loop | Completed | MO-007-2016 | TAQA North Ltd. (TAQA) – Application to Deactivate the Burnt Cabin Creek (Chinchaga) Pipeline Loop (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-04-08 | 2016-04-08 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 3 | TAQA shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
TAQA NORTH by its managing partner TAQA NORTH Ltd. | TAQA North amendment application for deactivation of the subject pipeline (Burnt Cabin Creek (Chinchaga) Loop) | Deactivate Burnt Cabin Creek Loop | Completed | MO-007-2016 | TAQA North Ltd. (TAQA) – Application to Deactivate the Burnt Cabin Creek (Chinchaga) Pipeline Loop (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-04-08 | 2016-04-08 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 4 | Within 30 days after the date of this Order, TAQA shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, TAQA shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of TAQA. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Northern Blizzard Resources Inc. | Cuthbert 9-36 Gas Pipeline Deactivation | Deactivate Cuthbert 9-36 Pipeline | Completed | XG-N707-019-2012 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation of the Pipeline is approved, subject to the following conditions:... | 2012-12-24 | 2012-12-24 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard shall comply with all the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Northern Blizzard Resources Inc. | Cuthbert 9-36 Gas Pipeline Deactivation | Deactivate Cuthbert 9-36 Pipeline | Completed | XG-N707-019-2012 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation of the Pipeline is approved, subject to the following conditions:... | 2012-12-24 | 2012-12-24 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard shall cause the Pipeline to be deactivated in accordance with the specifications, standards, commitments, and other information referred to in its application or related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Northern Blizzard Resources Inc. | Cuthbert 9-36 Gas Pipeline Deactivation | Deactivate Cuthbert 9-36 Pipeline | Completed | XG-N707-019-2012 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation of the Pipeline is approved, subject to the following conditions:... | 2012-12-24 | 2012-12-24 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 3 | Northern Blizzard shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Northern Blizzard Resources Inc. | Cuthbert 9-36 Gas Pipeline Deactivation | Deactivate Cuthbert 9-36 Pipeline | Completed | XG-N707-019-2012 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation of the Pipeline is approved, subject to the following conditions:... | 2012-12-24 | 2012-12-24 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 4 | Within 30 days of the date of this Order, Northern Blizzard shall file with the Board a confirmation, by an officer of the company, that the approved deactivation was completed in compliance with all applicable conditions of this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Northern Blizzard Resources Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | Condition Compliance to Certificate OC-059 | Condition Compliance OC-059 | Completed | MO-005-2013 |  | 2013-01-21 | 2013-01-21 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage shall provide a comprehensive and dedicated on-site environmental training on or before 4 Feb 2013 to all Vantage staff and contractors involved in the construction of the Project, during which no construction activities will proceed. The syllabus of the training as well as an invitation for the Board to attend shall be provided to the NEB Operations Project Manager no later than seven calendar days prior to the date of training. | Closed | During Construction Phase | Standard | Filing Required | Environmental Protection
Vantage Pipeline Canada ULC | Condition Compliance to Certificate OC-059 | Condition Compliance OC-059 | Completed | MO-005-2013 |  | 2013-01-21 | 2013-01-21 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage shall select an independent third party auditor to audit its Environmental Protection Plan (EPP). Vantage shall file confirmation that the audit has been initiated as well as the auditor's qualifications, audit protocol, timelines and audit scope with the Board within 15 calendar days of the date of issuance of this Order. The auditor shall be independent of all parties involved in the development and implementation of the EPP to date. | Closed | During Construction Phase | Standard | Filing Required | Environmental Protection
Vantage Pipeline Canada ULC | Condition Compliance to Certificate OC-059 | Condition Compliance OC-059 | Completed | MO-005-2013 |  | 2013-01-21 | 2013-01-21 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Vantage shall file the third party audit report and a corrective action plan for approval by the Board, within 45 calendar days of the date of issuance of this Order. | Closed | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Vantage Pipeline Canada ULC | Condition Compliance to Certificate OC-059 | Condition Compliance OC-059 | Completed | MO-005-2013 |  | 2013-01-21 | 2013-01-21 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 4 | Construction activities shall not proceed in environmentally sensitive areas as described in the EPP and alignment sheets, until the Board is satisfied that:a) A site specific plan for construction activities is reviewed by the Vantage Environmental Inspector (EI);b) The EI has determined that the proposed activities will be completed in compliance with required environmental mitigation and commitments of the EPP; andc) The environmentally sensitive areas have been identified I marked as required by the EPP."" | Closed | Post Construction Phase | Standard | Filing Required | Environmental Protection
Vantage Pipeline Canada ULC | Condition Compliance to Certificate OC-059 | Condition Compliance OC-059 | Completed | MO-005-2013 |  | 2013-01-21 | 2013-01-21 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 5 | For each week where construction activity is planned to occur for the duration of the construction of the Project, Vantage shall file with the Board weekly Project construction updates, which shall include;a) A list of all locations identified by reference to kilometre post locations where construction activity in environmentally sensitive areas is anticipated to be conducted for the following week;b) A cross reference to any applicable mitigation measures described in the EPP for those areas and confirmation of the presence of Environmental Monitors for any planned activities, where required; andc) A copy of the updated Project Non-Compliance Summary Report."" | Closed | During Construction Phase | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Vantage Pipeline Canada ULC | Vantage s. 74 (1)(c) application to enter into an agreement to amalgamate with Pembina Prairie Facilities. | Amalgamate Vantage with Pembina Prairie as Pembina Prairie | Completed | AO-002-OC-059 | Leave to Enter into an Amalgamation Agreement, effectively transferring ownership of the Vantage Pipeline (Pipeline) to Pembina Prairie Facilities Ltd. (Application) under Paragraphs 74(1)(c) of the National Energy Board Act (NEB Act) | 2014-10-22 | 2015-05-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Pembina Prairie shall file, for approval, within 60 days of the date of the issuance of this Amending Order, a Management System and Program report that includes, but is not limited to:(a) an assessment of whether the operator’s management system and programs meet the Board’s requirements outlined in sections 6.1 to 6.6 of the NEB Onshore Pipeline Regulations (OPR), as well as the programs referred to in section 55 of the OPR;(b) a corrective action plan to address deficiencies, if identified in (a); and(c) a description of how Pembina Prairie will provide oversight over the operator so that it can make sure that:(i) The pipeline is operated in a manner that ensures the safety of people, security of the pipeline and protection of the environment; and(ii) The operation of the pipeline complies with the OPR. | Closed | Not Construction Related | Standard | Filing Not Required | Management System
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Sunoco Logistics Partners Operations GP LLC on behalf of Sunoco Pipeline LP | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Wild Stream Exploration Inc. | Transfer Board Order XG-R040-10-2003 | Variance XG-R040-10-2003 | Completed | AO-003-XG-R040-010-2003 | IT IS ORDERED THAT, pursuant to subsection 21(1) of the Act, Order AO-2-XG-R040-10-2003 is varied to change the name of the holder of the facilities set out in Schedule A from Eagle Rock to WSX, subject to the following condition: a. Within 15 days from the date of this Amending Order, WSX shall file three copies of its Emergency Preparedness and Response Plan(s) as required by the Onshore Pipeline Regulations, 1999. | 2010-11-15 | 2010-11-15 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1:00 | Within 15 days from the date of this Amending Order, WSX shall file three copies of its Emergency Prepardness and Response Plan(s) as required by the Onshore Pipeline Regulations, 1999. | Closed | Post Construction Phase | Standard | Filing Not Required | Emergency Management
Bellatrix Exploration Ltd. | Bellatrix Exploration Ltd. s. 44 Deactivation of Cypress Merryflat pipeline | Deactivate Cypress Merryflat Pipeline | Completed | MO-044-2016 | Bellatrix Exploration Ltd. (Bellatrix) – Cypress Merryflat Pipeline Deactivation (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-05 | 2016-10-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Bellatrix Exploration Ltd. | Bellatrix Exploration Ltd. s. 44 Deactivation of Cypress Merryflat pipeline | Deactivate Cypress Merryflat Pipeline | Completed | MO-044-2016 | Bellatrix Exploration Ltd. (Bellatrix) – Cypress Merryflat Pipeline Deactivation (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-05 | 2016-10-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix shall maintain the Cypress Merryflat Pipeline in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Bellatrix Exploration Ltd. | Bellatrix Exploration Ltd. s. 44 Deactivation of Cypress Merryflat pipeline | Deactivate Cypress Merryflat Pipeline | Completed | MO-044-2016 | Bellatrix Exploration Ltd. (Bellatrix) – Cypress Merryflat Pipeline Deactivation (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-05 | 2016-10-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 3 | Bellatrix shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Bellatrix Exploration Ltd. | Bellatrix Exploration Ltd. s. 44 Deactivation of Cypress Merryflat pipeline | Deactivate Cypress Merryflat Pipeline | Completed | MO-044-2016 | Bellatrix Exploration Ltd. (Bellatrix) – Cypress Merryflat Pipeline Deactivation (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-05 | 2016-10-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 4 | Within 30 days after the date of this Order, Bellatrix shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Bellatrix shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Bellatrix, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 1 | Plains shall comply with all the conditions contained in this order unless the Board directs otherwise | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 2 | Plains shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments, and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 4 | Plains shall file with the Board, at least 10 days prior to the planned start of construction, an updated, project-specific Environmental Protection Plan (EPP) and associated Environmental Alignment Sheets. This EPP shall be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Plains’ application for the Project, subsequent filings, and related submissions as well as through consultation with government agencies. Plains shall not deviate from the terms of the filed Plan without prior approval from the Board.The EPP shall address, but is not limited to, the following elements:a) Environmental procedures including site-specific plans, criteria forimplementation of these procedures, mitigation measures and monitoringapplicable to all project phases, and activities;b) Environmental Alignment Sheets which include each of the locationswhere mitigation measures are to be implemented (e.g., delineation offencing for weeds, rare plants and wetlands; equipment cleaning stations;watercourse crossing methods etc.); andc) A reclamation plan which includes a description of the condition to which the applicant intends to reclaim and maintain the right-of-way once the construction has been completed, and a description of measurable goals for reclamation. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 5 | On or before 31 January after each of the first, third, fifth and tenth complete growing seasons following the commencement of operation of the Project, Plains shall file with the Board, a post-construction monitoring report that:a) Describes the methodology used for monitoring, the criteria established for evaluating success and the results found;b) Identifies the issues to be monitored, including but not limited tounexpected issues that arose during construction, and their locations (e.g., on a map or diagram, in a table);c) Describes the current status of the issues (resolved or unresolved), any deviations from plans and corrective actions undertaken;d) Assesses the effectiveness of mitigation (planned and corrective) measures applied against the criteria for success;e) Includes details of consultation undertaken with appropriate provincial and federal authorities;f) Provides proposed measures and the schedule that Plains wouldimplement to address ongoing issues or concerns; andg) Includes an assessment of wetland habitat and native prairie habitat.The report shall address, but not be limited to, issues pertaining to wetland health and functionality; soil productivity, erosion and compaction; reclamation of native prairie, weeds, rare plant species and species at risk. | In Progress | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 6 | Plains shall file with the Board a Construction Safety Manual 14 days prior to the commencement of construction activities. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Safety Management
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 7 | Plains shall file with the Board, at least 14 days prior to the commencement of construction:a) A copy of the correspondence from Alberta Culture confirming that Plains has obtained all archaeological and heritage resources permits and clearances; andb) A statement on how Plains intends to implement any recommendations contained in a) above. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 8 | Plains shall file with the Board, within 30 days of the date that the approved Project is placed in service, a confirmation that the approved Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Plains shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Milk River Pipeline Replacement | Replace Milk River Pipeline | In Progress | XO-P384-011-2012 | Application Pursuant to Section 58 of the National Energy Board Act (NEB Act) to Construct and Operate a Pipeline to Replace Plains’ existing Milk River Pipeline (Milk River Pipeline Replacement or Project) | 2012-08-20 | 2012-08-20 | 2013-08-13 | In Progress | Lethbridge--Medicine Hat/Alberta | 9 | Unless the Board otherwise directs prior to 20 August 2013, this Order shall expire on 20 August 2013, unless construction in respect of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-3 Facilities | Deactivate Windsor E-3 Facilities | Completed | MO-001-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-3 Facilities | Deactivate Windsor E-3 Facilities | Completed | MO-001-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall cause the Windsor E-3 Facilities to be deactivated and maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-3 Facilities | Deactivate Windsor E-3 Facilities | Completed | MO-001-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-3 Facilities | Deactivate Windsor E-3 Facilities | Completed | MO-001-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | i) If the Windsor E-3 facilities are not reactivated within 180 days of the approval of the Deactivation, Plains Midstream Canada ULC shall file with the NEB within that time an Environmental Monitoring Plan that shall include but is not limited to:a) identification and discussion of all potential environmental hazards and risks associated with past and on-going activities related to the deactivated facilities, taking mitigation measures into account;b) a description of, and rationale for, the proposed monitoring of each described hazard/risk identified above, including monitoring to determine the success of mitigation, detailing:1) which mediums will be monitored;2) proposed monitoring methods;3) location(s) and frequency of monitoring; and4) the duration of monitoring;c) contingency plan(s) for dealing with adverse or unexpected monitoring results, including thresholds that trigger contingency responses; andd) content and schedule for Environmental Monitoring Summary Reports to be filed with the NEB.ii) If the facilities are reactivated within 180 days of the approval of the Deactivation, Plains Midstream Canada ULC shall file with the NEB within that time a letter noting that the above Environmental Monitoring Plan is not required."" | Closed | Unspecified | Standard | Filing Not Required | Environmental Protection
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-3 Facilities | Deactivate Windsor E-3 Facilities | Completed | MO-001-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 5 | If Condition 4 i) in this Order is applicable, Plains shall file with the NEB the Environmental Monitoring Summary Reports described in that Plan and in conformity with the schedule in that Plan. | Closed | Unspecified | Standard | Filing Not Required | Environmental Protection
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-3 Facilities | Deactivate Windsor E-3 Facilities | Completed | MO-001-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 6 | Within 30 days of the date of the approval of the Deactivation, Plains shall file with the Board a confirmation, by an officer of Plains, that the approved Deactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-5 Facilities | Deactivate Windsor E-5 Facilities | Completed | MO-003-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-5 Facilities | Deactivate Windsor E-5 Facilities | Completed | MO-003-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall cause the Windsor E-5 Facilities to be deactivated and maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-5 Facilities | Deactivate Windsor E-5 Facilities | Completed | MO-003-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-5 Facilities | Deactivate Windsor E-5 Facilities | Completed | MO-003-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | i) If the Windsor E-5 facilities are not reactivated within 180 days of the approval of the Deactivation, Plains Midstream Canada ULC shall file with the NEB within that time an Environmental Monitoring Plan that shall include but is not limited to:a) identification and discussion of all potential environmental hazards and risks associated with past and on-going activities related to the deactivated facilities, taking mitigation measures into account;b) a description of, and rationale for, the proposed monitoring of each described hazard/risk identified above, including monitoring to determine the success of mitigation, detailing:1) which mediums will be monitored;2) proposed monitoring methods;3) location(s) and frequency of monitoring; and4) the duration of monitoring;c) contingency plan(s) for dealing with adverse or unexpected monitoring results, including thresholds that trigger contingency responses; andd) content and schedule for Environmental Monitoring Summary Reports to be filed with the NEB.ii) If the facilities are reactivated within 180 days of the approval of the Deactivation, Plains Midstream Canada ULC shall file with the NEB within that time a letter noting that the above Environmental Monitoring Plan is not required."" | Closed | Unspecified | Standard | Filing Not Required | Environmental Protection
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-5 Facilities | Deactivate Windsor E-5 Facilities | Completed | MO-003-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 5 | If Condition 4 i) in this Order is applicable, Plains shall file with the NEB the Environmental Monitoring Summary Reports described in that Plan and in conformity with the schedule in that Plan. | Closed | Unspecified | Standard | Filing Required | Environmental Protection
Plains Midstream Canada ULC | Application of Plains Midstream Canada ULC for Leave to Deactivate Windsor E-5 Facilities | Deactivate Windsor E-5 Facilities | Completed | MO-003-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 6 | Within 30 days of the date of the approval of the Deactivation, Plains shall file with the Board a confirmation, by an officer of Plains, that the approved Deactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer ofthe company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall cause the Project to be maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 4 | Plains shall file with the Board for review, an engineering assessment of the EDSS in accordance with the Canadian Standards Association Z662-11 and OPR-99 at least one month prior the commencement of operation. | Closed | During Construction Phase | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 5 | Plains shall file with the Board for review, the results of the pressure test and inline inspection of the EDSS in accordance with the Canadian Standards Association Z662-11 and OPR-99 at least one month prior the commencement of operation. | Closed | During Construction Phase | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 6 | Within 30 days of the date that the approved reactivation is completed, Plains shall file with the Board a confirmation, by an officer of Plains, that the approved reactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - EDS-S Reactivation Application | Reactivate EDS-S | Completed | MO-035-2012 | Application pursuant to section 45 of the Onshore Pipeline Regulations, 1999 (OPR-99) to Reactivate the Eastern Delivery System South (Project) | 2012-11-22 | 2012-11-22 | 2013-11-22 | All Conditions Met | Windsor--Sarnia/Ontario | 7 | Unless the Board otherwise directs prior to 22 November 2013, this Order shall expire on 22 November 2013, unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all ofthe conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall cause the Windsor E-3 Facilities to be reactivated and maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | Plains shall file with the Board for review, an engineering assessment of the E-3 Cavern in accordance with the Canadian Standards Association Z341-10 and OPR-99, at least 30 days prior the commencement of operation. | Closed | Unspecified | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 5 | Plains shall file with the Board for review, the results of the Mechanical Integrity Testing of the E-3 Cavern in accordance with the Canadian Standards Association Z341-10 and OPR-99, at least 30 days prior the commencement of operation. | Closed | Unspecified | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 6 | Within 30 days of the date the Reactivation is completed, Plains shall file with the Board a confirmation, by an officer of Plains, that the approved Reactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E3 Cavern | Reactivate Windsor E3 Cavern | Completed | MO-002-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 7 | Unless the Board otherwise directs prior to 18 January 2014, this Order shall expire on 18 January 2014, unless the Reactivation has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board directs otherwise. | Closed | Not Construction Related | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall cause the Windsor E-5 Facilities to be reactivated and maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | Plains shall file with the Board for review, an engineering assessment of the E-5 Cavern in accordance with the Canadian Standards Association Z341-IO and OPR-99 at least 30 days prior to the commencement of operation. | Closed | Unspecified | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 5 | Plains shall file with the Board for review, the results of the Mechanical Integrity Testing of the E-5 Cavern in accordance with the Canadian Standards Association Z341-10 and OPR-99 at least 30 days prior to the commencement of operation. | Closed | Unspecified | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 6 | Within 30 days of the date the Reactivation is completed, Plains shall file with the Board a confirmation, by an officer of Plains, that the approved Reactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains. | Closed | Post Construction Phase | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application for Reactivation of Windsor E 5 Cavern | Reactivate Windsor E5 Cavern | Completed | MO-004-2013 |  | 2013-01-18 | 2013-01-18 |  | All Conditions Met | Windsor--Sarnia/Ontario | 7 | Unless the Board otherwise directs prior to 18 January 2014, this Order shall expire on 18 January 2014, unless the Reactivation has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Plains Midstream Requesting the Variance of Additional Orders and Certificates | Variance Orders and Certificates | Completed | AO-001-MO-011-2012 |  | 2013-08-01 | 2013-08-01 |  | All Conditions Met | Windsor--Sarnia/Ontario | 6 | Conduct an In Line Inspection Program (i.e. ILI run, excavation and validation) using high resolution mechanical finger (geometry) and Ultrasonic Crack Detection ILI technologies and ensuring that data integration analysis and evaluation of dents in proximity to metal loss seam and girth weld are conducted. Plains shall file the results of the In Line Inspection Program with the Board by 31 December 2004. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains updated s. 21 Wascana Pipeline Application for variation to Order No. MO-52-76, revised for bi-directional service. | Variance MO-52-76 | Completed | AO-001-MO-52-76 |  | 2013-05-03 | 2013-05-03 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Plains must fulfill the requirements of Order SO-P384-004-2011 before commencing bi-directional flow on the Wascana Pipeline. | Closed | Not Construction Related | Standard | Filing Required | Administrative, Integrity Management
Plains Midstream Canada ULC | Plains updated s. 21 Wascana Pipeline Application for variation to Order No. MO-52-76, revised for bi-directional service. | Variance MO-52-76 | Completed | AO-001-MO-52-76 |  | 2013-05-03 | 2013-05-03 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Plains shall notify all oil producers and marketers operating in Southern Saskatchewan, and who are not Enbridge Mainline Shippers, of Plains&rsquo; plans for bi-directional service on the Wascana Pipeline. Within 45 days of the date of this Order, Plains shall file with the Board.<br />a) a summary of the methods used to notify these oil producers and marketers;<br />b) a summary of the comments and inquiries received; and<br />c) any follow-up steps that Plains has taken or will take with these oil producers and marketers. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | Plains updated s. 21 Wascana Pipeline Application for variation to Order No. MO-52-76, revised for bi-directional service. | Variance MO-52-76 | Completed | AO-001-MO-52-76 |  | 2013-05-03 | 2013-05-03 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Within 45 days prior to commencing bi-directional flow, Plains shall conduct a Management of Change assessment on its Environmental, Health and Safety and Emergency Management programs, plans and procedures and file, for Board approval, the results of this assessment including, but not limited to:<br />a) a listing of the programs, plans and procedures that were evaluated;<br />b) any potential or related changes caused and/or considered;<br />c) any existing practices or controls that make new changes unnecessary; and<br />d) a listing of the required changes and the timeframe for implementation. | Closed | Not Construction Related | Standard | Filing Not Required | Management System, Safety Management
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | Plains Midstream s. 44 OPR application to deactivate sections of the Milk River Pipeline System | Deactivate sections of Milk River Pipeline | Completed | MO-007-2014 | IT IS ORDERED that, pursuant to section 20 of the NEB Act, and section 44 of the OPR, the applied-for deactivations, as specified in Schedule A, are approved subject to the following conditions:... | 2014-02-07 | 2014-02-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream s. 44 OPR application to deactivate sections of the Milk River Pipeline System | Deactivate sections of Milk River Pipeline | Completed | MO-007-2014 | IT IS ORDERED that, pursuant to section 20 of the NEB Act, and section 44 of the OPR, the applied-for deactivations, as specified in Schedule A, are approved subject to the following conditions:... | 2014-02-07 | 2014-02-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Plains shall maintain the deactivated Pipelines in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Plains Midstream s. 44 OPR application to deactivate sections of the Milk River Pipeline System | Deactivate sections of Milk River Pipeline | Completed | MO-007-2014 | IT IS ORDERED that, pursuant to section 20 of the NEB Act, and section 44 of the OPR, the applied-for deactivations, as specified in Schedule A, are approved subject to the following conditions:... | 2014-02-07 | 2014-02-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Plains Midstream Canada ULC | Plains request to lift the pressure restriction Safety Order SO-P384-004-2011, Wascana crude oil mainline | Increase MOP Wascana Mainline | Completed | SO-P384-001-2014 |  | 2015-03-17 | 2015-03-17 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | 1. (a) Nine (9) months after returning the Wascana crude oil pipeline to service, Plains shall re-assess the remaining fatigue life estimations for cracks and the unrepaired dents using the appropriate weighting for the number of cycles associated with each direction of flow. (b) Plains shall file with the Board a report respecting the re-assessment no later than twelve (12) months after returning the Wascana crude oil pipeline to service. The report shall include the results of the re-assessment and mitigation measures that address threats to the pipeline identified in the re-assessment. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains request to lift the pressure restriction Safety Order SO-P384-004-2011, Wascana crude oil mainline | Increase MOP Wascana Mainline | Completed | SO-P384-001-2014 |  | 2015-03-17 | 2015-03-17 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | 2. (a) Plains shall re-inspect the Wascana crude oil mainline for corrosion metal loss no later than 31 October 2015. After conducting the re-inspection, Plains shall conduct an assessment of the fitness-for-purpose for corrosion metal loss of the Wascana crude oil mainline. (b) Within six (6) months after conducting the re-inspection, Plains shall file with the Board a report respecting the assessment of the fitness-for-purpose for corrosion metal loss of the Wascana crude oil mainline. The report shall include field data validation results and the corrosion growth. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains request to lift the pressure restriction Safety Order SO-P384-004-2011, Wascana crude oil mainline | Increase MOP Wascana Mainline | Completed | SO-P384-001-2014 |  | 2015-03-17 | 2015-03-17 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | 3. (a) Plains shall conduct a baseline crack in-line inspection on the Wascana crude oil mainline no later than 31 December 2015. (b) Within six (6) months after conducting the baseline crack in-line inspection, Plains shall file with the Board a report that summarizes the findings of the inspection and includes the mitigation measures required to maintain the integrity of the pipeline. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains request to lift the pressure restriction Safety Order SO-P384-004-2011, Wascana crude oil mainline | Increase MOP Wascana Mainline | Completed | SO-P384-001-2014 |  | 2015-03-17 | 2015-03-17 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | 4. (a) Plains shall conduct a depth of cover survey on the Wascana crude oil mainline including water crossings no later than 31 December 2014. (b) Within three (3) months after conducting the survey, Plains shall file with the Board the results of the survey. The results of the survey shall include the mitigation measures required to maintain a proper depth of cover over the pipeline. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC – 2010 Management and Protection Program Audit – Corrective Action Plan (CAP) Implementation Assessment | Management System CAP - Plains Midstream | In Progress | SO-P384-001-2015 | Approved at Special Board Meeting of 13-JAN-2015. | 2015-01-15 | 2015-01-15 |  | In Progress | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Saskatoon--Biggar/Saskatchewan, Southwest /Manitoba, Windsor--Sarnia/Ontario, Camrose--Drumheller/Alberta | 1 | Prior to 31 January 2015, Plains shall file, for Board approval:<br />(a) A listing of the safety critical tasks and the rationale for how these tasks were identified;<br />(b) Operational controls used to mitigate the hazards and risks associated with the identified safety critical tasks; and<br />(c) Demonstration of the process that will be used for the revision and maintenance of these controls to ensure their adequacy and effectiveness on an on-going basis. | Closed | Not Construction Related | Standard | Filing Not Required | Enforcement, Safety Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC – 2010 Management and Protection Program Audit – Corrective Action Plan (CAP) Implementation Assessment | Management System CAP - Plains Midstream | In Progress | SO-P384-001-2015 | Approved at Special Board Meeting of 13-JAN-2015. | 2015-01-15 | 2015-01-15 |  | In Progress | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Saskatoon--Biggar/Saskatchewan, Southwest /Manitoba, Windsor--Sarnia/Ontario, Camrose--Drumheller/Alberta | 2 | Plains shall contract an independent third party expert to conduct an audit of its management system and Environmental Protection Program, as required in section 53 and 55 of the Onshore Pipeline Regulations (OPR), in order to assess the adequacy, implementation and effectiveness of Plains&rsquo; pipeline system and ensure compliance with the OPR, including the identification of any deficiencies:<br />(a) Prior to 28 February 2015, Plains shall file, for Board approval, the name and qualifications of the independent third party expert(s) as well as the scope and protocol to be utilized for the audit;<br />(b) The independent third party expert(s) shall submit all draft and partial reports to both Plains and the Board simultaneously;<br />(c) Prior to 30 November 2015, the independent third party expert(s) shall submit the final report(s) to both Plains and the Board simultaneously; and<br />(d) Prior to 31 December 2015, Plains shall file a response to the independent third party expert(s) report(s) with the Board. Plains&rsquo; response shall include the rationale for the exclusion or acceptance of any deficiencies identified by the third party expert(s). Where accepted, a corrective action plan, including timelines for implementation, shall be provided. | Closed | Not Construction Related | Standard | Filing Not Required | Management System, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC – 2010 Management and Protection Program Audit – Corrective Action Plan (CAP) Implementation Assessment | Management System CAP - Plains Midstream | In Progress | SO-P384-001-2015 | Approved at Special Board Meeting of 13-JAN-2015. | 2015-01-15 | 2015-01-15 |  | In Progress | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Saskatoon--Biggar/Saskatchewan, Southwest /Manitoba, Windsor--Sarnia/Ontario, Camrose--Drumheller/Alberta | 3 | Prior to 30 April 2015, Plains shall file, for Board approval, its quality assurance program as required by section 6.5(1) (w) of the OPR. | In Progress | Not Construction Related | Standard | Filing Not Required | Management System, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC – 2010 Management and Protection Program Audit – Corrective Action Plan (CAP) Implementation Assessment | Management System CAP - Plains Midstream | In Progress | SO-P384-001-2015 | Approved at Special Board Meeting of 13-JAN-2015. | 2015-01-15 | 2015-01-15 |  | In Progress | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Saskatoon--Biggar/Saskatchewan, Southwest /Manitoba, Windsor--Sarnia/Ontario, Camrose--Drumheller/Alberta | 4 | Plains shall contract an independent third party expert to conduct an audit of its Integrity Management Program, as required in section 53 and 55 of the OPR, in order to assess the adequacy, implementation and effectiveness Plains&rsquo; pipeline systems and ensure compliance with the OPR, including the identification of any deficiencies:<br />(a) Prior to 28 February 2016, Plains shall file, for Board approval, the name and qualifications of the independent third party expert(s) as well as the scope and protocol to be utilized for the audit;<br />(b) The independent third party expert(s) shall submit all draft and partial reports to both Plains and the Board simultaneously;<br />(c) Prior to 30 November 2016, the independent third party expert(s) shall submit the final report(s) to both Plains and the Board simultaneously; and<br />(d) Prior to 31 December 2016, Plains shall file a response to the independent third party expert(s) report(s) with the Board. Plains&rsquo; response shall include the rationale for the exclusion or acceptance of any deficiencies identified by the third party expert(s). Where accepted, a corrective action plan, including timelines for implementation, shall be provided. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC – 2010 Management and Protection Program Audit – Corrective Action Plan (CAP) Implementation Assessment | Management System CAP - Plains Midstream | In Progress | SO-P384-001-2015 | Approved at Special Board Meeting of 13-JAN-2015. | 2015-01-15 | 2015-01-15 |  | In Progress | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Saskatoon--Biggar/Saskatchewan, Southwest /Manitoba, Windsor--Sarnia/Ontario, Camrose--Drumheller/Alberta | 5 | Plains shall ensure that all filings associated with the conditions of this Order are reviewed and approved by its Accountable Officer and confirmation of this will be filed with the Board. | In Progress | Not Construction Related | Non Standard | Filing Not Required | Standard Condition, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC – 2010 Management and Protection Program Audit – Corrective Action Plan (CAP) Implementation Assessment | Management System CAP - Plains Midstream | In Progress | SO-P384-001-2015 | Approved at Special Board Meeting of 13-JAN-2015. | 2015-01-15 | 2015-01-15 |  | In Progress | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Saskatoon--Biggar/Saskatchewan, Southwest /Manitoba, Windsor--Sarnia/Ontario, Camrose--Drumheller/Alberta | 6 | Prior to 31 March 2015 and continuing quarterly until all conditions on this Order have been met, Plains shall coordinate quarterly meetings with Board staff to discuss the progress of its management system, performance of its management and protection programs and the status of any corrective and preventative actions. | In Progress | Not Construction Related | Standard | Filing Required | Management System, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application to reactivate the Eastern Delivery System South - Conditions 4 & 5 Filing and s. 47 application for Leave to Open of Amended Order AO-001-MO-035-2012. | Leave to Open Eastern Delivery System South | In Progress | OPLO-P384-002-2015 | IT IS ORDERED THAT Plains is granted leave to open the EDSS for the transmission of natural gas liquids at a maximum operating pressure of 8460 kPa, subject to the following conditions:... | 2015-03-13 | 2015-03-13 |  | In Progress | Windsor--Sarnia/Ontario | 1 | Plains shall file with the Board by 31 December 2017 and 31 December 2022, engineering assessments for the EDSS pipeline in accordance with the most current version of Canadian Standard Association Standard Z662 and the National Energy Board Onshore Pipeline Regulations that demonstrate the pipeline is fit for service at the current or the operating pressure in force at that time. | In Progress | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application to reactivate the Eastern Delivery System South - Conditions 4 & 5 Filing and s. 47 application for Leave to Open of Amended Order AO-001-MO-035-2012. | Leave to Open Eastern Delivery System South | In Progress | OPLO-P384-002-2015 | IT IS ORDERED THAT Plains is granted leave to open the EDSS for the transmission of natural gas liquids at a maximum operating pressure of 8460 kPa, subject to the following conditions:... | 2015-03-13 | 2015-03-13 |  | In Progress | Windsor--Sarnia/Ontario | 2 | Plains shall file with the Board a Crack-like Anomaly Assessment within one year of commencing operation. The Crack-like Anomaly Assessment will take into account the past year of operational pressure cycling. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application to reactivate the Eastern Delivery System South - Conditions 4 & 5 Filing and s. 47 application for Leave to Open of Amended Order AO-001-MO-035-2012. | Leave to Open Eastern Delivery System South | In Progress | OPLO-P384-002-2015 | IT IS ORDERED THAT Plains is granted leave to open the EDSS for the transmission of natural gas liquids at a maximum operating pressure of 8460 kPa, subject to the following conditions:... | 2015-03-13 | 2015-03-13 |  | In Progress | Windsor--Sarnia/Ontario | 3 | Plains shall file with the Board, within 30 days of receipt of this Order, an explanation of why the 2013 annual survey cathodic protection on/off potentials start to converge at mile post 0.81 and why they are identical at mile post 0.97 and mile post 1.00. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Application to reactivate the Eastern Delivery System South - Conditions 4 & 5 Filing and s. 47 application for Leave to Open of Amended Order AO-001-MO-035-2012. | Leave to Open Eastern Delivery System South | In Progress | OPLO-P384-002-2015 | IT IS ORDERED THAT Plains is granted leave to open the EDSS for the transmission of natural gas liquids at a maximum operating pressure of 8460 kPa, subject to the following conditions:... | 2015-03-13 | 2015-03-13 |  | In Progress | Windsor--Sarnia/Ontario | 4 | Plains shall file with the Board, within 20 days of commencing operation, a statement signed by Plains’ Accountable Officer stating the EDSS pipeline is fit for service and safe to operate at the requested operating pressure. | Closed | Post Construction Phase | Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Plains s. 44 OPR application to deactivate the Aurora NPS 8 pipeline, OC-11 | Deactivate Aurora NPS 8 pipeline | Completed | MO-065-2015 |  | 2015-11-25 | 2015-11-25 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Aurora shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains s. 44 OPR application to deactivate the Aurora NPS 8 pipeline, OC-11 | Deactivate Aurora NPS 8 pipeline | Completed | MO-065-2015 |  | 2015-11-25 | 2015-11-25 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Aurora shall maintain the Aurora NPS 8 pipeline in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Plains s. 44 OPR application to deactivate the Aurora NPS 8 pipeline, OC-11 | Deactivate Aurora NPS 8 pipeline | Completed | MO-065-2015 |  | 2015-11-25 | 2015-11-25 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 3 | Aurora shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Plains Midstream Canada ULC | Plains s. 44 OPR application to deactivate the Aurora NPS 8 pipeline, OC-11 | Deactivate Aurora NPS 8 pipeline | Completed | MO-065-2015 |  | 2015-11-25 | 2015-11-25 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 4 | Within 30 days after the date of this Order, Aurora shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Aurora shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Aurora. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada s. 58 Application Regina Terminal Tank CRTK-124 | Construct Regina Terminal Tank CRTK-124 | Completed | XO-P384-002-2016 | Application for the Regina Terminal Tank CRTK-124 (Project) under section 58 of the National Energy Board Act (NEB Act) | 2016-02-04 | 2016-02-05 | 2017-02-04 | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Plains Midstream shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada s. 58 Application Regina Terminal Tank CRTK-124 | Construct Regina Terminal Tank CRTK-124 | Completed | XO-P384-002-2016 | Application for the Regina Terminal Tank CRTK-124 (Project) under section 58 of the National Energy Board Act (NEB Act) | 2016-02-04 | 2016-02-05 | 2017-02-04 | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Plains Midstream shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada s. 58 Application Regina Terminal Tank CRTK-124 | Construct Regina Terminal Tank CRTK-124 | Completed | XO-P384-002-2016 | Application for the Regina Terminal Tank CRTK-124 (Project) under section 58 of the National Energy Board Act (NEB Act) | 2016-02-04 | 2016-02-05 | 2017-02-04 | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Plains Midstream shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Plains Midstream Canada ULC | Plains Midstream Canada s. 58 Application Regina Terminal Tank CRTK-124 | Construct Regina Terminal Tank CRTK-124 | Completed | XO-P384-002-2016 | Application for the Regina Terminal Tank CRTK-124 (Project) under section 58 of the National Energy Board Act (NEB Act) | 2016-02-04 | 2016-02-05 | 2017-02-04 | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | Within 30 days of the date that the approved Project is placed in service, Plains Midstream shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Plains Midstream shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Plains Midstream. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada s. 58 Application Regina Terminal Tank CRTK-124 | Construct Regina Terminal Tank CRTK-124 | Completed | XO-P384-002-2016 | Application for the Regina Terminal Tank CRTK-124 (Project) under section 58 of the National Energy Board Act (NEB Act) | 2016-02-04 | 2016-02-05 | 2017-02-04 | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 5 | Unless the Board otherwise directs prior to 4 February 2017, this Order shall expire on 4 February 2017 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Variance Request to Safety Order SO-P384-001-2014 -Extension to Condition 2b and 3b Deadline. | Variance SO-P384-001-2014 Condition 2b and 3b Extension | Completed | AO-001-SO-P384-001-2014 | Variance Request to Safety Order SO-P384-001-2014 (Order) Extension to Condition 2b and 3b deadline | 2016-02-05 | 2016-02-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 b | 2(b) No later than 30 April 2016, Plains shall file with the Board a report respecting the assessment of the fitness-for-purpose for corrosion metal loss of the Wascana crude oil mainline. The report shall include field data validation results and the corrosion growth. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC - Variance Request to Safety Order SO-P384-001-2014 -Extension to Condition 2b and 3b Deadline. | Variance SO-P384-001-2014 Condition 2b and 3b Extension | Completed | AO-001-SO-P384-001-2014 | Variance Request to Safety Order SO-P384-001-2014 (Order) Extension to Condition 2b and 3b deadline | 2016-02-05 | 2016-02-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 b | 3(b) No later than 30 April 2016, Plains shall file with the Board a report that summarizes the findings of the baseline crack in-line inspection and includes the mitigation measures required to maintain the integrity of the pipeline. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management, Enforcement
Plains Midstream Canada ULC | Plains Midstream Canada ULC. s. 58 Windsor Terminal Reconfiguration Project | Upgrade Windsor Terminal | Completed | XO-P384-011-2016 | Plains Midstream Canada ULC (Plains) Windsor Terminal Reconfiguration Project Application under section 58 of the National Energy Board Act (NEB Act) | 2016-05-16 | 2016-05-16 | 2017-05-16 | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC. s. 58 Windsor Terminal Reconfiguration Project | Upgrade Windsor Terminal | Completed | XO-P384-011-2016 | Plains Midstream Canada ULC (Plains) Windsor Terminal Reconfiguration Project Application under section 58 of the National Energy Board Act (NEB Act) | 2016-05-16 | 2016-05-16 | 2017-05-16 | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Plains Midstream Canada ULC | Plains Midstream Canada ULC. s. 58 Windsor Terminal Reconfiguration Project | Upgrade Windsor Terminal | Completed | XO-P384-011-2016 | Plains Midstream Canada ULC (Plains) Windsor Terminal Reconfiguration Project Application under section 58 of the National Energy Board Act (NEB Act) | 2016-05-16 | 2016-05-16 | 2017-05-16 | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Plains Midstream Canada ULC | Plains Midstream Canada ULC. s. 58 Windsor Terminal Reconfiguration Project | Upgrade Windsor Terminal | Completed | XO-P384-011-2016 | Plains Midstream Canada ULC (Plains) Windsor Terminal Reconfiguration Project Application under section 58 of the National Energy Board Act (NEB Act) | 2016-05-16 | 2016-05-16 | 2017-05-16 | All Conditions Met | Windsor--Sarnia/Ontario | 4 | Within 30 days of the date that the approved Project is placed in service, Plains shall file with the Board a confirmation that the approved Project was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, Plains shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Plains, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream Canada ULC. s. 58 Windsor Terminal Reconfiguration Project | Upgrade Windsor Terminal | Completed | XO-P384-011-2016 | Plains Midstream Canada ULC (Plains) Windsor Terminal Reconfiguration Project Application under section 58 of the National Energy Board Act (NEB Act) | 2016-05-16 | 2016-05-16 | 2017-05-16 | All Conditions Met | Windsor--Sarnia/Ontario | 5 | Unless the Board otherwise directs prior to 16 May 2017, this Order shall expire on 16 May 2017 unless construction of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Kinder Morgan Cochin ULC and Plains Midstream Canada ULC s. 74 Application to transfer 1.6 K.M. of Cochin Pipeline to Plains | Transfer Cochin Pipeline from Kinder Morgan to Plains | Completed | MO-015-2017 | Kinder Morgan Cochin ULC (Kinder Morgan Cochin) and Plains Midstream Canada ULC (Plains Midstream) Application to Transfer to Plains Midstream a 1.6 km segment of the Cochin Pipeline and Associated Piping and Facilities (pipeline segment) under Subsection 74(1) of the National Energy Board Act (NEB Act) | 2017-04-07 | 2017-04-07 | 2017-06-07 | All Conditions Met | Edmonton/Alberta | 1 | Within 60 days of the date of the Order, Kinder Morgan Cochin must file a revised executed Cochin Pipeline Reclamation Trust Agreement for Board approval. Schedule A of the revised executed trust agreement must reflect the transfer of the pipeline segment from Kinder Morgan Cochin to Plains Midstream. | Closed | Post Construction Phase | Standard | Filing Not Required | Financial
Plains Midstream Canada ULC | Kinder Morgan Cochin ULC and Plains Midstream Canada ULC s. 74 Application to transfer 1.6 K.M. of Cochin Pipeline to Plains | Transfer Cochin Pipeline from Kinder Morgan to Plains | Completed | MO-015-2017 | Kinder Morgan Cochin ULC (Kinder Morgan Cochin) and Plains Midstream Canada ULC (Plains Midstream) Application to Transfer to Plains Midstream a 1.6 km segment of the Cochin Pipeline and Associated Piping and Facilities (pipeline segment) under Subsection 74(1) of the National Energy Board Act (NEB Act) | 2017-04-07 | 2017-04-07 | 2017-06-07 | All Conditions Met | Edmonton/Alberta | 2 | Unless the Board otherwise directs, this Order shall expire on 7 June 2017 unless the Applicants confirm that the transaction has been completed. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Plains Midstream- Application to Vary Condition 7 of Order MO-035-2012, to extend sunset Clause to 30 April 2014. | Variance Condition 7 MO-035-2012 to Extend Sunset Clause | Completed | AO-001-MO-035-2012 |  | 2013-06-10 | 2013-06-10 | 2013-04-30 | All Conditions Met | Windsor--Sarnia/Ontario | 7 | Unless the Board otherwise directs prior to 30 April 2014, this Order shall expire on&nbsp;30 April 2014, unless the Project has commenced by that date. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Sunset Clause
Plains Midstream Canada ULC | Plains Midstream s. 74 (1)(c) application for Plains Midstream Empress Management ULC to amalgamate with Plains Midstream Canada ULC | Amalgamate PMEM ULC with PMC ULC as Plains Midstream Canada ULC | Completed | AO-006-GC-19 | Confirmation of the amalgamation of Plains Midstream Empress Management ULC (PMEM ULC) and Plains Midstream Canada ULC (PMCULC) and variance of Certificate of Public Convenience and Necessity GC-19 pursuant to subsection 21(2) of the National Energy Board Act (NEB Act) | 2017-06-23 | 2017-06-23 |  | In Progress | North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | <p>Plains Midstream Canada ULC shall comply with all of the conditions contained in Certificate GC-19, as amended, unless the Board otherwise directs.</p> | Closed | Unspecified | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream s. 74 (1)(c) application for Plains Midstream Empress Management ULC to amalgamate with Plains Midstream Canada ULC | Amalgamate PMEM ULC with PMC ULC as Plains Midstream Canada ULC | Completed | AO-006-GC-19 | Confirmation of the amalgamation of Plains Midstream Empress Management ULC (PMEM ULC) and Plains Midstream Canada ULC (PMCULC) and variance of Certificate of Public Convenience and Necessity GC-19 pursuant to subsection 21(2) of the National Energy Board Act (NEB Act) | 2017-06-23 | 2017-06-23 |  | In Progress | North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | <p>Plains Midstream Canada ULC shall file with the Board, no later than 90 days of the issuance of this Amending Order, confirmation that all facility signage has been changed to reflect new ownership and include current emergency response numbers.</p> | Closed | Unspecified | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream s. 74 (1)(c) application for Plains Midstream Empress Management ULC to amalgamate with Plains Midstream Canada ULC | Amalgamate PMEM ULC with PMC ULC as Plains Midstream Canada ULC | Completed | AO-006-GC-19 | Confirmation of the amalgamation of Plains Midstream Empress Management ULC (PMEM ULC) and Plains Midstream Canada ULC (PMCULC) and variance of Certificate of Public Convenience and Necessity GC-19 pursuant to subsection 21(2) of the National Energy Board Act (NEB Act) | 2017-06-23 | 2017-06-23 |  | In Progress | North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 3 | <p>Plains Midstream Canada ULC shall file with the Board, no later than 45 days from the issuance of this Amending Order, confirmation that all records pursuant to CSA Z662 and paragraphs 56(e) to 56(g) of the <em>National Energy Board Onshore Pipeline Regulations </em>have been received from Plains Midstream Empress Management ULC.</p> | Closed | Unspecified | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Plains Midstream s. 74 (1)(c) application for Plains Midstream Empress Management ULC to amalgamate with Plains Midstream Canada ULC | Amalgamate PMEM ULC with PMC ULC as Plains Midstream Canada ULC | Completed | AO-006-GC-19 | Confirmation of the amalgamation of Plains Midstream Empress Management ULC (PMEM ULC) and Plains Midstream Canada ULC (PMCULC) and variance of Certificate of Public Convenience and Necessity GC-19 pursuant to subsection 21(2) of the National Energy Board Act (NEB Act) | 2017-06-23 | 2017-06-23 |  | In Progress | North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 4 | <p>Within 90 days of the date of this Amending Order, Plains Midstream Canada ULC shall file with the Board a confirmation that the transfer of the PTC Pipeline was completed in compliance with all applicable conditions contained in this Amending Order and all applicable directions contained in the Board&rsquo;s letter dated 23 June 2017. If compliance with any of these conditions cannot be confirmed, Plains Midstream Canada ULC shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Plains Midstream Canada ULC, appointed as Accountable Officer pursuant to s.6.2 of the OPR.</p> | Closed | Unspecified | Non Standard | Filing Not Required | Standard Condition
Plains Midstream Canada ULC | Kinder Morgan Utopia Ltd. and Plains Midstream Canada ULC s. 74 Joint Application Regarding Transfer of Utopia Pipeline section to Plains Midstream and vary Certificates of Public Convenience and Necessity OC-29 and OC-52 to reflect the transfer. | Transfer Utopia Pipeline from Kinder Morgan to Plains Midstream | Completed | XO-P384-003-2018 | Confirmation of the Transfer of a 0.15 kilometre Segment of the Utopia Pipeline and Associated Piping and Facilities (Pipeline Segment) from Kinder Morgan Utopia Ltd. (Kinder Morgan) to Plains Midstream Canada ULC (Plains) pursuant to subsection 21(1) and section 58 of the National Energy Board Act (NEB Act) | 2018-03-01 | 2018-03-01 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Plains shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Expiry Date of Reg. Instr. | Non Standard | Filing Required | Standard Condition
Plains Midstream Canada ULC | Kinder Morgan Utopia Ltd. and Plains Midstream Canada ULC s. 74 Joint Application Regarding Transfer of Utopia Pipeline section to Plains Midstream and vary Certificates of Public Convenience and Necessity OC-29 and OC-52 to reflect the transfer. | Transfer Utopia Pipeline from Kinder Morgan to Plains Midstream | Completed | XO-P384-003-2018 | Confirmation of the Transfer of a 0.15 kilometre Segment of the Utopia Pipeline and Associated Piping and Facilities (Pipeline Segment) from Kinder Morgan Utopia Ltd. (Kinder Morgan) to Plains Midstream Canada ULC (Plains) pursuant to subsection 21(1) and section 58 of the National Energy Board Act (NEB Act) | 2018-03-01 | 2018-03-01 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Plains shall file with the Board, no later than 90 days after the issuance of this Order, confirmation that all facility signage has been changed to reflect new ownership and include current emergency response numbers. | Closed | Not Construction Related | Non Standard | Filing Not Required | Damage Prevention
Plains Midstream Canada ULC | Kinder Morgan Utopia Ltd. and Plains Midstream Canada ULC s. 74 Joint Application Regarding Transfer of Utopia Pipeline section to Plains Midstream and vary Certificates of Public Convenience and Necessity OC-29 and OC-52 to reflect the transfer. | Transfer Utopia Pipeline from Kinder Morgan to Plains Midstream | Completed | XO-P384-003-2018 | Confirmation of the Transfer of a 0.15 kilometre Segment of the Utopia Pipeline and Associated Piping and Facilities (Pipeline Segment) from Kinder Morgan Utopia Ltd. (Kinder Morgan) to Plains Midstream Canada ULC (Plains) pursuant to subsection 21(1) and section 58 of the National Energy Board Act (NEB Act) | 2018-03-01 | 2018-03-01 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Plains shall file with the Board, no later than 45 days after the issuance of this Order, confirmation that all records pursuant to CSA Z662 and paragraphs 56(e) to 56(g) of the <em>National Energy Board Onshore Pipeline Regulations </em>(OPR) have been received from Kinder Morgan. | Closed | Not Construction Related | Non Standard | Filing Not Required | Integrity Management
Plains Midstream Canada ULC | Kinder Morgan Utopia Ltd. and Plains Midstream Canada ULC s. 74 Joint Application Regarding Transfer of Utopia Pipeline section to Plains Midstream and vary Certificates of Public Convenience and Necessity OC-29 and OC-52 to reflect the transfer. | Transfer Utopia Pipeline from Kinder Morgan to Plains Midstream | Completed | XO-P384-003-2018 | Confirmation of the Transfer of a 0.15 kilometre Segment of the Utopia Pipeline and Associated Piping and Facilities (Pipeline Segment) from Kinder Morgan Utopia Ltd. (Kinder Morgan) to Plains Midstream Canada ULC (Plains) pursuant to subsection 21(1) and section 58 of the National Energy Board Act (NEB Act) | 2018-03-01 | 2018-03-01 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | Within 90 days after the issuance of this Order on 1 March 2018, Plains shall file with the Board a confirmation that the transfer of the Pipeline Segment was completed in compliance with all applicable conditions contained in this Order and all applicable directions contained in the cover letter accompanying this Order. If compliance with any of these conditions cannot be confirmed, Plains shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Plains, appointed as Accountable Officer pursuant to section 6.2 of the OPR. | Closed | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Shell Canada Products, an Alberta general partnership by it's managing partner, Shell Canada Limited | Deactivation of Sections B, C & D of the Salmon Pipelines | Deactivate Sections Sections B, C & D of Salmon Pipelines | Completed | MO-013-2011 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation is approved, subject to the conditions below:... | 2011-05-17 | 2011-05-17 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell shall comply with all of the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Shell Canada Products, an Alberta general partnership by it's managing partner, Shell Canada Limited | Deactivation of Sections B, C & D of the Salmon Pipelines | Deactivate Sections Sections B, C & D of Salmon Pipelines | Completed | MO-013-2011 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation is approved, subject to the conditions below:... | 2011-05-17 | 2011-05-17 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell shall cause the Pipeline to be deactivated and maintained in accordance with the specifications, standards and other information referred to in its application or related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Shell Canada Products, an Alberta general partnership by it's managing partner, Shell Canada Limited | Deactivation of Sections B, C & D of the Salmon Pipelines | Deactivate Sections Sections B, C & D of Salmon Pipelines | Completed | MO-013-2011 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation is approved, subject to the conditions below:... | 2011-05-17 | 2011-05-17 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Shell shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Shell Canada Products, an Alberta general partnership by it's managing partner, Shell Canada Limited | Deactivation of Sections B, C & D of the Salmon Pipelines | Deactivate Sections Sections B, C & D of Salmon Pipelines | Completed | MO-013-2011 | IT IS ORDERED that, pursuant to section 44 of the OPR-99, the deactivation is approved, subject to the conditions below:... | 2011-05-17 | 2011-05-17 |  | All Conditions Met | Windsor--Sarnia/Ontario | 4 | Within 30 days of the date that the approved deactivation is completed, Shell shall file with the Board a confirmation, by an officer of the company, that the approved deactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. on behalf of Enbridge Bakken Pipeline Limited Partnership and Enbridge Pipelines (Westspur) Inc. Joint Application for Transfer of Ownership of a Portion of Line EX-02. | Transfer Portion of Line EX-02 from Enbridge Bakken to Enbridge Westspur | In Progress | AO-003-XO-W2-2-96 | Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership (Enbridge Bakken) and TEML Westspur Pipelines Limited (TEML) formerly Enbridge Pipelines Westspur Inc. (Enbridge Westspur) Transfer Ownership of a Portion of Line EX-02 (The Project) Application under paragraph 74(1)(a) and (b) and section 21 (1) of the National Energy Board Act (NEB Act) | 2017-07-28 | 2017-07-28 |  | In Progress | Regina--Moose Mountain/Saskatchewan | 1 | TEML shall comply with all of the conditions contained in Order XO-W2-96, asamended, unless the Board otherwise directs. | Closed | Not Construction Related | Non Standard | Filing Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. on behalf of Enbridge Bakken Pipeline Limited Partnership and Enbridge Pipelines (Westspur) Inc. Joint Application for Transfer of Ownership of a Portion of Line EX-02. | Transfer Portion of Line EX-02 from Enbridge Bakken to Enbridge Westspur | In Progress | AO-003-XO-W2-2-96 | Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership (Enbridge Bakken) and TEML Westspur Pipelines Limited (TEML) formerly Enbridge Pipelines Westspur Inc. (Enbridge Westspur) Transfer Ownership of a Portion of Line EX-02 (The Project) Application under paragraph 74(1)(a) and (b) and section 21 (1) of the National Energy Board Act (NEB Act) | 2017-07-28 | 2017-07-28 |  | In Progress | Regina--Moose Mountain/Saskatchewan | 2 | TEML shall file with the Board, no later than 90 days of the issuance of thisAmending Order, confirmation that all facility signage has been changed to reflectnew ownership and include current emergency response numbers. | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. on behalf of Enbridge Bakken Pipeline Limited Partnership and Enbridge Pipelines (Westspur) Inc. Joint Application for Transfer of Ownership of a Portion of Line EX-02. | Transfer Portion of Line EX-02 from Enbridge Bakken to Enbridge Westspur | In Progress | AO-003-XO-W2-2-96 | Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership (Enbridge Bakken) and TEML Westspur Pipelines Limited (TEML) formerly Enbridge Pipelines Westspur Inc. (Enbridge Westspur) Transfer Ownership of a Portion of Line EX-02 (The Project) Application under paragraph 74(1)(a) and (b) and section 21 (1) of the National Energy Board Act (NEB Act) | 2017-07-28 | 2017-07-28 |  | In Progress | Regina--Moose Mountain/Saskatchewan | 3 | TEML shall file with the Board, no later than 45 days from the issuance of thisAmending Order, confirmation that all records pursuant to CSA Z662 and paragraphs 56(e) to 56(g) of the National Energy Board Onshore Pipeline Regulations have been received from Enbridge Bakken. | In Progress | Not Construction Related | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. on behalf of Enbridge Bakken Pipeline Limited Partnership and Enbridge Pipelines (Westspur) Inc. Joint Application for Transfer of Ownership of a Portion of Line EX-02. | Transfer Portion of Line EX-02 from Enbridge Bakken to Enbridge Westspur | In Progress | AO-003-XO-W2-2-96 | Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership (Enbridge Bakken) and TEML Westspur Pipelines Limited (TEML) formerly Enbridge Pipelines Westspur Inc. (Enbridge Westspur) Transfer Ownership of a Portion of Line EX-02 (The Project) Application under paragraph 74(1)(a) and (b) and section 21 (1) of the National Energy Board Act (NEB Act) | 2017-07-28 | 2017-07-28 |  | In Progress | Regina--Moose Mountain/Saskatchewan | 4 | Within 90 days of the date of this Amending Order, TEML shall file with the Board aconfirmation that the transfer of the portion of Line EX-02 was completed incompliance with all applicable conditions contained in this Amending Order and allapplicable directions contained in the Board’s letter dated 28 July 2017. Ifcompliance with any of these conditions cannot be confirmed, TEML shall file withthe Board details as to why compliance cannot be confirmed. The filing required bythis condition shall include a statement confirming that the signatory to the filing isthe accountable officer of TEML, appointed as Accountable Officer pursuant to s.6.2of the OPR. | In Progress | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | MO-025-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must comply with all of the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | MO-025-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Enbridge Bakken must cause the segment of Line EX-02 to be deactivated and maintained in accordance with the specifications, standards, commitments made and other information referred to in its application and related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | MO-025-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken must implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures and its commitments for the protection of the environment included in or referred to in its application or related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | MO-025-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | Within 30 days of the date that the approved Deactivation Activities are completed, Enbridge Bakken must file with the Board a confirmation, by an officer of the company, that the approved Deactivation Activities were completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company must file with the Board details as to why compliance cannot be confirmed. The filing required by this condition must include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 10 | In the event of construction or clearing activities within restricted activity periods for non-migratory birds protected under federal and provincial jurisdiction and for migratory birds, Enbridge Bakken must retain a qualified avian biologist to carry out a pre-construction survey to identify any birds and active nests in areas immediately surrounding the site(s) and must file the following with the Board within 15 days following the commencement of these construction or clearing activities:a) the results of the survey;b) mitigation, including monitoring, developed in consultation with Environment Canada, the Canadian Wildlife Service and the appropriate provincial government authorities to protect any identified migratory and non-migratory birds and their nests;c) mitigation, including monitoring, developed in consultation with Environment Canada and the Canadian Wildlife Service to protect any identified Species at Risk Act- (SARA-) listed birds and their nests; andd) evidence to confirm that the appropriate federal and provincial government authorities were consulted on the proposed methodology for the survey, the results of the survey and the mitigation and monitoring to be used, and a description of any outstanding concerns they may have."" | Closed | During Construction Phase | Standard | Filing Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 11 | Enbridge Bakken must file with the Board the following programs within the time specified:a) field joining program – 14 days prior to joining; andb) field pressure testing program – 14 days prior to pressure test." Closed" | During Construction Phase | Standard | Filing Not Required | Integrity Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 12 | Enbridge Bakken must file construction progress reports with the Board on a monthly basis in a form satisfactory to the Board. The reports must include:a) information on the activities carried out during the reporting period, any environmental, socio-economic, security and safety issues and issues of non-compliance, and the measures undertaken for the resolution of each issue and non-compliance; andb) information on consultation activities undertaken with stakeholders and Aboriginal groups for the Section 58 Facilities during construction, including a summary of any issues or concerns raised and a description of how any concerns or issues were addressed."" | Closed | During Construction Phase | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 13 | Within 30 days of the date that the approved Section 58 Facilities is completed, Enbridge Bakken must file with the Board a confirmation, by an officer of the company, that the approved Section 58 Facilities were completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company must file with the Board details as to why compliance cannot be confirmed. The filing required by this condition must include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 14 | Unless the Board otherwise directs prior to 22 December 2012, this Order will expire on 22 December 2012, unless construction in respect of the Section 58 Facilities has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Enbridge Bakken must cause the approved Section 58 Facilities to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or as otherwise agreed to during questioning or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken must implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or as otherwise agreed to during questioning or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | Enbridge Bakken must:a) file with the Board, at least 14 days prior to commencing construction, an updated Commitments Tracking Table;b) update the status of the commitments in a) on a monthly basis until completion of the Section 58 Facilities; andc) maintain at its construction office(s):i) the relevant environmental portion of the Commitments Tracking Table listing all regulatory commitments, including but not limited to, those commitments resulting from Enbridge Bakken’s application and subsequent filings, and conditions from permits, authorizations and approvals;ii) copies of any permits, approvals or authorizations for the Section 58 Facilities issued by federal, provincial or other permitting authorities, which include environmental conditions or site-specific mitigation or monitoring measures; andiii) any subsequent variances to any permits, approvals or authorizations in ii)." Closed" | Prior to the Construction Phase | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 5 | Enbridge Bakken must file with the Board for approval, at least 45 days prior to commencing construction, an updated Environmental Protection Plan (EPP), including an Environmental Plot Plan, for the Section 58 Facilities. This EPP must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Enbridge Bakken 's application for the Project, its subsequent filings, evidence collected during the hearing process, or as otherwise agreed to during questioning or in its related submissions during the OH-01-2011 proceeding. The EPP must subsequently be updated to include any additional measures arising from all outstanding pre-construction field studies. Construction cannot begin until the Board approves the final updated EPP.The EPP must include, but not be limited to, the following elements:a) environmental procedures, including site-specific plans, criteria for implementation of these procedures, mitigation measures and monitoring applicable to the Section 58 Facilities and activities;b) a wetland reclamation plan which includes a description of the condition to which Enbridge Bakken intends to reclaim and maintain the wetlands once construction has been completed; andc) evidence of consultation with appropriate federal and provincial government authorities that indicates their views on the EPP." Closed" | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 6 | Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, a Security Management Plan for construction activities pursuant to NEB Proposed Regulatory Change (PRC) 2010-01, Pipeline Security Management Program. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Security
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 7 | Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, a Construction Safety Manual. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Safety Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 8 | Enbridge Bakken must file with the Board, at least 30 days prior to commencing construction, the wetland compensation plan and evidence demonstrating consultation with appropriate federal and provincial government authorities indicating their views on the methodology and results of the plan. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | XO-E256-007-2011 | Approval of Reasons for Decision OH-001-2011 | 2012-03-01 | 2011-12-22 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 9 | Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, a detailed construction schedule(s) identifying major construction activities and must notify the Board of any modifications to the schedule(s) as such modifications occur. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | 1. Enbridge Bakken must comply with all of the conditions contained in this Certificate unless the Board otherwise directs."" | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 10 | 10. Enbridge Bakken must file with the Board, at least 15 days prior to commencingconstruction:a) the results of the confirmatory surveys for SARA-listed wildlife species,including northern leopard frog and Sprague’s pipit;b) a detailed mitigation plan for each of the SARA-listed wildlife speciesaffected by construction and operation activities;c) evidence of consultation with appropriate federal and provincial governmentauthorities and copies of correspondence from these government authoritiesindicating their views on the proposed mitigation; andd) confirmation that the EPP and Environmental Alignment Sheets have beenupdated to include the mitigation measures developed or recommended as aresult of the survey findings in consultation with the government authorities."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 11 | 11. Enbridge Bakken must file with the Board and MDWS, at least 15 days prior to commencing construction, the methodology for conducting the wetland survey, the results of the survey and evidence demonstrating consultation with appropriate federal and provincial government authorities indicating their views on the methodology and results ofthe survey."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 12 | 12. Enbridge Bakken must file with the Board for approval, at least 30 days prior to commencing construction, a detailed weed management plan. This plan must describe Enbridge Bakken’s immediate and long-term weed control and monitoring procedures, treatment decision criteria and accountabilities for the construction and operations phases of the Section 52 Facilities as well as for the immediate post-construction reclamationperiod. The filed plan must include evidence that it was designed in consultation with any concerned landowners and federal and provincial government authorities."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 13 | 13. Enbridge Bakken must file with the Board, at least 30 days prior to commencing construction:a) A copy of the letter of clearance received from Saskatchewan Tourism; Parks Culture and Sport – Heritage Conservation Branch; and Manitoba Culture, Heritage and Tourism; andb) A statement of how Enbridge Bakken intends to address any recommendations or comments contained in a)."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Socio-Economic
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 14 | 14. Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, confirmation that all third party crossing agreements have been acquired. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Damage Prevention
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 15 | 15. Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, a detailed construction schedule(s) identifying major construction activities and must notify the Board of any modifications to the schedule(s) as such modifications occur. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Integrity Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 16 | 16. In the event of construction or clearing activities within restricted activity periods for all migratory birds, and non-migratory birds protected provincial jurisdiction, Enbridge Bakken must retain a qualified avian biologist to carry out a preconstruction survey to identify any birds and active nests in areas immediately surrounding the site(s) and must file the following with the Board within 15 days following the commencement of these construction or clearing activities:a) the results of the survey;b) mitigation, including monitoring, developed in consultation with Environment Canada, the Canadian Wildlife Service and the appropriate provincial government authorities to protect any identified migratory and non-migratory birds and their nests;c) mitigation, including monitoring, developed in consultation with Environment Canada and the Canadian Wildlife Service to protect any identified SARA listed birds and their nests; andd) evidence to confirm that the appropriate federal and provincial government authorities were consulted on the proposed methodology for the survey, the results of the survey and the mitigation and monitoring to be used, and a description of any outstanding concerns they may have."" | Closed | Prior to the Construction Phase | Standard | Filing Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 17 | 17. Enbridge Bakken must file with the Board the following programs within the time specified:a) field joining program – 14 days prior to joining; andb) field pressure testing program – 14 days prior to pressure test."" | Closed | During Construction Phase | Standard | Filing Not Required | Integrity Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 18 | 18. Enbridge Bakken must file construction progress reports with the Board on a monthly basis in a form satisfactory to the Board. The reports must include:a) information on the activities carried out during the reporting period, anyenvironmental, socio-economic, security and safety issues and issues of noncompliance, and the measures undertaken for the resolution of each issue and noncompliance; andb) information on consultation activities undertaken with stakeholders and Aboriginal groups for the Section 52 Facilities during construction, including a summary of any issues or concerns raised and a description of how any concerns or issues were addressed."" | Closed | During Construction Phase | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 19 | 19. Enbridge Bakken must file with the Board, at least 14 days prior to applying for Leave to Open, three updated copies of its Emergency Preparedness and Response Manual. | Closed | During Construction Phase | Standard | Filing Not Required | Emergency Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | 2. Enbridge Bakken must cause the approved Section 52 Facilities to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments made and other information referred to in its application or as otherwise agreed to during questioning or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 20 | &quot;20. On or before the 31st of January following each of the first, third and fifth growing seasons after the completion of right-of-way reclamation and final clean-up activities for the Project, Enbridge Bakken must file with the Board and appropriate federal and provincial government authorities, a Post-Construction Environmental Monitoring Report that:a) describes the methodology used for monitoring, the criteria used forevaluating success and the results found;b) assesses the effectiveness of the mitigation measures applied duringconstruction against the criteria for success;c) identifies any deviations from plans and alternate mitigation applied;d) identifies locations (e.g., on a map or diagram, in a table) whereenvironmental issues arose during construction and where corrective actionswere taken;e) identifies the current status of the issues identified (resolved or unresolved);f) includes details of consultation undertaken with appropriate provincial andfederal authorities; andg) provides proposed measures and the schedule that Enbridge Bakken willimplement to address any unresolved issues or concerns.&quot; | Closed | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 21 | 21. Within one year following the close of the five-year post-construction monitoring program, Enbridge Bakken must file with the Board and appropriate federal and provincial government authorities including MDWS, a Wetland Restoration/Compensation Plan for the Project for all wetlands where wetland function has not been fully restored by the close of the program. This plan must include evidence that it was developed in consultation with appropriate federal and provincial government authorities, as well as details of any proposed alternatives to the above authorities&rsquo; recommendations and the rationale for proposing those alternatives. | Closed | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 22 | 22. Within 30 days of the date that the approved Project is placed in service, Enbridge Bakken must file with the Board a confirmation, by an officer of the company, that the approved Project was completed in compliance with all applicable conditions in this Certificate. If compliance with any of these conditions cannot be confirmed, the officer of the company must file with the Board details as to why compliance cannot be confirmed. The filing required by this condition must include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 23 | Unless the Board otherwise directs prior to 22 December 2012, this Certificate will expire on 22 December 2012, unless construction in respect of the Section 52 Facilities has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | 3. Enbridge Bakken must implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or as otherwise agreed to during questioning or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | 4. Enbridge Bakken must:a) file with the Board, at least 14 days prior to commencing construction, an updated Commitments Tracking Table;b) update the status of the commitments in a) on a monthly basis until completion of the Section 52 Facilities; andc) maintain at its construction office(s):i) the relevant environmental portion of the Commitments Tracking Table listing all regulatory commitments, including but not limited to, those commitments resulting from Enbridge Bakken’s application and subsequent filings, and conditions from permits, authorizations and approvals;ii) copies of any permits, approvals or authorizations for the Section 52 Facilities issued by federal, provincial or other permitting authorities, which include environmental conditions or site-specific mitigation or monitoring measures; andiii) any subsequent variances to any permits, approvals or authorizations in ii)."" | Closed | Includes all Phases of Constr. | Standard | Filing Not Required | Administrative
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 5 | 5. Enbridge Bakken must file with the Board for approval, at least 45 days prior to commencing construction, an updated Environmental Protection Plan (EPP), including Environmental Alignment Sheets, for the Section 52 Facilities. This EPP must be a comprehensive compilation of all environmental protection procedures, mitigation measures, and monitoring commitments, as set out in Enbridge Bakken 's application for the Project, its subsequent filings, evidence collected during the hearing process, or as otherwise agreed to during questioning or in its relatedsubmissions during the OH-01-2011 proceeding. The EPP and Environmental Alignment Sheets must subsequently be updated to include any additional measures arising from all outstanding pre-construction filed studies. Construction cannot begin until the Board approves the final updated EPP.The EPP must include, but not be limited to, the following elements:a) environmental procedures, including site-specific plans, criteria forimplementation of these procedures, mitigation measures and monitoringapplicable to all Section 52 Facilities and activities;b) a reclamation plan which includes a description of the condition to which Enbridge Bakken intends to reclaim and maintain the right-of-way once construction has been completed, and a description of measurable goals for reclamation;c) a wetland mitigation plan which includes the criteria used, and the rationale for selecting those criteria, in determining the crossing methods and mitigation measures to be employed; andd) evidence of consultation with appropriate federal and provincial government authorities indicating their views on the EPP, including information provided in c).Any filings pertaining to this condition must also be submitted to appropriate federal and provincial authorities (including Manitoba Department of Water Stewardship [MWDS]), unless those authorities have specifically asked not to receive such filings."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 6 | 6. Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, a Security Management Plan for construction activities pursuant to NEB Proposed Regulatory Change (PRC) 2010-01, Pipeline Security Management Program. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Security
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 7 | 7. Enbridge Bakken must file with the Board, at least 14 days prior to commencing construction, a Construction Safety Manual. | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Safety Management
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 8 | 8. Enbridge Bakken must file with the Board either:a) upon successful completion of the horizontal directionally drilled (HDD)watercourse crossings for Alameda Reservoir West, Alameda Reservoir East and Pipestone Creek, confirmation of their completion; orb) in the event of any changes to the proposed HDD watercourse crossingmethod for Alameda Reservoir West, Alameda Reservoir East and Pipestone Creek, at least 10 days prior to crossing,i) notification in writing of any such change(s) and the rationale for thechange(s);ii) evidence of consultation with appropriate federal and provincialgovernment authorities and provide copies of all relevantcorrespondence from them, including approvals for amendedwatercourse crossing methods; andiii) file a description of amended reclamation and re-vegetation measures, and fish and fish habitat monitoring for the affected watercourse crossings."" | Closed | During Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken Pipeline Company Inc. - Bakken Pipeline Project Canada (OH-01-2011) | Construct Bakken Pipeline | Completed | OC-058 | Pursuant to Section 52 of the NEB Act Bakken Pump Station and Facilities at the existing Enbridge Pipelines Cromer Terminal | 2012-03-01 | 2012-03-08 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 9 | 9. Enbridge Bakken must file with the Board, at least 30 days prior to starting each pre-construction survey for SARA-listed wildlife species:a) the methodology(ies) for conducting the confirmatory surveys for SARA- listed wildlife species (including northern leopard frog and Sprague’s pipit); andb) a summary of consultation on the methodology with appropriate federal and provincial government authorities, including copies of correspondence from these government authorities regarding the methodology(ies)."" | Closed | Prior to the Construction Phase | Standard | Filing Not Required | Environmental Protection
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken s. 74(1)(a) application for leave to transfer the ownership of the Canadian portion of Line EX-01 from Enbridge Westspur to Enbridge Bakken. | Transfer Line EX-01 from Enbridge Westspur to Enbridge Bakken | Completed | AO-002-XO-2-71 | Enbridge Pipelines (Westspur) Inc. (“Enbridge Westspur”) and Enbridge Bakken Pipeline Company Inc., (“Enbridge Bakken”) on behalf of Enbridge Bakken Pipeline Limited Partnership (“Bakken LP”) Transfer of ownership of a portion of Line EX 01 (“the Pipeline”) Application under paragraphs 74(1) (a) and (b) of the National Energy Board Act (NEB Act) | 2017-06-26 | 2017-06-26 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | <p>Enbridge Bakken shall comply with all of the conditions contained in Order XO-2-71, as amended, unless the Board otherwise directs.</p> | Closed | Includes all Phases of Constr. | Standard | Filing Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken s. 74(1)(a) application for leave to transfer the ownership of the Canadian portion of Line EX-01 from Enbridge Westspur to Enbridge Bakken. | Transfer Line EX-01 from Enbridge Westspur to Enbridge Bakken | Completed | AO-002-XO-2-71 | Enbridge Pipelines (Westspur) Inc. (“Enbridge Westspur”) and Enbridge Bakken Pipeline Company Inc., (“Enbridge Bakken”) on behalf of Enbridge Bakken Pipeline Limited Partnership (“Bakken LP”) Transfer of ownership of a portion of Line EX 01 (“the Pipeline”) Application under paragraphs 74(1) (a) and (b) of the National Energy Board Act (NEB Act) | 2017-06-26 | 2017-06-26 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | <p>Enbridge Bakken shall file with the Board, no later than 90 days of the issuance of this Amending Order, confirmation that all facility signage has been changed to reflect new ownership and include current emergency response numbers.</p> | Closed | Not Construction Related | Non Standard | Filing Not Required | Damage Prevention, Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken s. 74(1)(a) application for leave to transfer the ownership of the Canadian portion of Line EX-01 from Enbridge Westspur to Enbridge Bakken. | Transfer Line EX-01 from Enbridge Westspur to Enbridge Bakken | Completed | AO-002-XO-2-71 | Enbridge Pipelines (Westspur) Inc. (“Enbridge Westspur”) and Enbridge Bakken Pipeline Company Inc., (“Enbridge Bakken”) on behalf of Enbridge Bakken Pipeline Limited Partnership (“Bakken LP”) Transfer of ownership of a portion of Line EX 01 (“the Pipeline”) Application under paragraphs 74(1) (a) and (b) of the National Energy Board Act (NEB Act) | 2017-06-26 | 2017-06-26 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | <p>Enbridge Bakken shall file with the Board, no later than 45 days from the issuance of this Amending Order, confirmation that all records pursuant to CSA Z662 and paragraphs 56(e) to 56(g) of the <em>National Energy Board Onshore Pipeline Regulations </em>have been received from Enbridge Westspur.</p> | Closed | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Enbridge Bakken Pipeline Company Inc., on behalf of Enbridge Bakken Pipeline Limited Partnership | Enbridge Bakken s. 74(1)(a) application for leave to transfer the ownership of the Canadian portion of Line EX-01 from Enbridge Westspur to Enbridge Bakken. | Transfer Line EX-01 from Enbridge Westspur to Enbridge Bakken | Completed | AO-002-XO-2-71 | Enbridge Pipelines (Westspur) Inc. (“Enbridge Westspur”) and Enbridge Bakken Pipeline Company Inc., (“Enbridge Bakken”) on behalf of Enbridge Bakken Pipeline Limited Partnership (“Bakken LP”) Transfer of ownership of a portion of Line EX 01 (“the Pipeline”) Application under paragraphs 74(1) (a) and (b) of the National Energy Board Act (NEB Act) | 2017-06-26 | 2017-06-26 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | <p>Within 90 days of the date of this Amending Order, Enbridge Bakken shall file with the Board a confirmation that the transfer of the Pipeline was completed in compliance with all applicable conditions contained in this Amending Order and all applicable directions contained in the Board&rsquo;s letter dated 26 June 2017. If compliance with any of these conditions cannot be confirmed, Enbridge Bakken shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of Enbridge Bakken, appointed as Accountable Officer pursuant to Section 6.2 of the OPR.</p> | Closed | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Terra Energy Corp. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Enerplus shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Enerplus shall cause the Pipeline to be abandoned in accordance with the specifications, standards, commitments made, and other information referred to in its Application, or in its related submissions. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition, Environmental Protection
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 3 | Enerplus shall implement or cause to be implemented, all of the policies, practices, programs, mitigation measures, recommendations, procedures, and its commitments for the protection of the environment included in or referred to in the Application, or in its related submissions. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition, Environmental Protection
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 4 | Enerplus shall file with the Board, at least fifteen days prior to commencing abandonment activities, an Environmental Protection Plan (EP Plan) for the Project. The EP Plan shall communicate its environmental protection procedures and monitoring commitments to employees and contractors. The EP Plan shall also describe the environmental protection procedures and measures used to mitigate environmental impacts from the abandonment activities associated with this Project, including, but not limited to:a) spill prevention and response procedures;b) confirmation that a wildlife survey will be conducted prior to commencing abandonment activities and a commitment that appropriate mitigation measures required to protect any species at risk identified during the wildlife survey will be implemented; andc) a post-abandonment monitoring schedule to assess the success of reclamation at disturbed areas. | Closed | Abandonment | Standard | Filing Not Required | Environmental Protection
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 5 | a) Within two years of completion of abandonment activities, Enerplus shall submit to the Board for approval, a Post Abandonment Report for the Pipeline. The Post Abandonment Report shall include but not be limited to:a.1) a Phase 1 Environmental Site Assessment, conducted to describe any historical contamination associated with the Pipeline; andIf further assessment is required base on conclusions of the Phase 1 Assessment:a.2) a Phase 2 Environmental Site Assessment; based on visual, olfactory or analytical observations of contamination made during abandonment activities; andIf remediation is required based on the conclusions drawn in a.2),a.3) a remediation report confirming that all contamination has been remediated to the most stringent federal or provincial environmental criteria. The report must include a description of all applied remedial activities and a summary of the methods and results of any soil and ground water sampling and analyses conducted; andb) A report demonstrating that the areas of the Pipeline RoW in both Alberta and Saskatchewan disturbed during abandonment activities meet reclamation criteria defined in Alberta Environment’s 2010 Reclamation Criteria for Wellsites and Associated Facilities (or applicable updates). If reclamation criteria are not met based on the provincial criteria cited above, Enerplus shall describe what additional reclamation work will be undertaken or provide justification as to why additional work is not warranted. | Closed | Abandonment | Standard | Filing Not Required | Environmental Protection
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 6 | Enerplus shall file with the Board, at least seven days prior to the planned start of abandonment activities confirmation of whether an archaeological field assessment was required for the Project, and if applicable;a) the results of the archaeological field assessment;b) a copy of any correspondence from provincial authorities confirming that Enerplus has obtained all of the required archeological and heritage resource permits and clearances; andc) a statement confirming how Enerplus proposes to address any comments and recommendations from provincial authorities. | Closed | Abandonment | Standard | Filing Not Required | Socio-Economic
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 7 | Enerplus shall file with the Board, within two years of the date of completion of all abandonment activities, confirmation, by an officer of the company, that the Project was completed, and that all abandonment activities were conducted in compliance with the conditions of this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition must include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Abandonment | Non Standard | Filing Not Required | Standard Condition
Enerplus Corporation acting on behalf of the Enerplus Partnership | Enerplus Corp s. 74 (1) (d) application for Abandonment of the Maple Creek Pipeline from 11-36-011-01 W4 to 08-02-012-30 W3 which crosses the Alberta-Saskatchewan border | Abandon Maple Creek Pipeline | Completed | ZO-E257-002-2013 | IT IS ORDERED pursuant to paragraph 74(1)(d) of the NEB Act, that Enerplus is granted leave abandon the Pipeline; IT IS FURTHER ORDERED that pursuant to subsection 19(1) of the NEB Act, this Order shall come into force upon the performance, to the satisfaction of the Board, of the following conditions:... | 2013-11-26 | 2013-11-26 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 8 | Unless the Board otherwise directs prior to 26 November 2014, this Order shall expire on 26 November 2014, unless abandonment activities in respect of the Project have commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
FortisBC Huntingdon Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | Deactivation of NEB Pipeline relating to Order AO-002-XO-T097-001-2003 | Deactivate AO-002-XO-T097-001-2003 | Completed | MO-024-2012 | application pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 for Deactivation of the Sour Oil Pipeline Located From 04-20-082-13W5 To 15-17-082-13W6 (the Pipeline). | 2012-07-13 | 2012-07-13 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Bonavista shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Bonavista Energy Corporation | Deactivation of NEB Pipeline relating to Order AO-002-XO-T097-001-2003 | Deactivate AO-002-XO-T097-001-2003 | Completed | MO-024-2012 | application pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 for Deactivation of the Sour Oil Pipeline Located From 04-20-082-13W5 To 15-17-082-13W6 (the Pipeline). | 2012-07-13 | 2012-07-13 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Bonavista shall cause the Pipeline to be deactivated and maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Bonavista Energy Corporation | Deactivation of NEB Pipeline relating to Order AO-002-XO-T097-001-2003 | Deactivate AO-002-XO-T097-001-2003 | Completed | MO-024-2012 | application pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 for Deactivation of the Sour Oil Pipeline Located From 04-20-082-13W5 To 15-17-082-13W6 (the Pipeline). | 2012-07-13 | 2012-07-13 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Bonavista shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Bonavista Energy Corporation | Deactivation of NEB Pipeline relating to Order AO-002-XO-T097-001-2003 | Deactivate AO-002-XO-T097-001-2003 | Completed | MO-024-2012 | application pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 for Deactivation of the Sour Oil Pipeline Located From 04-20-082-13W5 To 15-17-082-13W6 (the Pipeline). | 2012-07-13 | 2012-07-13 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 4 | Within 30 days of the date of this Order, Bonavista shall tile with the Board a confirmation, by an officer of the company, that the deactivation was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-004-1992 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Glenogle shall comply with all of the conditions contained in Order XG-4-92, as amended, unless the Board otherwise directs. | Closed | Not Construction Related | Non Standard | Filing Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-004-1992 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, three copies of its Emergency Procedures Manual(s). | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-004-1992 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, one copy of its Integrity Management Program. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-004-1992 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 4 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, confirmation that all records pursuant to section 10.4 of CSA Z662-11 and paragraphs 56(e) to 56(g) of the Onshore Pipeline Regulations have been received from Bonavista. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-004-1992 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 5 | Within 60 days of the date of this Amending Order, Glenogle shall file with the Board a confirmation that the transfer of the Pipeline was completed in compliance with all applicable conditions contained in this Order and all applicable directions contained in the Board’s letter to Bonavista and Glenogle, dated 23 April 2014. If compliance with any of these conditions cannot be confirmed, Glenogle shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Glenogle. | Closed | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XO-T097-001-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Glenogle shall comply with all of the conditions contained in Order XO-T097-01-2003, as amended, unless the Board otherwise directs. | Closed | Not Construction Related | Non Standard | Filing Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XO-T097-001-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, three copies of its Emergency Procedures Manual(s). | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XO-T097-001-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, one copy of its Integrity Management Program. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XO-T097-001-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 4 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, confirmation that all records pursuant to section 10.4 of CSA Z662-11 and paragraphs 56(e) to 56(g) of the Onshore Pipeline Regulations have been received from Bonavista. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XO-T097-001-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 5 | Within 60 days of the date of this Amending Order, Glenogle shall file with the Board a confirmation that the transfer of the Pipeline was completed in compliance with all applicable conditions contained in this Order and all applicable directions contained in the Board’s letter to Bonavista and Glenogle, dated 23 April 2014. If compliance with any of these conditions cannot be confirmed, Glenogle shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Glenogle. | Closed | Not Construction Related | Standard | Filing Not Required | Sunset Clause
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-009-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Glenogle shall comply with all of the conditions contained in Order XG-T097-09-2003, as amended, unless the Board otherwise directs. | Closed | Not Construction Related | Non Standard | Filing Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-009-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, three copies of its Emergency Procedures Manual(s). | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-009-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, one copy of its Integrity Management Program. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-009-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 4 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, confirmation that all records pursuant to section 10.4 of CSA Z662-11 and paragraphs 56(e) to 56(g) of the Onshore Pipeline Regulations have been received from Bonavista. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-009-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 5 | Within 60 days of the date of this Amending Order, Glenogle shall file with the Board a confirmation that the transfer of the Pipeline was completed in compliance with all applicable conditions contained in this Order and all applicable directions contained in the Board’s letter to Bonavista and Glenogle, dated 23 April 2014. If compliance with any of these conditions cannot be confirmed, Glenogle shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Glenogle. | Closed | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-034-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia | 1 | Glenogle shall comply with all of the conditions contained in Order XG-T097-34-2003, as amended, unless the Board otherwise directs. | Closed | Not Construction Related | Non Standard | Filing Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-034-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia | 2 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, three copies of its Emergency Procedures Manual(s). | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-034-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia | 3 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, one copy of its Integrity Management Program. | Closed | Not Construction Related | Standard | Filing Not Required | Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-034-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia | 4 | Glenogle shall file with the Board, no later than 30 days from the issuance of this Amending Order, confirmation that all records pursuant to section 10.4 of CSA Z662-11 and paragraphs 56(e) to 56(g) of the Onshore Pipeline Regulations have been received from Bonavista. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-003-XG-T097-034-2003 |  | 2014-04-22 | 2014-04-22 |  | All Conditions Met | Northeast /British Columbia | 5 | Within 60 days of the date of this Amending Order, Glenogle shall file with the Board a confirmation that the transfer of the Pipeline was completed in compliance with all applicable conditions contained in this Order and all applicable directions contained in the Board’s letter to Bonavista and Glenogle, dated 23 April 2014. If compliance with any of these conditions cannot be confirmed, Glenogle shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of Glenogle. | Closed | Not Construction Related | Non Standard | Filing Not Required | Standard Condition
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XG-004-1992 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met |  | 1 | In conditions 2, 3 and 4, the deadlines for filing the Emergency Procedures Manual, the Integrity Management Program and to confirm the Transfer of Records, respectively, are extended from 30 to 60 days. | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management, Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XG-004-1992 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met |  | 2 | In condition 5, the deadline for filing a Compliance Confirmation letter is extended from 60 days to 90 days. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XO-T097-001-2003 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia | 1 | In conditions 2, 3 and 4, the deadlines for filing the Emergency Procedures Manual, the Integrity Management Program and to confirm the Transfer of Records, respectively, are extended from 30 to 60 days. | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management, Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XO-T097-001-2003 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia | 2 | In condition 5, the deadline for filing a Compliance Confirmation letter is extended from 60 days to 90 days. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XG-T097-009-2003 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia | 1 | In conditions 2, 3 and 4, the deadlines for filing the Emergency Procedures Manual, the Integrity Management Program and to confirm the Transfer of Records, respectively, are extended from 30 to 60 days. | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management, Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XG-T097-009-2003 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia | 2 | In condition 5, the deadline for filing a Compliance Confirmation letter is extended from 60 days to 90 days. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XG-T097-034-2003 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia | 1 | In conditions 2, 3 and 4, the deadlines for filing the Emergency Procedures Manual, the Integrity Management Program and to confirm the Transfer of Records, respectively, are extended from 30 to 60 days. | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management, Integrity Management
Bonavista Energy Corporation | Bonavista s. 74 and 21 application for the transfer of ownership to Glenogle Energy Inc. | Change Owner from Bonavista to Glenogle | Completed | AO-004-XG-T097-034-2003 |  | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia | 2 | In condition 5, the deadline for filing a Compliance Confirmation letter is extended from 60 days to 90 days. | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | NuVista s. 74(1)(a) application for transfer of ownership of the Hallam Pipeline from NuVista to Bonavista. | Change Owner Hallam Pipeline from NuVista to Bonavista | Completed | AO-003-XG-C041-044-1995 | IT IS ORDERED THAT, pursuant to subsection 21(1) of the NEB Act, Order XG-C41-44-95, as amended, is varied to change the name of the holder of the Order to Bonavista Energy Corporation subject to the following condition:... | 2014-10-15 | 2014-10-15 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Bonavista shall file with the Board, no later than 30 days from the issuance of this Amending Order, confirmation that all records maintained by NuVista since its acquisition of the Hallam pipeline, pursuant to section 10.4 of CSA Z661-11 and subsections 56(e) to 56(g) of the NEB Onshore Pipeline Regulations, have been received from NuVista | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Bonavista shall comply with all of the conditions contained in this Order, unless the Board otherwise directs. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 10 | Unless the Board otherwise directs prior to 20 September 2017, this Order shall expire on 20 September 2017, unless Abandonment Activities in respect of the Project have commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Bonavista shall cause the Project to be abandoned in accordance with the specifications, standards (including Canadian Standards Association (CSA) Z662-15, Oil and Gas Pipeline Systems), commitments made and other information referred to in its Application and related submissions. | Closed | Abandonment | Non Standard | Filing Required | Standard Condition, Integrity Management
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 3 | Bonavista shall implement or cause to be implemented, all of the policies, practices, programs, mitigation measures, recommendations, commitments and procedures for the protection of the environment included or referred to in its Application and related submissions. | In Progress | Abandonment | Non Standard | Filing Required | Standard Condition, Environmental Protection
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 4 | Bonavista shall file with the Board for approval, at least 45 days prior to commencing Abandonment Activities, an Environmental Protection Plan for the Project. The Environmental Protection Plan shall describe the environmental protection procedures and measures used to mitigate environmental impacts from the abandonment activities associated with this Project, including, but not limited to: a) procedures for planned Abandonment Activities and reclamation including soils handling, appropriate handling, testing and disposal of materials, and revegetation or vegetation management techniques designed to restore disturbed areas to the equivalent land capability; b) measures to identify and characterize any contamination encountered during Abandonment Activities (for example, by visual or olfactory indicators, soil vapour testing, or soil sampling) and a contingency plan to be implemented in the event that potential contamination is encountered; and c) procedures for spill prevention, response and reporting during the Abandonment Activities. "" | Closed | Abandonment | Standard | Filing Not Required | Environmental Protection
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 5 | Bonavista shall file with the Board, at least 45 days prior to commencing the Abandonment Activities, the results of a Phase I Environmental Site Assessment (ESA). The Phase I ESA shall consider the guidance provided in the most recent version of CSA Standard Z768-01, Phase I Environmental Site Assessment, to investigate and describe any potentially hazardous materials and the likelihood of any historical contamination associated with the sites where the Project is located. The Phase I ESA shall include: a) confirmation that the Phase I ESA did not identify potential contamination associated with the Project; or b) a plan, for approval, which includes a detailed description of procedures to be implemented for: i. investigation of all existing or potential contamination identified pursuant to the Phase I ESA; and ii. remediation of all contamination to the most stringent of federal or applicable provincial environmental criteria. The plan listed in b) shall be consistent with the process described in the NEB’s Remediation Process Guide, and may include conducting a Phase II ESA, preparing a Remedial Action Plan and/or conducting remediation, as required to achieve compliance with Condition 5(b)(ii). The plan shall include dates by which Bonavista will report to the Board results of the planned activities and any proposed revisions to the plan in response to those results. "" | Closed | Abandonment | Standard | Filing Not Required | Environmental Protection
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 6 | If, while undertaking the Abandonment Activities, Bonavista discovers soil and/or groundwater contamination that is in excess of federal or applicable provincial environmental criteria, Bonavista shall file a Notification of Contamination (NOC) with the Board, within seven days of discovering the contamination. The NOC shall include: a) location of the contamination [Universal Transverse Mercator (UTM) coordinates (zone included) or latitude/longitude]; b) identified contaminants of concern and details of their origin if available; c) nearby receptors of immediate concern; d) a summary of the communications to date with stakeholders; and e) a detailed plan to remediate the site to the most stringent federal or provincial criteria, or if remediation has already been undertaken, a summary of all actions taken to mitigate any impacts related to the discovered contamination. "" | Closed | Abandonment | Standard | Filing Required | Environmental Protection
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 7 | On or before 31 January after the first complete growing season following the completion of Abandonment Activities, Bonavista shall submit to the Board, for approval, the following reports: a) a Post-Abandonment Monitoring Report that shall include: i. a description of the environmental components or issues that were monitored; ii. monitoring methods for each environmental component or issue; iii. corrective actions taken, observed success, and current status; and iv. any further corrective actions planned and a schedule for future monitoring. b) a Post-Abandonment Report that shall include: i. photographs and a brief description of landscape and land cover on and off the pipeline right-of-way; ii. demonstration that either the state of land at the area disturbed during the Abandonment Activities is restored to equivalent land capability or that outlines plans for further corrective actions and monitoring; andiii. confirmation that no contamination in excess of federal or applicable provincial environmental criteria was identified during the Abandonment Activities; or iv. a remediation report confirming that all contamination has been remediated to the most stringent federal or applicable provincial environmental criteria, if any contamination was discovered during the Abandonment Activities. The remediation report shall describe all applied remedial activities and summarize the methods and results of any soil and groundwater sampling and analyses conducted. "" | In Progress | Abandonment | Standard | Filing Not Required | Environmental Protection
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 8 | Bonavista shall notify directly affected landowners and land users of the timing of upcoming Abandonment Activities at least 15 days prior to commencing them. Confirmation of this notification shall be provided to the Board prior to commencing Abandonment Activities. | Closed | Abandonment | Standard | Filing Not Required | Socio-Economic
Bonavista Energy Corporation | Bonavista Abandonment of Hallum Pipeline | Abandon Hallum Pipeline | In Progress | ZO-B263-002-2016 | Abandonment Order with letter decision | 2016-09-20 | 2016-09-20 |  | In Progress | Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 9 | Bonavista shall file with the Board, within two years of the date of completion of all Abandonment Activities, confirmation, by an officer of the company, that the Project was completed, and that all Abandonment Activities were conducted in compliance with the conditions of this Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition must include a statement confirming that the signatory to the filing is an officer of the company. | Closed | Abandonment | Non Standard | Filing Not Required | Standard Condition
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Lone Pine Resources Canada Ltd. | Section 21 application to Vary Board Order XG-C357-009-2010 | Variance XG-C357-009-2010 | Completed | AO-002-XG-C357-009-2010 | IT IS ORDERED THAT, pursuant to subsection 21(1) of the NEB Act, Condition 15 of Order XG-357-009-2010 is amended by extending the deadlines for filing the third and fifth year post-construction environmental monitoring reports to on or before 31 January after each of the fourth and sixth complete growing seasons following the commencement of operation of the Project. | 2014-08-07 | 2014-08-07 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 15 | Pursuant to subsection 21(1) of the NEB Act, Condition 15 of Order XG-357-009-2010 is amended by extending the deadlines for filing the third and fifth year post-construction environmental monitoring reports to on or before 31 January after each of the fourth and sixth complete growing seasons following the commencement of operation of the Project. | Closed | Post Construction Phase | Standard | Filing Not Required | Environmental Protection
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Tundra Oil & Gas Limited | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | Ruger Energy Inc. Application to Deactivate a Pipeline - Order XO-R042-02-2003 | Deactivate XO-R042-02-2003 | Completed | MO-031-2012 | Application to the National Energy Board pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 (OPR-99) for Deactivation of a Pipeline Order XO-R042-02-2003 (Pipeline) | 2012-10-04 | 2010-10-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger shall comply with all of the conditions contained in this Order unless the Board otherwise directs | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Ruger Energy Inc. | Ruger Energy Inc. Application to Deactivate a Pipeline - Order XO-R042-02-2003 | Deactivate XO-R042-02-2003 | Completed | MO-031-2012 | Application to the National Energy Board pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 (OPR-99) for Deactivation of a Pipeline Order XO-R042-02-2003 (Pipeline) | 2012-10-04 | 2010-10-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger shall cause the Pipeline to be deactivated and maintained in accordance with the specifications, standards and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Ruger Energy Inc. | Ruger Energy Inc. Application to Deactivate a Pipeline - Order XO-R042-02-2003 | Deactivate XO-R042-02-2003 | Completed | MO-031-2012 | Application to the National Energy Board pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 (OPR-99) for Deactivation of a Pipeline Order XO-R042-02-2003 (Pipeline) | 2012-10-04 | 2010-10-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 3 | Ruger shall implement or cause to be implemented all of the policies, practices, program, mitgiation measures, recommendations and procedures for the protection of the environment included in or referred to in the application or related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Ruger Energy Inc. | Ruger Energy Inc. Application to Deactivate a Pipeline - Order XO-R042-02-2003 | Deactivate XO-R042-02-2003 | Completed | MO-031-2012 | Application to the National Energy Board pursuant to Section 44 of the Onshore Pipeline Regulations, 1999 (OPR-99) for Deactivation of a Pipeline Order XO-R042-02-2003 (Pipeline) | 2012-10-04 | 2010-10-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 4 | Within 30 days of the date that the deactivation is completed, Ruger shall file with the Board a confirmation, by an officer of the company, that the deactivation was completed in compliance with all applicable conditions in the Order. If compliance with any of these conditions cannot be confirmed, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the company | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Ruger Energy Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Bear Paw Processing Company (Canada) Ltd operating as ONEOK Rockies Processing Company (Canada) Ltd. | Bear Paw Processing Plant Compnay Application for Deactivation and Name Change | Deactivate North Portal Pipeline & Change Name to ONEOK | Completed | MO-004-2012 | Application pursuant to section 44 of the Onshore Pipeline Regulation, 1999 (OPR-99) for Deactivation of North Portal Pipeline, Saskatchewan and application for name change. | 2012-03-15 | 2012-03-15 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK shall comply with all the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Bear Paw Processing Company (Canada) Ltd operating as ONEOK Rockies Processing Company (Canada) Ltd. | Bear Paw Processing Plant Compnay Application for Deactivation and Name Change | Deactivate North Portal Pipeline & Change Name to ONEOK | Completed | MO-004-2012 | Application pursuant to section 44 of the Onshore Pipeline Regulation, 1999 (OPR-99) for Deactivation of North Portal Pipeline, Saskatchewan and application for name change. | 2012-03-15 | 2012-03-15 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK shall cause the Pipeline to be deactivated and maintained in accordance with the specifications, standards, and other information referred to in its application or in related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Bear Paw Processing Company (Canada) Ltd operating as ONEOK Rockies Processing Company (Canada) Ltd. | Bear Paw Processing Plant Compnay Application for Deactivation and Name Change | Deactivate North Portal Pipeline & Change Name to ONEOK | Completed | MO-004-2012 | Application pursuant to section 44 of the Onshore Pipeline Regulation, 1999 (OPR-99) for Deactivation of North Portal Pipeline, Saskatchewan and application for name change. | 2012-03-15 | 2012-03-15 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | ONEOK shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Bear Paw Processing Company (Canada) Ltd operating as ONEOK Rockies Processing Company (Canada) Ltd. | Bear Paw Processing Plant Compnay Application for Deactivation and Name Change | Deactivate North Portal Pipeline & Change Name to ONEOK | Completed | MO-004-2012 | Application pursuant to section 44 of the Onshore Pipeline Regulation, 1999 (OPR-99) for Deactivation of North Portal Pipeline, Saskatchewan and application for name change. | 2012-03-15 | 2012-03-15 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 4 | Within 30 days of the date of the Order, ONEOK shall file with the Board a confirmation that the amroved Proiect was completed and constructed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confiied, the officer of the company shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confiig that the signatory to the filing is an officer of the company. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Bear Paw Processing Company (Canada) Ltd operating as ONEOK Rockies Processing Company (Canada) Ltd. | Request for variance, extension of Condition 3, Board Order MO-024-2011 | Variance MO-024-2011 Condition 3 | Completed | AO-001-MO-024-2011 | ONEOK Rockies Processing Company (Canada) Ltd. - Request for 60-day Extension | 2012-03-26 | 2012-03-26 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Condition 3 of Order M0-024-2011 is revoked and replaced by the following condition:On or before 31 May 2012 ONEOK shall file with the Board an EPM for the Pipeline. The EPM shall address the expectations of the Board for an EPM as set out in the Board's All Company Letter dated 24 April 2002, titled Security and Emergency Preparedness and Response Programs. | Closed | Not Construction Related | Standard | Filing Not Required | Emergency Management, Security
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Veresen Energy Infrastructure Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | Request to Amend Order AO-001-MO-024-2011 for 180 day extension, condition 3 | Variance AO-001-MO-024-2011 | Completed | AO-002-MO-024-2011 | ONEOK Rockies Processing Company (Canada) Ltd. - Request for 180-day Extension | 2012-06-07 | 2012-06-07 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Condition 3 of Order AO-001-MO-024-2011 is revoked and replaced by the following condition:3. On or before 29 June 2012 ONEOK shall file with the Board an EPM for the Pipeline. The EPM shall address the expectations of the Board for an EPM as set out in the Board's All Company Letter dated 24 April 2002, titled Security and Emergency Preparedness and Response Programs. | Closed | Post Construction Phase | Standard | Filing Not Required | Emergency Management
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
ONEOK Rockies Processing Company (Canada) Ltd. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Crescent Point Energy Corp. | Crescent Point s. 44 OPR application to deactivate Regent Coutts Gas Export Pipeline. | Deactivate Regent Coutts Gas Export Pipeline | Completed | MO-045-2016 | Crescent Point Energy Corp. (CPEC) – Application for the Deactivation of Pipeline XG-R040-10-2003 (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-07 | 2016-10-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | CPEC shall comply with all of the conditions contained in this Order unless the Board otherwise directs. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Crescent Point Energy Corp. | Crescent Point s. 44 OPR application to deactivate Regent Coutts Gas Export Pipeline. | Deactivate Regent Coutts Gas Export Pipeline | Completed | MO-045-2016 | Crescent Point Energy Corp. (CPEC) – Application for the Deactivation of Pipeline XG-R040-10-2003 (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-07 | 2016-10-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | CPEC shall deactivate and maintain the Regent Coutts Gas Export Pipeline in its deactivated state in accordance with the specifications, standards, commitments made and other information referred to in its application or in its related submission | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Crescent Point Energy Corp. | Crescent Point s. 44 OPR application to deactivate Regent Coutts Gas Export Pipeline. | Deactivate Regent Coutts Gas Export Pipeline | Completed | MO-045-2016 | Crescent Point Energy Corp. (CPEC) – Application for the Deactivation of Pipeline XG-R040-10-2003 (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-07 | 2016-10-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 3 | CPEC shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and its commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Crescent Point Energy Corp. | Crescent Point s. 44 OPR application to deactivate Regent Coutts Gas Export Pipeline. | Deactivate Regent Coutts Gas Export Pipeline | Completed | MO-045-2016 | Crescent Point Energy Corp. (CPEC) – Application for the Deactivation of Pipeline XG-R040-10-2003 (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-07 | 2016-10-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 4 | Within 30 days of the date that the deactivation is completed, CPEC shall file with the Board a confirmation that the Project was completed in compliance with all applicable conditions in this Order. If compliance with any of these conditions cannot be confirmed, CPEC shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is the accountable officer of CPEC, appointed as Accountable Officer pursuant to s. 6.2 of the OPR. | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Crescent Point Energy Corp. | Crescent Point s. 44 OPR application to deactivate Regent Coutts Gas Export Pipeline. | Deactivate Regent Coutts Gas Export Pipeline | Completed | MO-045-2016 | Crescent Point Energy Corp. (CPEC) – Application for the Deactivation of Pipeline XG-R040-10-2003 (Project) under section 44 of the National Energy Board Onshore Pipeline Regulations (OPR) | 2016-10-07 | 2016-10-07 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 5 | Unless the Board otherwise directs prior to 7 October 2017, this Order shall expire on7 October 2017 unless the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Pembina Energy Services Inc. | Pembina S.45.1 OPR 99 application - Taylor and Goodlow Decommissioning Project | Decommission Taylor and Goodlow | Completed | MO-016-2013 |  | 2013-05-17 | 2013-05-17 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Pembina shall comply with all of the conditions contained in this Order unless theBoard otherwise directs."" | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
Pembina Energy Services Inc. | Pembina S.45.1 OPR 99 application - Taylor and Goodlow Decommissioning Project | Decommission Taylor and Goodlow | Completed | MO-016-2013 |  | 2013-05-17 | 2013-05-17 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Pembina shall cause the Facilities to be decommissioned and maintained inaccordance with the specifications, standards and other information referred to in itsapplication."" | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Integrity Management
Pembina Energy Services Inc. | Pembina S.45.1 OPR 99 application - Taylor and Goodlow Decommissioning Project | Decommission Taylor and Goodlow | Completed | MO-016-2013 |  | 2013-05-17 | 2013-05-17 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Pembina shall implement or cause to be implemented all of the policies, practices,programs, mitigation measures, recommendations and procedures for theprotection of the environment included in or referred to in the application or inrelated submissions."" | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition, Environmental Protection
Pembina Energy Services Inc. | Pembina S.45.1 OPR 99 application - Taylor and Goodlow Decommissioning Project | Decommission Taylor and Goodlow | Completed | MO-016-2013 |  | 2013-05-17 | 2013-05-17 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 4 | Pembina shall file with the Board, within 30 days of the date that thedecommissioning is completed, a confirmation, by an officer of the company, that thedecommissioning was completed in compliance with all applicable conditions in theOrder. If compliance with any of these conditions cannot be confirmed, the officer ofthe company shall file with the Board details as to why compliance cannot beconfirmed. The filing required by this condition shall include a statement confirmingthat the signatory to the filing is an officer of the company."" | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
Pembina Energy Services Inc. | Pembina S.45.1 OPR 99 application - Taylor and Goodlow Decommissioning Project | Decommission Taylor and Goodlow | Completed | MO-016-2013 |  | 2013-05-17 | 2013-05-17 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 5 | Unless the Board otherwise directs prior to 16 May 2014, this Order shallexpire on 16 May 2014 unless the Project has commenced by that date."" | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Vector may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Vector chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | Canada Border Services Agency must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-072-2014 | Canada Border Services Agency | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Canada Border Services Agency must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 1 | Mid-Continent must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-073-2014 | Mid-Continent Pipelines Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Lethbridge--Medicine Hat/Alberta | 2 | Mid-Continent must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | NuVista must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-074-2014 | NuVista Energy Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | NuVista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 1 | The Board approves PMGC’s request for an exemption from the requirement to provide set-aside and collection mechanisms.Board Exemption: A78959 | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-075-2014 | Portal Municipal Gas Company Canada Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met |  | 2 | Portal must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 1 | Penn West must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | ONEOK must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-065-2014 | Penn West Petroleum Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Athabasca--Grande Prairie--Peace River/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia | 2 | Penn West must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Tamarack must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-068-2014 | Tamarack Acquisition Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Tamarack must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Terra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-069-2014 | Terra Energy Corp. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Terra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Yoho must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-070-2014 | Yoho Resources Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Yoho must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Keyera must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-060-2014 | Keyera Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Keyera must file, for Board approval, a letter of credit or surety bond consistent with theReasons by 31 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Lone Pine must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-061-2014 | Lone Pine Resources Canada Ltd. THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that: 1. Lone Pine must implement the findings, directions and decisions set out in the Reasons; and 2. Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Lone Pine must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Omimex must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-063-2014 | Omimex Canada Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Omimex must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | ONEOK must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-064-2014 | ONEOK Rockies Processing Company (Canada) Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | ONEOK must file, for Board Approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | ATCO must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-053-2014 | 6720471 Canada Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | ATCO must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | Bellatrix must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-054-2014 | Bellatrix Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | Bellatrix must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 1 | Bonavista must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-055-2014 | Bonavista Energy Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Saskatoon--Biggar/Saskatchewan | 2 | Bonavista must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 1 | ExxonMobil must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-058-2014 | ExxonMobil Canada Properties | 2014-06-04 | 2014-06-04 |  | All Conditions Met | North Shore /Nova Scotia , Cape Breton/Nova Scotia | 2 | ExxonMobil must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | TAQA must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-047-2014 | TAQA North Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | TAQA must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Tundra must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-048-2014 | Tundra Oil & Gas Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Tundra must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 1 | CNRL must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-049-2014 | Canadian Natural Resources Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Saskatoon--Biggar/Saskatchewan, Camrose--Drumheller/Alberta | 2 | CNRL must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Imperial must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-051-2014 | Imperial Oil Resources | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Imperial must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Harvest must implement the findings, directions and decision set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-052-2014 | 1057533 Alberta Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Harvest must file, for Board approval, a letter of credit or surety bond consistent with the Rea ons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 1 | AltaGas must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-041-2014 | AltaGas Holdings Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Saskatoon--Biggar/Saskatchewan, Prince Albert/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Wood Buffalo--Cold Lake/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta, Swift Current--Moose Jaw/Saskatchewan | 2 | AltaGas must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | ARC must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-042-2014 | by ARC Resources Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | ARC must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Vantage must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-044-2014 | Vantage Pipeline Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Vantage must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Sunoco must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-046-2014 | Sunoco Pipeline L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Sunoco must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ISH must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-036-2014 | ISH Energy Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ISH must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 1 | Murphy must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-037-2014 | Murphy Oil Company Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Prince Albert/Saskatchewan, Regina--Moose Mountain/Saskatchewan | 2 | Murphy must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Pengrowth must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-038-2014 | Pengrowth Corporation | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Pengrowth must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 1 | Ruger must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-039-2014 | Ruger Energy Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta | 2 | Ruger must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Strategic must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-040-2014 | Strategic Transmission Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Strategic must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 1 | TransCanada must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 2 | TransCanada must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TransCanada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of TransCanada's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TransCanada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-029-2014 | TransCanada PipeLines Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northwest /Ontario, Montréal/Quebec , Yorkton--Melville/Saskatchewan, Lethbridge--Medicine Hat/Alberta, North Central /Manitoba, Regina--Moose Mountain/Saskatchewan, Kitchener--Waterloo--Barrie/Ontario, Hamilton--Niagara Peninsula/Ontario, Montérégie/Quebec , Swift Current--Moose Jaw/Saskatchewan, Muskoka--Kawarthas/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Southeast /Manitoba, Toronto/Ontario, Northeast /Ontario, Ottawa/Ontario | 3 | TransCanada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 1 | Enbridge must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 2 | Enbridge must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge's proposed trustee;b. a collection mechani m filing, by 5 December 2014, consi tent with the findings, direction and decision set out in the Reasons. The collection mechanism filing must set out Enbridge's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-030-2014 | Enbridge Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba, Toronto/Ontario, Lanaudière/Quebec , Hamilton--Niagara Peninsula/Ontario, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba, Kingston--Pembroke/Ontario, Saskatoon--Biggar/Saskatchewan, Laurentides/Quebec | 3 | Enbridge must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 1 | Champion must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 2 | Subject to Clause 3 of this Order:a. Champion must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 201 4, containing: (i) Champion's proposed form of trust agreement that is consistent with the findings, directions and decisions et out in the Reason , and (ii) the identity of Champion's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, direction and deci ions set out in the Reasons. The collection mechanism filing must set out Champion's annual contribution amount, anytoll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Champion must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-031-2014 | Champion Pipe Line Corporation Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Abitibi-Témiscamingue/Quebec , Northeast /Ontario | 3 | Champion may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Champion chooses to u e a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 1 | Plains must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 2 | Subject to Clause 3 of this Order:a. Plains must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Plains' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Plains'proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must, as applicable to the Common Carrier Pipelines, and the Windsor Storage Facility, set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the currentversion together with a clean version;iii. an annual contribution amount filing, by 31 December 2014 for the Proprietary Pipelines, consistent with the findings, directions and decisions set out in the Reasons; andb. Plains must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-032-2014 | Plains Midstream Canada ULC | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Edmonton/Alberta, Yorkton--Melville/Saskatchewan, Regina--Moose Mountain/Saskatchewan, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, North Central /Manitoba, Camrose--Drumheller/Alberta, Windsor--Sarnia/Ontario, Southwest /Manitoba | 3 | Plains may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Plains chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 1 | TNPI must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 2 | TNPI must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TNPI's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity ofTNPI's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent wi th the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out TNPI's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheet showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-033-2014 | Trans-Northern Pipelines Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Laval/Quebec , Laurentides/Quebec , Ottawa/Ontario, Kingston--Pembroke/Ontario, Toronto/Ontario, Montérégie/Quebec , Hamilton--Niagara Peninsula/Ontario, Montréal/Quebec | 3 | TNPI must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Talisman must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-034-2014 | Talisman Energy Inc. | 2014-06-04 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Talisman must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 1 | Whitecap must implement the findings, directions and decisions set out in the MH-001-2013 Reasons for Decision | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | AO-001-MO-051-2014 | THEREFORE, IT IS ORDERED, pursuant to subsection 21(1) of the NEB Act, that Order MO-051-2014 be amended to state that:... | 2014-06-17 | 2014-06-17 |  | All Conditions Met |  | 2 | Whitecap must file, for Board approval, a letter of credit or surety bond consistent with the MH-001-2013 Reasons for Decision by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | ConocoPhillips must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-035-2014 | ConocoPhillips Canada Operations Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | ConocoPhillips must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Northern Blizzard must implement the findings, directions and decisions set out in the&nbsp;Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-062-2014 | Northern Blizzard Resources Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Swift Current--Moose Jaw/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Northern Blizzard must file, for Board approval, a letter of credit or surety bond consistent&nbsp;with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Shell must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-066-2014 | Shell Canada Products Limited | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Shell must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 1 | Shiha must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-067-2014 | Shiha Energy Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Northeast /British Columbia | 2 | Shiha must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 1 | Abitibi must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-071-2014 | Abitibi-Consolidated Company of Canada | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario | 2 | Abitibi must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Spyglass must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-076-2014 | Spyglass Resources Corp. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Spyglass must file, for Board approval, a letter of credit or surety bond consistent with the&nbsp;Reasons by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 1 | Niagara must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 2 | Subject to Clause 3 of this Order:<br />a. Niagara must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Niagara&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Niagara&rsquo;s proposed trustee; ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Niagara&rsquo;s annual contribution amount, toll surcharges applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;<br />b. Niagara must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-081-2014 | Niagara Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Windsor--Sarnia/Ontario, Ottawa/Ontario | 3 | Niagara may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Niagara chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pembina must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:<br />a. Pembina must make the following filings for Board approval:<br />i. a set-aside mechanism filing, by 2 September 2014, containing:<br />(i) Pembina&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and<br />(ii) the identity of Pembina&rsquo;s proposed trustee;<br />ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;<br />b. Pembina must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-085-2014 | Pembina Energy Services Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pembina may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pembina chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014.&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | KM Cochin must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | KM Cochin must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) KM Cochin&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of KM Cochin&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out KM Cochin&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-096-2014 | Kinder Morgan Cochin ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Camrose--Drumheller/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | KM Cochin must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014.&nbsp;&nbsp; | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 1 | NGTL must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 2 | NGTL must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) NGTL&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of NGTL&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out NGTL&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-097-2014 | NOVA Gas Transmission Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta, Northeast /British Columbia , Camrose--Drumheller/Alberta, Wood Buffalo--Cold Lake/Alberta, Lethbridge--Medicine Hat/Alberta, Saskatoon--Biggar/Saskatchewan, Red Deer/Alberta, Edmonton/Alberta | 3 | NGTL must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 1 | Trans Mountain must implement the findings, directions and decisions set out in the Reasons. | Closed | Not Construction Related | Standard | Filing Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 2 | Trans Mountain must make the following filings for Board approval: a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Trans Mountain&rsquo;s proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Trans Mountain&rsquo;s proposed trustee; b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Trans Mountain&rsquo;s annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | SAM/COM | SAM/COM | Completed | MO-098-2014 | Trans Mountain Pipeline ULC | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Thompson--Okanagan/British Columbia , Lower Mainland--Southwest /British Columbia , Edmonton/Alberta, Cariboo/British Columbia , Banff--Jasper--Rocky Mountain House/Alberta | 3 | Trans Mountain must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Pembina Energy Services Inc. | Pembina s. 21 application to vary Order AO-002-XO-P115-04-2011 – Condition 21 | Variance AO-002-XO-P115-04-2011 Condition 21 | Completed | AO-003-XO-P115-004-2011 |  | 2013-05-17 | 2013-05-17 |  | All Conditions Met | Northeast /British Columbia | 1 | Pembina shall file a deactivation application for the existing Beatton River crossingwithin 30 days following commencement of operations."" | Closed | Post Construction Phase | Standard | Filing Not Required | Administrative
BlackPearl Resources Inc. | Black Pearl Resources s.58 application to construct and operate Central SK-AB PW Disposal Pipeline | Construct SK-AB PW Disposal Pipeline | Completed | XC-B268-001-2013 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the Project as specified in Schedule A of this Order, is exempted from the provisions of sections 30 through 33, inclusive, and section 47 of the NEB Act and is approved, subject to the following conditions:... | 2013-03-27 | 2013-03-27 | 2014-03-27 | All Conditions Met |  | 1 | BlackPearl shall comply with all the conditions contained in this Order unless the Board directs otherwise. | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
BlackPearl Resources Inc. | Black Pearl Resources s.58 application to construct and operate Central SK-AB PW Disposal Pipeline | Construct SK-AB PW Disposal Pipeline | Completed | XC-B268-001-2013 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the Project as specified in Schedule A of this Order, is exempted from the provisions of sections 30 through 33, inclusive, and section 47 of the NEB Act and is approved, subject to the following conditions:... | 2013-03-27 | 2013-03-27 | 2014-03-27 | All Conditions Met |  | 2 | BlackPearl shall cause the approved Project to be designed, located, constructed, installed, and operated in accordance with the specifications, standards, commitments, and other information referred to in its application or in its related submissions.&nbsp; | Closed | Includes all Phases of Constr. | Non Standard | Filing Required | Standard Condition
BlackPearl Resources Inc. | Black Pearl Resources s.58 application to construct and operate Central SK-AB PW Disposal Pipeline | Construct SK-AB PW Disposal Pipeline | Completed | XC-B268-001-2013 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the Project as specified in Schedule A of this Order, is exempted from the provisions of sections 30 through 33, inclusive, and section 47 of the NEB Act and is approved, subject to the following conditions:... | 2013-03-27 | 2013-03-27 | 2014-03-27 | All Conditions Met |  | 3 | BlackPearl shall implement or cause to be implemented all of the policies, practices, programs, mitigation measures, recommendations, procedures and commitments for the protection of the environment included in or referred to in its application or in its related submissions. | Closed | Includes all Phases of Constr. | Standard | Filing Required | Environmental Protection
BlackPearl Resources Inc. | Black Pearl Resources s.58 application to construct and operate Central SK-AB PW Disposal Pipeline | Construct SK-AB PW Disposal Pipeline | Completed | XC-B268-001-2013 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the Project as specified in Schedule A of this Order, is exempted from the provisions of sections 30 through 33, inclusive, and section 47 of the NEB Act and is approved, subject to the following conditions:... | 2013-03-27 | 2013-03-27 | 2014-03-27 | All Conditions Met |  | 4 | Within 30 days of the date that the approved Project is placed in service, BlackPearl shall file with the Board a confirmation that the approved Project was completed in compliance with all applicable conditions in this Order. Ifcompliance with any of these conditions cannot be confirmed, BlackPearl shall file with the Board details as to why compliance cannot be confirmed. The filing required by this condition shall include a statement confirming that the signatory to the filing is an officer of the BlackPearl."" | Closed | Post Construction Phase | Non Standard | Filing Not Required | Standard Condition
BlackPearl Resources Inc. | Black Pearl Resources s.58 application to construct and operate Central SK-AB PW Disposal Pipeline | Construct SK-AB PW Disposal Pipeline | Completed | XC-B268-001-2013 | IT IS ORDERED that, pursuant to section 58 of the NEB Act, the Project as specified in Schedule A of this Order, is exempted from the provisions of sections 30 through 33, inclusive, and section 47 of the NEB Act and is approved, subject to the following conditions:... | 2013-03-27 | 2013-03-27 | 2014-03-27 | All Conditions Met |  | 5 | Unless the Board otherwise directs prior to 27 March 2014, this Order shall expire on 27 March 2014, unless construction in respect of the Project has commenced by that date. | Closed | Expiry Date of Reg. Instr. | Standard | Filing Required | Sunset Clause
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 1 | TQM must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 2 | TQM must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) TOM's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reasons, and (ii) the identity of TQM 's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings,directions and decisions set out in the Reasons. The collection mechanism filing must set out TOM's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-023-2014 | THEREFORE, IT IS ORDERED, pursuant to paragraph 12(1)(b), Part III and Part IV of the NEB Act that:... | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Montérégie/Quebec , Mauricie/Quebec , Capitale-Nationale/Quebec , Lanaudière/Quebec , Estrie/Quebec , Laurentides/Quebec | 3 | TQM must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | DR Four Beat must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-025-2014 | DR Four Beat Energy Corp. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | DR Four Beat must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 1 | Kaiser must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-026-2014 | Kaiser Exploration Ltd. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta | 2 | Kaiser must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 1 | Husky, Husky Energy Inc. and Husky Oil Limited must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-028-2014 | Husky Oil Operations Limited | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia , Prince Albert/Saskatchewan, Camrose--Drumheller/Alberta | 2 | Husky, Husky Energy Inc. and Husky Oil Limited must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 1 | Spectra Empress must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Spectra Empress must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Empress' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Spectra Empress' proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Empress must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-101-2014 | Spectra Energy Empress Management Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan, North Central /Manitoba | 3 | Spectra Empress may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Empress chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Westspur must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Westspur must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Westspur's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Westspur's proposed trustee;ii. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Westspur's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Westspur must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-103-2014 | Enbridge Pipelines (Westspur) Inc. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Southwest /Manitoba, Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Westspur may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If E nbridge Westspur chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Veresen must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-104-2014 | Veresen Energy Infrastructure Inc. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Veresen must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 1 | Pine Cliff must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-105-2014 | Pine Cliff Border Pipelines Limited | 2015-06-05 | 2015-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta | 2 | Pine Cliff must file, for Board approval, a letter of credit or surety bond consistent with the Reasons by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 1 | Foothills must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 2 | Foothills must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Foothills' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Foothills' proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Foothills' annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcha rge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-095-2014 | Foothills Pipe Lines Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Kootenay/British Columbia , Nechako/British Columbia , Swift Current--Moose Jaw/Saskatchewan, Banff--Jasper--Rocky Mountain House/Alberta, Calgary/Alberta | 3 | Foothills must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 1 | Keystone must implement and comply with the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 2 | Keystone must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Keystone's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Keystone's proposed trustee;b. a collection mechanism filing, by 5 December 20 L4, consi tent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Keystone's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-099-2014 | TransCanada Keystone Pipeline GP Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Yorkton--Melville/Saskatchewan, Swift Current--Moose Jaw/Saskatchewan, Southwest /Manitoba, Camrose--Drumheller/Alberta, North Central /Manitoba, Lethbridge--Medicine Hat/Alberta, Regina--Moose Mountain/Saskatchewan | 3 | Keystone must file with the Board the statement of inve tment policy and procedure applicable to its trust by 1 December 20 L4 | Closed | Unspecified | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 1 | Spectra Midstream must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 2 | Subject to Clause 3 of this Order:a. Spectra Midstream must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Spectra Midstream's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof Spectra Midstream's proposed trustee;ii. an annual contribution amount filing, by 31 December 2014, consistent with the findings, directions and decisions set out in the Reasons;b. Spectra Midstream must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-100-2014 | Spectra Energy Midstream Canada Partner Corporation | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northeast /British Columbia | 3 | Spectra Midstream may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Spectra Midstream chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Safety Management
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Union must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Union must, for Board approval, make a set-aside mechanism filing, by 2 September 2014, containing: (i) Union's proposed form of trust agreement that is consistent with the finding , directions and decisions set out in the Reason , and (ii) the identity of Union's proposed trustee;b. Union must file with the Board a revised investment strategy, including the statement of investment policy and procedure applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-089-2014 | Union Gas Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | Union may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Union chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 1 | M&NP must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 2 | M&NP must make the following filings for Board approval:a. a set-aside mechani sm filing, by 2 September 201 4, containing: (i) M&NP's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of M&NP's proposed trustee;b. a collection mechani sm filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Rea ons. The collection mechanism filing must set out M&NP's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism propo. ed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-091-2014 | Maritimes &Northeast Pipeline Management Ltd | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Halifax/Nova Scotia , North Shore /Nova Scotia , Moncton--Richibucto/New Brunswick , Fredericton--Oromocto/New Brunswick , Saint John--St. Stephen/New Brunswick , Cape Breton/Nova Scotia | 3 | M&NP may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If M&NP chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 1 | Westcoast must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 2 | Westcoast must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Westcoast's proposed form of trust agreement that is cons istent with the findings, directions and decisions set out in the Reasons, and (i i) the identity of Westcoast's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out any applicable annual contribution amount, toll surcharge for each path or service, true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-092-2014 | Westcoast Energy Inc., carrying on business as Spectra Energy Transmission | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Yukon/Yukon, Athabasca--Grande Prairie--Peace River/Alberta, Lower Mainland--Southwest /British Columbia , Thompson--Okanagan/British Columbia , Northwest Territories /Northwest Territories , Cariboo/British Columbia | 3 | Westcoast must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Alliance must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Alliance must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Alliance's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Alliance's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Alliance's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-093-2014 | Alliance Pipeline Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan, Edmonton/Alberta, Banff--Jasper--Rocky Mountain House/Alberta, Camrose--Drumheller/Alberta, Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Alliance must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 1 | Enbridge NW must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 2 | Enbridge NW must make the following filings for Board approval:a. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge NW's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge NW's proposed trustee;b. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge NW's annual contribution amount (using the form in Appendix XIV of the Reasons), toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing aJJ changes black-lined from the current version together with a clean version; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-094-2014 | Enbridge Pipelines (NW) Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Athabasca--Grande Prairie--Peace River/Alberta, Northwest Territories /Northwest Territories | 3 | Enbridge NW must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 1 | Enbridge Southern Lights must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 2 | Subject to Clause 3 of this Order:a. Enbridge Southern Lights must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Southern Lights' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Southern Lights' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Southern Lights' annual contribution amount, any toll impacts applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Southern Lights must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014;"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-083-2014 | Enbridge Southern Lights GP on behalf of Enbridge Southern Lights L.P. | 2014-06-04 | 2014-06-04 |  | All Conditions Met | Camrose--Drumheller/Alberta, Edmonton/Alberta, Regina--Moose Mountain/Saskatchewan, South Central /Manitoba | 3 | Enbridge Southern Lights may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Southern Lights chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 1 | Pouce Coupé must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 2 | Subject to Clause 3 of this Order:a. Pouce Coupe must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Pouce Coupe's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Pouce Coupe's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Pouce Coupe's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Pouce Coupe must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-086-2014 | Pouce Coupé Pipe Line Ltd. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northeast /British Columbia , Athabasca--Grande Prairie--Peace River/Alberta | 3 | Pouce Coupé may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Pouce Coupé chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | St. Clair must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. St. Clair must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) St. Clair's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of St. Clair's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out St. Clair's annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version; andb. St. Clair must file with the Board a revised investment strategy, including the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-087-2014 | St. Clair Pipelines Management Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 3 | St. Clair may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If St. Clair chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Souris Valley must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order,a. Souris Valley must make the following filings:i. a set-aside mechanism fi ling, by 2 September 2014, containing Souris Valley's draft trust agreement that is consistent with the findings, directions and decisions set out in the Reasons;ii. the statement of investment policy and procedures applicable to its trust by 1 December 20 14. Souris Valley must make this filing only if the trust's SIPP is different from the SIPP provided by Souris Valley on the record of the MO-001-2013 proceeding;b. Souris Valley must, by 2 September 201 4, seek Board approval of its proposed trustee ; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-088-2014 | Souris Valley Pipeline Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Souris Valley may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Souris Valley chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 1 | 2193914 must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-077-2014 | 2193914 Canada Limited | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Toronto/Ontario | 2 | Subject to Clause 3 of this Order:a. 2193914 Canada must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) 2193914 Canada's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identityof 2193914 Canada's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out 2193914 Canada's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. 2193914 Canada must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 1 | Centra Transmission must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 2 | Subject to Clause 3 of this Order:a. Centra Transmission must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Centra Transmission's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Centra Transmission's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Centra Transmission's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Centra Transmission must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-078-2014 | Centra Transmission Holdings Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Northwest /Ontario, Southeast /Manitoba | 3 | Centra Transmission may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Centra Transmission chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 1 | Enbridge Bakken must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 2 | Subject to Clause 3 of this Order:a. Enbridge Bakken must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Enbridge Bakken's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Enbridge Bakken's proposed trustee;ii. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Enbridge Bakken's annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Enbridge Bakken must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-079-2014 | Enbridge Bakken Pipeline Company Inc. | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Regina--Moose Mountain/Saskatchewan | 3 | Enbridge Bakken may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Enbridge Bakken chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014. | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 1 | Express must implement the findings, directions and decisions set out in the Reasons | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 2 | Subject to Clause 3 of this Order:a. Express must make the following filings for Board approval:i. a set-aside mechanism filing, by 2 September 2014, containing: (i) Express' proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Express' proposed trustee;n. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Express' annual contribution amount, tollsurcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all changes black-lined from the current version together with a clean version;b. Express must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-080-2014 | Express Pipeline Ltd. | 2014-06-05 | 2014-06-05 |  | All Conditions Met | Lethbridge--Medicine Hat/Alberta, Camrose--Drumheller/Alberta | 3 | Express may choose to use a letter of credit or surety bond consistent with the Reasons as a set-aside mechanism. If Express chooses to use a letter of credit or a surety bond, it must notify the Board by 2 September 2014, and file the letter of credit or surety bond by 31 December 2014 | Closed | Not Construction Related | Standard | Filing Not Required | Financial
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 1 | Vector must implement the findings, directions and decisions set out in the Reasons; and | Closed | Not Construction Related | Standard | Filing Not Required | Administrative
Canada Border Services Agency | SAM/COM | SAM/COM | Completed | MO-082-2014 | Vector Pipeline Limited Partnership | 2014-05-05 | 2014-05-05 |  | All Conditions Met | Windsor--Sarnia/Ontario | 2 | Subject to Clause 3 of this Order:a. Vector must make the following filings for Board approval:1. a set-aside mechanism filing, by 2 September 2014, containing: (i) Vector's proposed form of trust agreement that is consistent with the findings, directions and decisions set out in the Reasons, and (ii) the identity of Vector's proposed trustee;11. a collection mechanism filing, by 5 December 2014, consistent with the findings, directions and decisions set out in the Reasons. The collection mechanism filing must set out Vector· s annual contribution amount, toll surcharge applicable to each path or service, any true-up mechanism proposed and revised tariff sheets showing all change black-lined from the current version together with a clean version;b. Vector must file with the Board the statement of investment policy and procedures applicable to its trust by 1 December 2014; and"" | Closed | Not Construction Related | Standard | Filing Not Required | Financial